## Contract Clause Library
Clause / Topic | Location | Plain English Meaning | Beneath the Lines | Who Holds Leverage | Notice / Time Bar | Money Impact | Schedule Impact | Practical Action / Evidence | Source File | Claim Type | Risk Level | Claim Strength | Exact Clause Text
Agreement Summary | 1 | Defines the synthetic agreement framework, parties, scope, contract amount, commencement basis, and key delivery obligations for Nasr city-Tunnel. | Tie every entitlement position to the agreement particulars and the accepted project-control baseline. | Shared | Yes | Possible | Yes | Agreement, contract data, commencement record, baseline programme, access evidence, and correspondence. | Nasr_city_Tunnel_Overall_Contract.pdf | Contract Foundation | Medium | Strong | 1. Agreement Summary - Nasr city-Tunnel; Contract No. NCT-CTR-2026-017; effective 03-Feb-2026.
Time for Completion | 1 | The contractual completion period is 26 months from the Commencement Date. | A delay claim must distinguish contractual completion, forecast completion, and any approved extension. | Shared | Yes | Possible | Yes | Accepted baseline, monthly updates, milestone records, recovery programmes, and critical-path analysis. | Nasr_city_Tunnel_Overall_Contract.pdf | Notice Compliance | High | Strong | Time for Completion: 26 months from the Commencement Date.
Document Priority | 2 | Establishes the order used to resolve inconsistencies between contract documents. | A lower-priority drawing or requirement cannot silently override a higher-priority contractual obligation. | Shared | Unclear | Possible | Possible | Complete document set, revision register, conflict matrix, and formal clarification correspondence. | Nasr_city_Tunnel_Overall_Contract.pdf | Document Interpretation | Medium | Medium | 2. Document Priority.
This Agreement | 2.1 | The signed agreement has first priority in the synthetic document hierarchy. | Use the agreement to anchor party names, contract amount, effective date, and principal obligations. | Shared | Unclear | Possible | Possible | Executed agreement, amendments, and signature records. | Nasr_city_Tunnel_Overall_Contract.pdf | General Contract Risk | Low | Medium | 1. This Agreement.
Appendix to Tender / Contract Data | 2.2 | The contract data supplements the agreement with project-specific commercial and time requirements. | Project-specific entries should prevail over generic wording where the priority clause permits. | Shared | Unclear | Possible | Possible | Appendix, tender clarifications, accepted programme requirements, and commercial schedules. | Nasr_city_Tunnel_Overall_Contract.pdf | General Contract Risk | Low | Medium | 2. Appendix to Tender / Contract Data.
Particular Conditions | 2.3 | The Particular Conditions modify or supplement the General Conditions. | Check every relied-upon general clause against any project-specific amendment. | Shared | Yes | Possible | Possible | Particular Conditions, clause comparison matrix, and legal review notes. | Nasr_city_Tunnel_Overall_Contract.pdf | General Contract Risk | Medium | Strong | 3. Particular Conditions.
General Conditions | 2.4 | The General Conditions provide the standard administrative and entitlement framework. | General wording remains subject to the higher-priority documents and Particular Conditions. | Shared | Yes | Possible | Possible | General Conditions, notices, determinations, and project records. | Nasr_city_Tunnel_Overall_Contract.pdf | General Contract Risk | Medium | Medium | 4. General Conditions.
General Requirements | 2.5 | Defines execution, reporting, quality, HSE, planning, and information-management requirements. | Non-compliance can weaken otherwise valid time or cost entitlement. | Employer / Engineer | Yes | Possible | Possible | Submittals, approvals, reports, method statements, QA/QC, and HSE records. | Nasr_city_Tunnel_Overall_Contract.pdf | Compliance Risk | High | Strong | 5. General Requirements.
Bill of Quantities | 2.6 | Provides the primary measurement and pricing structure for the synthetic works. | Separate quantity growth, scope change, and rate entitlement; do not treat them as the same issue. | Shared | Yes | Yes | Possible | BOQ, measurement sheets, instructions, quantity reconciliation, and cost build-up. | Nasr_city_Tunnel_Overall_Contract.pdf | Variation / Valuation | High | Strong | 6. Bill of Quantities.
Issued-for-Construction Drawings | 2.7 | IFC drawings define the construction information available for execution. | A late or conflicting IFC revision may support entitlement only when the affected work was otherwise ready. | Contractor | Yes | Possible | Yes | Drawing register, transmittals, RFIs, readiness evidence, and programme linkage. | Nasr_city_Tunnel_Overall_Contract.pdf | Design Information Delay | High | Strong | 7. Issued-for-Construction Drawings.
Site-interface documents | 2.8 | Utility surveys, traffic plans, geotechnical data, and interface matrices govern critical tunnel constraints. | Interface assumptions must be tested against actual access, utilities, and ground conditions. | Shared | Yes | Possible | Yes | Survey records, permits, obstruction logs, photographs, and daily reports. | Nasr_city_Tunnel_Overall_Contract.pdf | Site / Interface Risk | High | Medium | 8. Utility survey, traffic-management plan, geotechnical report, and site-interface matrix.
Commercial Data | 3 | Sets the synthetic advance payment, retention, security, payment, damages, and adjustment rules. | Commercial entitlement depends on both the clause wording and auditable valuation records. | Contractor | Yes | Yes | Possible | Contract data, IPCs, certificates, payment receipts, securities, and notices. | Nasr_city_Tunnel_Overall_Contract.pdf | Payment / Certification | High | Strong | 3. Commercial Data.
Advance Payment | 3.1 | Advance payment is 18%, structured as 35% cash and 65% Employer-supplied steel/material support. | Treat cash release and free-issue material availability as separate factual and contractual streams. | Contractor | Yes | Yes | Yes | Guarantees, payment records, approved programme, requisitions, delivery notes, and stock ledger. | Nasr_city_Tunnel_Overall_Contract.pdf | Advance Payment / Materials | Critical | Strong | 18% structured as 35% cash advance and 65% Employer-supplied steel/material support.
Retention | 3.2 | Retention is 7.5% of the Contract Price. | Confirm the deduction basis, cap, release milestones, and treatment of variations. | Shared | Yes | Yes | No | IPCs, certificates, retention ledger, taking-over records, and release requests. | Nasr_city_Tunnel_Overall_Contract.pdf | Payment / Certification | Medium | Strong | Retention: 7.5% of the Contract Price.
Performance Security | 3.3 | Performance security is 10% of the Accepted Contract Amount unless formally amended. | Any reduction, extension, or release must be documented through the contract mechanism. | Employer | Yes | Yes | No | Security instrument, amendments, expiry tracker, and release correspondence. | Nasr_city_Tunnel_Overall_Contract.pdf | Security / Commercial | Medium | Medium | Performance Security: 10% of the Accepted Contract Amount.
Minimum IPC | 3.4 | The minimum IPC threshold is 70% of approved monthly cash flow. | Low monthly valuation can defer certification even where measured work exists. | Shared | Yes | Yes | Possible | Cash flow, measured work, material-on-site records, statement, and certificate. | Nasr_city_Tunnel_Overall_Contract.pdf | Payment / Certification | High | Strong | Minimum IPC: 70% of the approved monthly cash-flow value.
Payment Period | 3.5 | Payment is due 42 days after receipt of a complete monthly statement. | The due date depends on completeness, receipt evidence, certification steps, and any valid deductions. | Contractor | Yes | Yes | Possible | Statement submission, receipt confirmation, certificate, bank record, and payment notice. | Nasr_city_Tunnel_Overall_Contract.pdf | Payment / Certification | Critical | Strong | Payment Period: 42 days after receipt of a complete monthly statement.
Delay Damages | 3.6 | Delay damages are 0.50% of outstanding works per week, capped at 8% of the Contract Price. | Defence depends on excusable delay, approved EOT, concurrency treatment, and the proper outstanding-work basis. | Shared | Yes | Yes | Yes | EOT notices, critical-path analysis, milestone status, concurrency review, and mitigation records. | Nasr_city_Tunnel_Overall_Contract.pdf | Delay Damages Defense | Critical | Strong | Delay Damages: 0.50% per week, capped at 8% of the Contract Price.
Programme and Progress | 4 | Requires a maintained P6 baseline, periodic updates, narratives, cash flow, procurement curves, and recovery programmes. | Programme compliance is both an obligation and the evidential platform for delay entitlement. | Engineer | Yes | Possible | Yes | Accepted baseline, updates, narratives, logs, curves, and recovery submissions. | Nasr_city_Tunnel_Overall_Contract.pdf | Programme Compliance | High | Strong | 4. Programme, Progress, and Delay Entitlement.
Extension of Time | 4.2 | EOT requires demonstrated critical or longest-path impact using an approved delay-analysis method. | A late event alone is insufficient without logic, criticality, timing, and causation. | Contractor | Yes | Possible | Yes | Notice, chronology, TIA or windows analysis, source programme, contemporaneous records, and mitigation evidence. | Nasr_city_Tunnel_Overall_Contract.pdf | Extension of Time | Critical | Strong | EOT entitlement must demonstrate delay to the critical or longest path using an approved method.
Concurrent Delay | 4.4 | Concurrency must be assessed by responsibility, timing, affected activities, float, and actual programme effect. | Broad project-level overlap is not enough; the overlap must be analysed at event and path level. | Shared | Yes | Yes | Yes | Concurrency matrix, event windows, path analysis, daily records, and resource evidence. | Nasr_city_Tunnel_Overall_Contract.pdf | Concurrency | Critical | Strong | Events must be separated by responsibility, timing, affected activities, float, criticality, and actual effect.
Claims Time Bar | 4.5 | Delay, disruption, variation, payment, and access claims must be notified within the contractual period. | Maintain a continuing notice trail where the event and its consequences evolve over time. | Employer / Engineer | Yes | Yes | Yes | Notice register, claim register, correspondence, proof of receipt, and updated particulars. | Nasr_city_Tunnel_Overall_Contract.pdf | Notice Compliance | Critical | Strong | Claims must be notified within the contractual period and fully substantiated.
Site Access and Interfaces | 5.1 | Access must permit practical execution of tunnel, traffic, utility, and dewatering activities. | Record the difference between nominal possession and usable access. | Contractor | Yes | Possible | Yes | Access records, permits, traffic plans, photographs, obstruction logs, and daily reports. | Nasr_city_Tunnel_Overall_Contract.pdf | Site Access Delay | High | Strong | Site access and possession must permit practical execution of the Nasr city-Tunnel scope.
Employer Free-Issue Materials | 5.2 | Employer material support applies only to approved items requested against the accepted programme. | Entitlement depends on timely requisition, demonstrated readiness, delivery shortage, consumption, and path impact. | Contractor | Yes | Yes | Yes | Requisitions, delivery notes, inspections, storage records, consumption logs, and fragnet analysis. | Nasr_city_Tunnel_Overall_Contract.pdf | Employer Material Delay | Critical | Strong | Shortage, late delivery, or defect records must be supported by requisitions and delivery evidence.
Execution Control Matrix | 7 | Maps contract evidence to dashboard, payment, TIA, material, quality, and HSE workflows. | The matrix should drive document-control completeness checks and claim-strength scoring. | Shared | Unclear | Possible | Possible | Evidence index, dashboard mappings, workflow controls, and data-quality checks. | Nasr_city_Tunnel_Overall_Contract.pdf | Evidence / Substantiation | Medium | Strong | 7. Execution Control Matrix.
Signature Placeholders | 8 | Provides synthetic execution blocks for Employer, Contractor, and Engineer / PMO acknowledgement. | Unsigned placeholders do not create execution or acknowledgement. | Shared | Unclear | No | No | Executed signature pages, authority documents, amendments, and acknowledgements. | Nasr_city_Tunnel_Overall_Contract.pdf | Execution Formality | Low | Weak | 8. Signature Placeholders.