## Slide 1
SAMCO-PCO Project Controls Report
LMD Bridge & Road Interchange | 30 data-driven control sections | 2026-08-13T19:10:40+00:00

## Slide 2
PRO-TIA-01 | Time Impact & Extension of Time
AWAITING CONTROLLED CSV DATA
CSV sources
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (0 rows)
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 3
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (5 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
LMD-Bridge | Delay in employer free issue steel supply | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | Late IFC / design clarification | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | Delayed RFI response | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | Access constraint and traffic diversion | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26
LMD-Bridge | MEP sleeve coordination delay | CON-LB-ROAD-1050 | Approach road embankment and pavement | 27-Aug-26 | 30-Nov-26

## Slide 4
PRO-PRG-03 | Project Progress
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
progress: 01-data/import_templates/progress_updates.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 5
PRO-REC-04 | Recovery & Mitigation
DATA AVAILABLE
CSV sources
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (0 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 6
PRO-VAR-05 | Variation Report
DATA AVAILABLE
CSV sources
claims: 01-data/import_templates/claims.csv (2 rows)
project_id | claim_id | contract_id | claim_event_ref | claim_title | notice_date
LMD-Bridge | CL-001 | LB-PH-01 | DE-001 | Employer free issue steel delay | 3-Mar-26
LMD-Bridge | CL-002 | LB-PH-01 | DE-002 | Late IFC and RFI response impact | 30-Mar-26

## Slide 7
PRO-IPC-06 | Interim Payment
DATA AVAILABLE
CSV sources
payments: 01-data/import_templates/payments.csv (6 rows)
project_id | payment | contract | project | invoice no | invoice date
LMD-Bridge | 1.0 | LB-PH-01 | LMD-Bridge | 1.0 | 18-Feb-26
LMD-Bridge | 2.0 | LB-PH-01 | LMD-Bridge | 2.0 | 20-Mar-26
LMD-Bridge | 3.0 | LB-PH-01 | LMD-Bridge | 3.0 | 19-Apr-26
LMD-Bridge | 4.0 | LB-PH-01 | LMD-Bridge | 4.0 | 19-May-26
LMD-Bridge | 5.0 | LB-PH-01 | LMD-Bridge | 5.0 | 18-Jun-26
LMD-Bridge | 6.0 | LB-PH-01 | LMD-Bridge | 6.0 | 18-Jul-26

## Slide 8
PRO-RES-07 | Resource & Manpower
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 9
PRO-EQP-08 | Equipment & Plant
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 10
PRO-CST-09 | Cost Control
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
LMD-Bridge | KD-MS-1000 | Project Start Date | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MS-1010 | Contract Agreement | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MS-1020 | IFC Drawing Package | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MOB-1000 | Mobilization and traffic diversion setup | May-26 | 20481927.71 | 21710843.37
LMD-Bridge | SUR-LB-1010 | Survey control and utility relocation setting out | May-26 | 20481927.71 | 21710843.37
LMD-Bridge | E-SUB-LB-1020 | Bridge substructure shop drawings | May-26 | 30722891.57 | 24567990.36
LMD-Bridge | E-APP-LB-1020 | Approval of pier and deck shop drawings | May-26 | 30722891.57 | 18693036.14
LMD-Bridge | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | May-26 | 51204819.28 | 24478975.90
LMD-Bridge | CON-LB-PIL-1010 | Bored piles and pile caps | May-26 | 102409638.55 | 75662289.16
LMD-Bridge | CON-LB-RFT-1020 | RFT for piers and abutments | May-26 | 102409638.55 | 51628385.54
LMD-Bridge | CON-LB-CON-1030 | Concrete works for piers and abutments | May-26 | 102409638.55 | 32045204.82
LMD-Bridge | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | May-26 | 102409638.55 | 7121156.63

## Slide 11
PRO-EVM-10 | Earned Value
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
LMD-Bridge | KD-MS-1000 | Project Start Date | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MS-1010 | Contract Agreement | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MS-1020 | IFC Drawing Package | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MOB-1000 | Mobilization and traffic diversion setup | May-26 | 20481927.71 | 21710843.37
LMD-Bridge | SUR-LB-1010 | Survey control and utility relocation setting out | May-26 | 20481927.71 | 21710843.37
LMD-Bridge | E-SUB-LB-1020 | Bridge substructure shop drawings | May-26 | 30722891.57 | 24567990.36
LMD-Bridge | E-APP-LB-1020 | Approval of pier and deck shop drawings | May-26 | 30722891.57 | 18693036.14
LMD-Bridge | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | May-26 | 51204819.28 | 24478975.90
LMD-Bridge | CON-LB-PIL-1010 | Bored piles and pile caps | May-26 | 102409638.55 | 75662289.16
LMD-Bridge | CON-LB-RFT-1020 | RFT for piers and abutments | May-26 | 102409638.55 | 51628385.54
LMD-Bridge | CON-LB-CON-1030 | Concrete works for piers and abutments | May-26 | 102409638.55 | 32045204.82
LMD-Bridge | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | May-26 | 102409638.55 | 7121156.63

## Slide 12
PRO-CFS-11 | Cash Flow
DATA AVAILABLE
CSV sources
planned_cash_flow: 01-data/import_templates/planned_cash_flow.csv (0 rows)
payments: 01-data/import_templates/payments.csv (6 rows)
project_id | payment | contract | project | invoice no | invoice date
LMD-Bridge | 1.0 | LB-PH-01 | LMD-Bridge | 1.0 | 18-Feb-26
LMD-Bridge | 2.0 | LB-PH-01 | LMD-Bridge | 2.0 | 20-Mar-26
LMD-Bridge | 3.0 | LB-PH-01 | LMD-Bridge | 3.0 | 19-Apr-26
LMD-Bridge | 4.0 | LB-PH-01 | LMD-Bridge | 4.0 | 19-May-26
LMD-Bridge | 5.0 | LB-PH-01 | LMD-Bridge | 5.0 | 18-Jun-26
LMD-Bridge | 6.0 | LB-PH-01 | LMD-Bridge | 6.0 | 18-Jul-26

## Slide 13
PRO-SCV-12 | S-Curve
DATA AVAILABLE
CSV sources
s_curve: 01-data/import_templates/s_curve.csv (10 rows)
project_id | months | monthly_planned | cumm_monthly_planned | monthly_actual | cumm_monthly_actual
LMD-Bridge | 1-Nov-25 | 17000000.00 | 17000000.00 | 11849000.00 | 11849000.00
LMD-Bridge | 1-Dec-25 | 34000000.00 | 51000000.00 | 24534400.00 | 36383400.00
LMD-Bridge | 1-Jan-26 | 59500000.00 | 110500000.00 | 44398900.00 | 80782300.00
LMD-Bridge | 1-Feb-26 | 85000000.00 | 195500000.00 | 65518000.00 | 146300300.00
LMD-Bridge | 1-Mar-26 | 102000000.00 | 297500000.00 | 81130800.00 | 227431100.00
LMD-Bridge | 1-Apr-26 | 119000000.00 | 416500000.00 | 97580000.00 | 325011100.00
LMD-Bridge | 1-May-26 | 110500000.00 | 527000000.00 | 93328300.00 | 418339400.00
LMD-Bridge | 1-Jun-26 | 102000000.00 | 629000000.00 | 88658400.00 | 506997800.00
LMD-Bridge | 1-Jul-26 | 85000000.00 | 714000000.00 | 60222500.00 | 567220300.00
LMD-Bridge | 1-Aug-26 | 68000000.00 | 782000000.00 | 49504000.00 | 616724300.00

## Slide 14
PRO-PRC-13 | Procurement Status
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 15
PRO-MAT-14 | Material Status
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 16
PRO-LAH-15 | Labour Hours
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 17
PRO-CPM-16 | Critical Path
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 18
PRO-FLT-17 | Float Analysis
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 19
PRO-MIL-18 | Milestone Status
DATA AVAILABLE
CSV sources
milestones: 01-data/import_templates/milestones.csv (5 rows)
milestone_id | project_id | activity_name | planned_date | forecast_date | actual_date
KD-MS-1000 | LMD-Bridge | Project Start Date | 5-Nov-25 | 5-Nov-25 | 5-Nov-25
KD-MS-1010 | LMD-Bridge | Contract Agreement | 5-Nov-25 | 5-Nov-25 | 5-Nov-25
KD-MS-1020 | LMD-Bridge | IFC Drawing Package | 12-Nov-25 | 3-Dec-25 | 12-Nov-25
KD-MS-5000 | LMD-Bridge | Structural Works Completion | 5-Nov-26 | 7-Jan-27 | 
KD-MS-9000 | LMD-Bridge | Substantial Completion | 20-Mar-27 | 9-Jun-27 | 

## Slide 20
PRO-RSK-19 | Risk Report
DATA AVAILABLE
CSV sources
risks: 01-data/import_templates/risks.csv (3 rows)
risk_id | project_id | risk_title | risk_category | probability | time_impact_days
R-001 | LMD-Bridge | Steel delivery delay | Schedule | high | yes
R-002 | LMD-Bridge | Late design clarification and IFC revisions | Engineering | medium | yes
R-003 | LMD-Bridge | Cashflow pressure due to delayed certification | Commercial | medium | no

## Slide 21
PRO-RFI-20 | RFI & Submittals
AWAITING CONTROLLED CSV DATA
CSV sources
rfi: 02-delay_analysis/unified_tia_csv/09- rfi_status.csv (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 22
PRO-QAQC-21 | QA/QC Performance
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 23
PRO-PROD-22 | Productivity
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
progress: 01-data/import_templates/progress_updates.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 24
PRO-EXE-23 | Executive Report
DATA AVAILABLE
CSV sources
projects: 01-data/import_templates/projects.csv (1 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
evm: 01-data/import_templates/evm.csv (17 rows)
risks: 01-data/import_templates/risks.csv (3 rows)
project_id | project_name | client_name | contractor | planned_start | planned_finish
LMD-Bridge | LMD Bridge & Road Interchange | LMD Infrastructure Company | Prime Roads & Bridges | 5-Nov-25 | 20-Mar-27

## Slide 25
PRO-BLC-24 | Baseline vs Current
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 26
PRO-FCF-25 | Forecast Completion
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 27
PRO-ML-26 | ML Project Controls
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
evm: 01-data/import_templates/evm.csv (17 rows)
risks: 01-data/import_templates/risks.csv (3 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26

## Slide 28
PRO-CAD-27 | Contract Administration
DATA AVAILABLE
CSV sources
contracts: 01-data/import_templates/contracts.csv (2 rows)
claims: 01-data/import_templates/claims.csv (2 rows)
contract_id | project_id | package | contractor | contract_type | original_value
LB-PH-01 | LMD-Bridge | 1 | Prime Roads & Bridges | Unit rate | 850000000
LB-PH-02 | LMD-Bridge | 2 | Prime Roads & Bridges | Lump sum | 153000000

## Slide 29
PRO-CHG-28 | Change Control
DATA AVAILABLE
CSV sources
claims: 01-data/import_templates/claims.csv (2 rows)
project_id | claim_id | contract_id | claim_event_ref | claim_title | notice_date
LMD-Bridge | CL-001 | LB-PH-01 | DE-001 | Employer free issue steel delay | 3-Mar-26
LMD-Bridge | CL-002 | LB-PH-01 | DE-002 | Late IFC and RFI response impact | 30-Mar-26

## Slide 30
PRO-DOC-29 | Document Control
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 31
PRO-IFC-30 | Interface Management
AWAITING CONTROLLED CSV DATA
CSV sources
ifc: 02-delay_analysis/unified_tia_csv/07- ifc_conflict.csv (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.