## Slide 1
SAMCO-PCO PRO-REC-04 Recovery & Mitigation Report
LMD Bridge & Road Interchange | 1 data-driven control section | 2026-08-15T05:30:57+00:00

## Slide 2
PRO-REC-04 | Recovery & Mitigation
DATA AVAILABLE
CSV sources
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (0 rows)
activities: 01-data/import_templates/project_input_bundle.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1000 | Project Start Date | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1010 | Contract Agreement | 5-Nov-25 | 
LMD-Bridge | LMD-Bridge.MILESTONE | KD-MS-1020 | IFC Drawing Package | 12-Nov-25 | 
LMD-Bridge | LMD-Bridge.MOBILIZATION | KD-MOB-1000 | Mobilization and traffic diversion setup | 9-Nov-25 | 9-Dec-25
LMD-Bridge | LMD-Bridge.SURVEY | SUR-LB-1010 | Survey control and utility relocation setting out | 27-Nov-25 | 19-Dec-25
LMD-Bridge | LMD-Bridge.ENGINEERING | E-SUB-LB-1020 | Bridge substructure shop drawings | 20-Dec-25 | 24-Jan-26
LMD-Bridge | LMD-Bridge.ENGINEERING | E-APP-LB-1020 | Approval of pier and deck shop drawings | 26-Jan-26 | 27-Feb-26
LMD-Bridge | LMD-Bridge.PROCUREMENT | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | 14-Jan-26 | 25-Mar-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | LMD-Bridge.CONSTRUCTION | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26