## Slide 1
SAMCO-PCO PRO-TIA-01 Time Impact & Extension of Time Report
Nasr city-Tunnel | 1 data-driven control section | 2026-08-15T05:31:06+00:00

## Slide 2
PRO-TIA-01 | Time Impact & Extension of Time
DATA AVAILABLE
CSV sources
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (6 rows)
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (6 rows)
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
project_id | event_id | activity_id | root_cause | delay_type | entitlement_status
Nasr city-Tunnel | EV-01 | NCT-ST-CLB-RFT-1100 | Employer steel delivery below approved requirement | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-02 | NCT-ST-PMP-RFT-1200 | Late revised IFC bearing-pedestal detail | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-03 | NCT-ST-CLR-RFT-1300 | Clarifier waterstop and embedded-pipe conflict | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-04 | NCT-ST-FLT-RFT-1400 | Delayed response to filter gallery opening RFI | Excusable Compensable | Under Assessment
Nasr city-Tunnel | EV-05 | NCT-ST-RES-RFT-1500 | Outstanding high-diameter employer steel | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-06 | NCT-ST-ADM-RFT-1600 | Delayed interim payment certification | Commercial / Potential Compensable | Under Assessment