## Slide 1
SAMCO-PCO PRO-REC-04 Recovery & Mitigation Report
Nasr city-Tunnel | 1 data-driven control section | 2026-08-15T05:31:06+00:00

## Slide 2
PRO-REC-04 | Recovery & Mitigation
DATA AVAILABLE
CSV sources
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (6 rows)
activities: 01-data/import_templates/project_input_bundle.csv (17 rows)
project_id | scenario_id | scenario_name | analyst_status | activity_id | status_date
Nasr city-Tunnel | SCN-01 | Steel priority delivery and two reinforcement crews | Approved for Modelling | NCT-ST-CLB-RFT-1100 | 2026-07-31
Nasr city-Tunnel | SCN-02 | Pump hall revised sequence with extended shift | Approved for Modelling | NCT-ST-PMP-RFT-1200 | 2026-07-31
Nasr city-Tunnel | SCN-03 | Clarifier segmented pour and parallel embedded works | Approved for Modelling | NCT-ST-CLR-RFT-1300 | 2026-07-31
Nasr city-Tunnel | SCN-04 | Filter gallery additional fixing gang | Candidate | NCT-ST-FLT-RFT-1400 | 2026-07-31
Nasr city-Tunnel | SCN-05 | Reservoir prioritized steel diameters and night shift | Recommended | NCT-ST-RES-RFT-1500 | 2026-07-31
Nasr city-Tunnel | SCN-06 | Administration foundation subcontract package | Candidate | NCT-ST-ADM-RFT-1600 | 2026-07-31