## Slide 1
SAMCO-PCO PRO-FLT-17 Float Analysis Report
Nasr city-Tunnel | 1 data-driven control section | 2026-08-15T05:31:06+00:00

## Slide 2
PRO-FLT-17 | Float Analysis
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/project_input_bundle.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26