## Slide 1
SAMCO-PCO PRO-CPM-16 Critical Path Report
Sophia Mall Mixed-Use Development | 1 data-driven control section | 2026-08-15T05:31:03+00:00

## Slide 2
PRO-CPM-16 | Critical Path
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/project_input_bundle.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Sophia-Mall | Sophia-Mall.MILESTONE | KD-MS-1000 | Project Start Date | 15-Oct-25 | 
Sophia-Mall | Sophia-Mall.MILESTONE | KD-MS-1010 | Contract Agreement | 15-Oct-25 | 
Sophia-Mall | Sophia-Mall.MILESTONE | KD-MS-1020 | IFC Drawing Package | 25-Oct-25 | 
Sophia-Mall | Sophia-Mall.MOBILIZATION | KD-MOB-1000 | Mobilization and site logistics setup | 17-Oct-25 | 18-Nov-25
Sophia-Mall | Sophia-Mall.SURVEY | SUR-SM-1010 | Surveying and benchmark establishment | 5-Nov-25 | 23-Nov-25
Sophia-Mall | Sophia-Mall.ENGINEERING | E-SUB-SM-1020 | Structural and architectural shop drawings | 22-Nov-25 | 6-Jan-26
Sophia-Mall | Sophia-Mall.ENGINEERING | E-APP-SM-1020 | Approval of podium and basement drawings | 5-Jan-26 | 10-Feb-26
Sophia-Mall | Sophia-Mall.PROCUREMENT | P-MDEL-SM-1000 | Long lead procurement for steel and MEP sleeves | 24-Dec-25 | 2-Mar-26
Sophia-Mall | Sophia-Mall.CONSTRUCTION | CON-SM-EXC-1010 | Bulk excavation and dewatering | 9-Dec-25 | 19-Mar-26
Sophia-Mall | Sophia-Mall.CONSTRUCTION | CON-SM-RFT-1020 | RFT for raft foundation | 22-Feb-26 | 30-Mar-26
Sophia-Mall | Sophia-Mall.CONSTRUCTION | CON-SM-CON-1030 | Raft foundation concrete works | 30-Mar-26 | 29-Apr-26
Sophia-Mall | Sophia-Mall.CONSTRUCTION | CON-SM-B1-1040 | Basement B1 columns and walls | 29-Apr-26 | 26-Jun-26