## Slide 1
SAMCO-PCO PRO-CST-09 Cost Control Report
Suez Tunnel Civil & MEP Works | 1 data-driven control section | 2026-08-15T05:31:08+00:00

## Slide 2
PRO-CST-09 | Cost Control
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/project_input_bundle.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
Suez-Tunnel | KD-MS-1000 | Project Start Date | May-26 | 15060240.96 | 15963855.42
Suez-Tunnel | KD-MS-1010 | Contract Agreement | May-26 | 15060240.96 | 15963855.42
Suez-Tunnel | KD-MS-1020 | IFC Drawing Package | May-26 | 15060240.96 | 15963855.42
Suez-Tunnel | KD-MOB-1000 | Mobilization and temporary facilities | May-26 | 30120481.93 | 31927710.84
Suez-Tunnel | SUR-ST-1010 | Topographic survey and utility detection | May-26 | 30120481.93 | 31927710.84
Suez-Tunnel | E-SUB-ST-1020 | Tunnel alignment shop drawings | May-26 | 45180722.89 | 39750000.00
Suez-Tunnel | E-APP-ST-1020 | Approval of tunnel alignment shop drawings | May-26 | 45180722.89 | 31800000.00
Suez-Tunnel | P-MDEL-ST-1000 | Delivery of waterproofing membrane and steel | May-26 | 75301204.82 | 47700000.00
Suez-Tunnel | CON-ST-EXC-1010 | Open cut excavation and shoring | May-26 | 150602409.64 | 108650000.00
Suez-Tunnel | CON-ST-RFT-1020 | RFT for base slab reinforcement | May-26 | 150602409.64 | 79500000.00
Suez-Tunnel | CON-ST-CON-1030 | Concrete casting for base slab | May-26 | 150602409.64 | 55650000.00
Suez-Tunnel | CON-ST-WALL-1040 | Tunnel wall reinforcement and formwork | May-26 | 150602409.64 | 33125000.00