## Slide 1
SAMCO-PCO PRO-FCF-25 Forecast Completion Report
Suez Tunnel Civil & MEP Works | 1 data-driven control section | 2026-08-15T05:31:08+00:00

## Slide 2
PRO-FCF-25 | Forecast Completion
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (17 rows)
evm: 01-data/import_templates/project_input_bundle.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Suez-Tunnel | Suez-Tunnel.MILESTONE | KD-MS-1000 | Project Start Date | 1-Sep-25 | 
Suez-Tunnel | Suez-Tunnel.MILESTONE | KD-MS-1010 | Contract Agreement | 1-Sep-25 | 
Suez-Tunnel | Suez-Tunnel.MILESTONE | KD-MS-1020 | IFC Drawing Package | 6-Sep-25 | 
Suez-Tunnel | Suez-Tunnel.MOBILIZATION | KD-MOB-1000 | Mobilization and temporary facilities | 4-Sep-25 | 2-Oct-25
Suez-Tunnel | Suez-Tunnel.SURVEY | SUR-ST-1010 | Topographic survey and utility detection | 19-Sep-25 | 11-Oct-25
Suez-Tunnel | Suez-Tunnel.ENGINEERING | E-SUB-ST-1020 | Tunnel alignment shop drawings | 6-Oct-25 | 10-Nov-25
Suez-Tunnel | Suez-Tunnel.ENGINEERING | E-APP-ST-1020 | Approval of tunnel alignment shop drawings | 12-Nov-25 | 7-Dec-25
Suez-Tunnel | Suez-Tunnel.PROCUREMENT | P-MDEL-ST-1000 | Delivery of waterproofing membrane and steel | 2-Nov-25 | 27-Dec-25
Suez-Tunnel | Suez-Tunnel.CONSTRUCTION | CON-ST-EXC-1010 | Open cut excavation and shoring | 29-Oct-25 | 27-Jan-26
Suez-Tunnel | Suez-Tunnel.CONSTRUCTION | CON-ST-RFT-1020 | RFT for base slab reinforcement | 28-Dec-25 | 25-Jan-26
Suez-Tunnel | Suez-Tunnel.CONSTRUCTION | CON-ST-CON-1030 | Concrete casting for base slab | 28-Jan-26 | 21-Feb-26
Suez-Tunnel | Suez-Tunnel.CONSTRUCTION | CON-ST-WALL-1040 | Tunnel wall reinforcement and formwork | 26-Feb-26 | 27-Apr-26