## Slide 1
SAMCO-PCO Project Controls Report
ROYA-BIG PROJECT PHASE01 (B1-4) | 30 data-driven control sections | 2026-08-15T05:31:00+00:00

## Slide 2
PRO-TIA-01 | Time Impact & Extension of Time
DATA AVAILABLE
CSV sources
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (0 rows)
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (1363 rows)
project_id | Activity ID | Activity Name | WBS | Baseline Start | Baseline Finish
The Big -P.01-UP-20-April-26 | KD-MS-1000 | Project Start Date | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1050 | Project Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 10-Apr-27
The Big -P.01-UP-20-April-26 | KD-MS-1040 | Ground Works Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 11-May-26
The Big -P.01-UP-20-April-26 | KD-MS-1010 | Contract Agreement | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1020 | IFC Drawing Package | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MOB-1000 | Surveying Works | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1010 | Equipment Mobilization | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1020 | Site Preparation | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | E-DR-1000 | Design Review | The Big - P.01 - UP-24-MAY-26.EN.1 | 11-Sep-25 | 09-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | 11-Sep-25 | 01-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 01-Oct-25 | 22-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1010 | Submittal for RC Raft & Footings Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 05-Oct-25 | 26-Oct-25

## Slide 3
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (25 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | 23-Dec-25 | 29-Dec-25
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | 6-Dec-25 | 18-Dec-25
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 13-Dec-25 | 21-Dec-25
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | 15-Jan-26 | 24-Jan-26
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | 21-Jan-26 | 27-Jan-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS02-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 02) | 20-Nov-25 | 16-Feb-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS02-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02) | 30-Nov-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS01-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 01) | 2-Nov-25 | 10-Mar-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS01-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 01) | 5-Nov-25 | 31-Mar-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B02-BAS02-1020 | Submittal for Beams Conc. Dim.& RFT DWGs (B02) (Bas 02) | 22-Oct-25 | 11-Nov-25
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B02-BAS02-1030 | Submittal for Slabs Conc. Dim.& RFT DWGs (B02) (Bas 02) | 26-Oct-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B02-BAS01-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B02) (Bas 01) | 2-Nov-25 | 23-Nov-25

## Slide 4
PRO-PRG-03 | Project Progress
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
progress: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 5
PRO-REC-04 | Recovery & Mitigation
DATA AVAILABLE
CSV sources
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (0 rows)
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 6
PRO-VAR-05 | Variation Report
DATA AVAILABLE
CSV sources
claims: 01-data/import_templates/claims.csv (1 rows)
project_id | claim_id | contract_id | claim_event_ref | claim_title | notice_date
The Big -P.01-UP-20-April-26 | 1 | PH-01 | 2 | Employer free issue material | 85

## Slide 7
PRO-IPC-06 | Interim Payment
DATA AVAILABLE
CSV sources
payments: 01-data/import_templates/payments.csv (8 rows)
project_id | payment | contract | project | invoice no | invoice date
The Big -P.01-UP-20-April-26 | 1.0 | Ph-01 | The Big -P.01-UP-20-April-26 | 1.0 | 6-Dec-25
The Big -P.01-UP-20-April-26 | 2.0 | Ph-01 | The Big -P.01-UP-20-April-26 | 2.0 | 29-Dec-25
The Big -P.01-UP-20-April-26 | 3.0 | Ph-01 | The Big -P.01-UP-20-April-26 | 3.0 | 24-Jan-26
The Big -P.01-UP-20-April-26 | 4.0 | Ph-01 | The Big -P.01-UP-20-April-26 | 4.0 | 25-Feb-26
The Big -P.01-UP-20-April-26 | 5.0 | Ph-01 | The Big -P.01-UP-20-April-26 | 5.0 | 25-Mar-26
The Big -P.01-UP-20-April-26 | 6.0 | Ph-01 | The Big -P.01-UP-20-April-26 | 6.0 | 26-Apr-26
The Big -P.01-UP-20-April-26 |  |  |  |  | 
The Big -P.01-UP-20-April-26 |  |  |  |  | 

## Slide 8
PRO-RES-07 | Resource & Manpower
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 9
PRO-EQP-08 | Equipment & Plant
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 10
PRO-CST-09 | Cost Control
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | activity_id | activity_name | period | BAC | AC
The Big -P.01-UP-20-April-26 | KD-MS-1000 | Project Start Date | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MS-1010 | Contract Agreement | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MS-1020 | IFC Drawing Package | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | P-MS-1000 | Submittal for RFT Rebar | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | E-DR-1000 | Design Review | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MOB-1000 | Surveying Works | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MOB-1010 | Equipment Mobilization | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MOB-1020 | Site Preparation | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | P-MS-1020 | Submittal for Soil Replacement | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | P-MS-1010 | Submittal for Plain Concrete | 17-May-26 | 0.0 | 0.0

## Slide 11
PRO-EVM-10 | Earned Value
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | activity_id | activity_name | period | BAC | AC
The Big -P.01-UP-20-April-26 | KD-MS-1000 | Project Start Date | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MS-1010 | Contract Agreement | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MS-1020 | IFC Drawing Package | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | P-MS-1000 | Submittal for RFT Rebar | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | E-DR-1000 | Design Review | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MOB-1000 | Surveying Works | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MOB-1010 | Equipment Mobilization | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | KD-MOB-1020 | Site Preparation | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | P-MS-1020 | Submittal for Soil Replacement | 17-May-26 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | P-MS-1010 | Submittal for Plain Concrete | 17-May-26 | 0.0 | 0.0

## Slide 12
PRO-CFS-11 | Cash Flow
DATA AVAILABLE
CSV sources
planned_cash_flow: 01-data/import_templates/planned_cash_flow.csv (18 rows)
payments: 01-data/import_templates/payments.csv (8 rows)
project_id | period_date | planned_cash_out | planned_cumulative_cash_out | currency | basis
The Big -P.01-UP-20-April-26 | 1-Oct-25 | 0 | 0 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Nov-25 | 8347296.45 | 8347296.45 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Dec-25 | 61405155.86 | 69752452.31 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Jan-26 | 67496644.02 | 137249096.3 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Feb-26 | 33633991.22 | 170883087.6 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Mar-26 | 38111113.51 | 208994201.1 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Apr-26 | 29721101.71 | 238715302.8 | EGP | 
The Big -P.01-UP-20-April-26 | 1-May-26 | 20259735.78 | 258975038.6 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Jun-26 | 13490432.04 | 272465470.6 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Jul-26 | 14762397.2 | 287227867.8 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Aug-26 | 9924530.76 | 297152398.6 | EGP | 
The Big -P.01-UP-20-April-26 | 1-Sep-26 | 12399329.58 | 309551728.1 | EGP | 

## Slide 13
PRO-SCV-12 | S-Curve
DATA AVAILABLE
CSV sources
s_curve: 01-data/import_templates/s_curve.csv (18 rows)
project_id | months | monthly_planned | cumm_monthly_planned | monthly_actual | cumm_monthly_actual
The Big -P.01-UP-20-April-26 | 1-Oct-25 | 0.0 | 0.0 | 3974600.57 | 3974600.57
The Big -P.01-UP-20-April-26 | 1-Nov-25 | 8347296.45 | 8347296.45 | 8089030.9 | 12063631.47
The Big -P.01-UP-20-April-26 | 1-Dec-25 | 61405155.86 | 69752452.31 | 8521118.53 | 20584750.0
The Big -P.01-UP-20-April-26 | 1-Jan-26 | 67496644.02 | 137249096.3 | 34796118.93 | 55380868.93
The Big -P.01-UP-20-April-26 | 1-Feb-26 | 33633991.22 | 170883087.6 | 20205303.35 | 75586172.28
The Big -P.01-UP-20-April-26 | 1-Mar-26 | 38111113.51 | 208994201.1 | 14348185.06 | 89934357.34
The Big -P.01-UP-20-April-26 | 1-Apr-26 | 29721101.71 | 238715302.8 | 17873350.85 | 107807708.2
The Big -P.01-UP-20-April-26 | 1-May-26 | 20259735.78 | 258975038.6 | 5277326.61 | 113085034.8
The Big -P.01-UP-20-April-26 | 1-Jun-26 | 13490432.04 | 272465470.6 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | 1-Jul-26 | 14762397.2 | 287227867.8 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | 1-Aug-26 | 9924530.76 | 297152398.6 | 0.0 | 0.0
The Big -P.01-UP-20-April-26 | 1-Sep-26 | 12399329.58 | 309551728.1 | 0.0 | 0.0

## Slide 14
PRO-PRC-13 | Procurement Status
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 15
PRO-MAT-14 | Material Status
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 16
PRO-LAH-15 | Labour Hours
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 17
PRO-CPM-16 | Critical Path
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (1363 rows)
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | Activity ID | Activity Name | WBS | Baseline Start | Baseline Finish
The Big -P.01-UP-20-April-26 | KD-MS-1000 | Project Start Date | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1050 | Project Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 10-Apr-27
The Big -P.01-UP-20-April-26 | KD-MS-1040 | Ground Works Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 11-May-26
The Big -P.01-UP-20-April-26 | KD-MS-1010 | Contract Agreement | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1020 | IFC Drawing Package | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MOB-1000 | Surveying Works | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1010 | Equipment Mobilization | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1020 | Site Preparation | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | E-DR-1000 | Design Review | The Big - P.01 - UP-24-MAY-26.EN.1 | 11-Sep-25 | 09-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | 11-Sep-25 | 01-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 01-Oct-25 | 22-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1010 | Submittal for RC Raft & Footings Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 05-Oct-25 | 26-Oct-25

## Slide 18
PRO-FLT-17 | Float Analysis
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (1363 rows)
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | Activity ID | Activity Name | WBS | Baseline Start | Baseline Finish
The Big -P.01-UP-20-April-26 | KD-MS-1000 | Project Start Date | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1050 | Project Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 10-Apr-27
The Big -P.01-UP-20-April-26 | KD-MS-1040 | Ground Works Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 11-May-26
The Big -P.01-UP-20-April-26 | KD-MS-1010 | Contract Agreement | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1020 | IFC Drawing Package | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MOB-1000 | Surveying Works | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1010 | Equipment Mobilization | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1020 | Site Preparation | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | E-DR-1000 | Design Review | The Big - P.01 - UP-24-MAY-26.EN.1 | 11-Sep-25 | 09-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | 11-Sep-25 | 01-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 01-Oct-25 | 22-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1010 | Submittal for RC Raft & Footings Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 05-Oct-25 | 26-Oct-25

## Slide 19
PRO-MIL-18 | Milestone Status
DATA AVAILABLE
CSV sources
milestones: 01-data/import_templates/milestones.csv (4 rows)
milestone_id | project_id | activity_name | planned_date | forecast_date | actual_date
KD`-MS-1000 | The Big -P.01-UP-20-April-26 | Project Start Date | 11-Sep-25 | 11-Sep-25 | 11-Sep-25
KD-MS-1010 | The Big -P.01-UP-20-April-26 | Contract Agreement | 11-Sep-25 | 11-Sep-25 | 11-Sep-25
KD-MS-1020 | The Big -P.01-UP-20-April-26 | IFC Drawing Package | 11-Sep-25 | 11-Sep-25 | 11-Sep-25
KD-MS-1040 | The Big -P.01-UP-20-April-26 | Ground Works Finish Date | 11-May-26 | 10-Sep-26 | 

## Slide 20
PRO-RSK-19 | Risk Report
DATA AVAILABLE
CSV sources
risks: 01-data/import_templates/risks.csv (2 rows)
risk_id | project_id | risk_title | risk_category | probability | time_impact_days
1 | The Big -P.01-UP-20-April-26 | Steel delivery delay | Schedule | high | yes
0 | The Big -P.01-UP-20-April-26 | Deploting MEP sub contractor | Schedule | high | yes

## Slide 21
PRO-RFI-20 | RFI & Submittals
DATA AVAILABLE
CSV sources
rfi: 02-delay_analysis/unified_tia_csv/09- rfi_status.csv (4 rows)
project_id | RFI | Activity ID | Activity Name | Submittion date | Reply
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-001 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | 16-Feb-26 | 29-Mar-26
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-002 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 17-Feb-26 | 18-Mar-26
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-003 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | 10-Mar-26 | 7-Apr-26
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-004 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 10-Mar-26 | 5-Apr-26

## Slide 22
PRO-QAQC-21 | QA/QC Performance
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 23
PRO-PROD-22 | Productivity
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
progress: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 24
PRO-EXE-23 | Executive Report
DATA AVAILABLE
CSV sources
projects: 01-data/import_templates/projects.csv (1 rows)
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
evm: 01-data/import_templates/project_input_bundle.csv (1363 rows)
risks: 01-data/import_templates/risks.csv (2 rows)
project_id | project_name | client_name | contractor | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | ROYA-BIG PROJECT PHASE01 (B1-4) | ROYA | SAMCO | 11-Sep-25 | 10-Apr-27

## Slide 25
PRO-BLC-24 | Baseline vs Current
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (1363 rows)
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | Activity ID | Activity Name | WBS | Baseline Start | Baseline Finish
The Big -P.01-UP-20-April-26 | KD-MS-1000 | Project Start Date | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1050 | Project Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 10-Apr-27
The Big -P.01-UP-20-April-26 | KD-MS-1040 | Ground Works Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 11-May-26
The Big -P.01-UP-20-April-26 | KD-MS-1010 | Contract Agreement | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1020 | IFC Drawing Package | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MOB-1000 | Surveying Works | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1010 | Equipment Mobilization | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1020 | Site Preparation | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | E-DR-1000 | Design Review | The Big - P.01 - UP-24-MAY-26.EN.1 | 11-Sep-25 | 09-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | 11-Sep-25 | 01-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 01-Oct-25 | 22-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1010 | Submittal for RC Raft & Footings Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 05-Oct-25 | 26-Oct-25

## Slide 26
PRO-FCF-25 | Forecast Completion
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
evm: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 27
PRO-ML-26 | ML Project Controls
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
evm: 01-data/import_templates/project_input_bundle.csv (1363 rows)
risks: 01-data/import_templates/risks.csv (2 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25

## Slide 28
PRO-CAD-27 | Contract Administration
DATA AVAILABLE
CSV sources
contracts: 01-data/import_templates/contracts.csv (2 rows)
claims: 01-data/import_templates/claims.csv (1 rows)
contract_id | project_id | package | contractor | contract_type | original_value
PH-01 | The Big -P.01-UP-20-April-26 | 1 | SAMCO | Unite rate | 367286025
PH-02 | The Big -P.01-UP-20-April-26 | 2 | SAMCO | Unite rate | 900000000

## Slide 29
PRO-CHG-28 | Change Control
DATA AVAILABLE
CSV sources
claims: 01-data/import_templates/claims.csv (1 rows)
project_id | claim_id | contract_id | claim_event_ref | claim_title | notice_date
The Big -P.01-UP-20-April-26 | 1 | PH-01 | 2 | Employer free issue material | 85

## Slide 30
PRO-DOC-29 | Document Control
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 31
PRO-IFC-30 | Interface Management
DATA AVAILABLE
CSV sources
ifc: 02-delay_analysis/unified_tia_csv/07- ifc_conflict.csv (16 rows)
project_id | Activity ID | Activity Name | Original Duration | Start | Finish
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS02-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 02) | 18 | 20-Nov-25 | 16-Feb-26
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS02-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02) | 18 | 30-Nov-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS01-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 01) | 18 | 2-Nov-25 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS01-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 01) | 18 | 5-Nov-25 | 31-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS02-1020 | Submittal for Beams Conc. Dim.& RFT DWGs (B02) (Bas 02) | 18 | 22-Oct-25 | 11-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS02-1030 | Submittal for Slabs Conc. Dim.& RFT DWGs (B02) (Bas 02) | 18 | 26-Oct-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS01-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B02) (Bas 01) | 18 | 2-Nov-25 | 23-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS01-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B02) (Bas 01) | 18 | 5-Nov-25 | 31-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS02-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 02) | 18 | 01-Mr-26 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS02-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B03) (Bas 02) | 18 | 01-Mr-26 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS01-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B03) (Bas 01) | 18 | 01-Mr-26 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS01-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 01) | 10 | 02-Mr-26 | 12-Mar-26