## Slide 1
SAMCO-PCO PRO-MAT-14 Material Status Report
ROYA-BIG PROJECT PHASE01 (B1-4) | 1 data-driven control section | 2026-08-15T05:31:00+00:00

## Slide 2
PRO-MAT-14 | Material Status
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/project_input_bundle.csv (1363 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1000 | Project Start Date | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1010 | Contract Agreement | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MI | KD-MS-1020 | IFC Drawing Package | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1000 | Surveying Works | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1010 | Equipment Mobilization | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.KD.MO | KD-MOB-1020 | Site Preparation | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1000 | Submittal for RFT Rebar | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.1 | E-DR-1000 | Design Review | 11-Sep-25 | 9-Nov-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 1-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B02.SUB.1 | E-SUB-B02-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | 11-Sep-25 | 20-Sep-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.EN.2.S.P01.B04.SUB.2ndB.1 | E-SUB-B04-WT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B04) (Water Tank) | 13-Sep-25 | 2-Oct-25
The Big -P.01-UP-20-April-26 | The Big - P.01 - UP-24-MAY-26.P.MS.SS | P-MS-1020 | Submittal for Soil Replacement | 14-Sep-25 | 4-Oct-25