## Slide 1
SAMCO-PCO PRO-IFC-30 Interface Management Report
ROYA-BIG PROJECT PHASE01 (B1-4) | 1 data-driven control section | 2026-08-15T05:31:00+00:00

## Slide 2
PRO-IFC-30 | Interface Management
DATA AVAILABLE
CSV sources
ifc: 02-delay_analysis/unified_tia_csv/07- ifc_conflict.csv (16 rows)
project_id | Activity ID | Activity Name | Original Duration | Start | Finish
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS02-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 02) | 18 | 20-Nov-25 | 16-Feb-26
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS02-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02) | 18 | 30-Nov-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS01-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 01) | 18 | 2-Nov-25 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B01-BAS01-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 01) | 18 | 5-Nov-25 | 31-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS02-1020 | Submittal for Beams Conc. Dim.& RFT DWGs (B02) (Bas 02) | 18 | 22-Oct-25 | 11-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS02-1030 | Submittal for Slabs Conc. Dim.& RFT DWGs (B02) (Bas 02) | 18 | 26-Oct-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS01-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B02) (Bas 01) | 18 | 2-Nov-25 | 23-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B02-BAS01-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B02) (Bas 01) | 18 | 5-Nov-25 | 31-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS02-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 02) | 18 | 01-Mr-26 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS02-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B03) (Bas 02) | 18 | 01-Mr-26 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS01-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B03) (Bas 01) | 18 | 01-Mr-26 | 10-Mar-26
The Big -P.01-UP-20-April-26 | E-SUB-B03-BAS01-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 01) | 10 | 02-Mr-26 | 12-Mar-26