## Slide 1
SAMCO-PCO PRO-DLY-02 Delay Analysis Report
LMD Bridge & Road Interchange | 1 data-driven control section | 2026-08-14T03:05:27+00:00

## Slide 2
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (5 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
LMD-Bridge | Delay in employer free issue steel supply | CON-LB-PIL-1010 | Bored piles and pile caps | 10-Jan-26 | 15-Apr-26
LMD-Bridge | Late IFC / design clarification | CON-LB-RFT-1020 | RFT for piers and abutments | 17-Mar-26 | 24-Apr-26
LMD-Bridge | Delayed RFI response | CON-LB-CON-1030 | Concrete works for piers and abutments | 24-Apr-26 | 29-May-26
LMD-Bridge | Access constraint and traffic diversion | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | 13-Jun-26 | 1-Sep-26
LMD-Bridge | MEP sleeve coordination delay | CON-LB-ROAD-1050 | Approach road embankment and pavement | 27-Aug-26 | 30-Nov-26