## Slide 1
SAMCO-PCO PRO-CST-09 Cost Control Report
LMD Bridge & Road Interchange | 1 data-driven control section | 2026-08-14T03:05:27+00:00

## Slide 2
PRO-CST-09 | Cost Control
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
LMD-Bridge | KD-MS-1000 | Project Start Date | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MS-1010 | Contract Agreement | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MS-1020 | IFC Drawing Package | May-26 | 10240963.86 | 10855421.69
LMD-Bridge | KD-MOB-1000 | Mobilization and traffic diversion setup | May-26 | 20481927.71 | 21710843.37
LMD-Bridge | SUR-LB-1010 | Survey control and utility relocation setting out | May-26 | 20481927.71 | 21710843.37
LMD-Bridge | E-SUB-LB-1020 | Bridge substructure shop drawings | May-26 | 30722891.57 | 24567990.36
LMD-Bridge | E-APP-LB-1020 | Approval of pier and deck shop drawings | May-26 | 30722891.57 | 18693036.14
LMD-Bridge | P-MDEL-LB-1000 | Steel, bearings and expansion joints delivery | May-26 | 51204819.28 | 24478975.90
LMD-Bridge | CON-LB-PIL-1010 | Bored piles and pile caps | May-26 | 102409638.55 | 75662289.16
LMD-Bridge | CON-LB-RFT-1020 | RFT for piers and abutments | May-26 | 102409638.55 | 51628385.54
LMD-Bridge | CON-LB-CON-1030 | Concrete works for piers and abutments | May-26 | 102409638.55 | 32045204.82
LMD-Bridge | CON-LB-DECK-1040 | Deck formwork reinforcement and casting | May-26 | 102409638.55 | 7121156.63