## Slide 1
SAMCO-PCO PRO-DLY-02 Delay Analysis Report
Nasr city-Tunnel | 1 data-driven control section | 2026-08-14T03:05:38+00:00

## Slide 2
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (5 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (6 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
Nasr city-Tunnel | Late structural shop drawing approval | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Restricted Building B access | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Late utility diversion instruction | NCT-UTL-1140 | Underground Drainage Network | 16-Mar-26 | 14-Apr-26
Nasr city-Tunnel | Concrete plant interruption | NCT-B-CON-1130 | Building B Raft Concrete | 6-Apr-26 | 11-Apr-26
Nasr city-Tunnel | Additional dewatering requirement | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26