## Slide 1
SAMCO-PCO PRO-CST-09 Cost Control Report
Nasr city-Tunnel | 1 data-driven control section | 2026-08-14T03:05:38+00:00

## Slide 2
PRO-CST-09 | Cost Control
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
Nasr city-Tunnel | NCT-MS-1000 | Notice to Proceed | May-26 | 4500000.00 | 4635000.00
Nasr city-Tunnel | NCT-MS-1010 | Site Handover | May-26 | 5625000.00 | 5934375.00
Nasr city-Tunnel | NCT-ENG-1020 | Issue IFC Architectural Drawings | May-26 | 6750000.00 | 7290000.00
Nasr city-Tunnel | NCT-ENG-1030 | Approve Structural Shop Drawings | May-26 | 7125000.00 | 7338750.00
Nasr city-Tunnel | NCT-PRC-1040 | Procure Reinforcement Steel | May-26 | 8250000.00 | 8703750.00
Nasr city-Tunnel | NCT-PRC-1050 | Deliver Formwork Materials | May-26 | 9375000.00 | 10125000.00
Nasr city-Tunnel | NCT-A-EXC-1060 | Building A Excavation | May-26 | 9750000.00 | 10042500.00
Nasr city-Tunnel | NCT-A-PC-1070 | Building A Plain Concrete | May-26 | 10875000.00 | 11473125.00
Nasr city-Tunnel | NCT-A-RFT-1080 | Building A Raft Reinforcement | May-26 | 12000000.00 | 12960000.00
Nasr city-Tunnel | NCT-A-CON-1090 | Building A Raft Concrete | May-26 | 12375000.00 | 12746250.00
Nasr city-Tunnel | NCT-B-EXC-1100 | Building B Excavation | May-26 | 13500000.00 | 14242500.00
Nasr city-Tunnel | NCT-B-PC-1110 | Building B Plain Concrete | May-26 | 14625000.00 | 15795000.00