## Slide 1
SAMCO-PCO PRO-DLY-02 Delay Analysis Report
Sophia Mall Mixed-Use Development | 1 data-driven control section | 2026-08-14T03:05:35+00:00

## Slide 2
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (5 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
Sophia-Mall | Delay in employer free issue steel supply | CON-SM-EXC-1010 | Bulk excavation and dewatering | 9-Dec-25 | 19-Mar-26
Sophia-Mall | Late IFC / design clarification | CON-SM-RFT-1020 | RFT for raft foundation | 22-Feb-26 | 30-Mar-26
Sophia-Mall | Delayed RFI response | CON-SM-CON-1030 | Raft foundation concrete works | 30-Mar-26 | 29-Apr-26
Sophia-Mall | Access constraint and traffic diversion | CON-SM-B1-1040 | Basement B1 columns and walls | 29-Apr-26 | 26-Jun-26
Sophia-Mall | MEP sleeve coordination delay | CON-SM-GF-1050 | Ground floor slab and beams | 26-Jun-26 | 4-Sep-26