## Slide 1
SAMCO-PCO PRO-EVM-10 Earned Value Report
Sophia Mall Mixed-Use Development | 1 data-driven control section | 2026-08-14T03:05:35+00:00

## Slide 2
PRO-EVM-10 | Earned Value
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
Sophia-Mall | KD-MS-1000 | Project Start Date | May-26 | 25301204.82 | 25048192.77
Sophia-Mall | KD-MS-1010 | Contract Agreement | May-26 | 25301204.82 | 25048192.77
Sophia-Mall | KD-MS-1020 | IFC Drawing Package | May-26 | 25301204.82 | 25048192.77
Sophia-Mall | KD-MOB-1000 | Mobilization and site logistics setup | May-26 | 50602409.64 | 50096385.54
Sophia-Mall | SUR-SM-1010 | Surveying and benchmark establishment | May-26 | 50602409.64 | 50096385.54
Sophia-Mall | E-SUB-SM-1020 | Structural and architectural shop drawings | May-26 | 75903614.46 | 71687927.71
Sophia-Mall | E-APP-SM-1020 | Approval of podium and basement drawings | May-26 | 75903614.46 | 62129537.35
Sophia-Mall | P-MDEL-SM-1000 | Long lead procurement for steel and MEP sleeves | May-26 | 126506024.10 | 88946132.53
Sophia-Mall | CON-SM-EXC-1010 | Bulk excavation and dewatering | May-26 | 253012048.19 | 250481927.71
Sophia-Mall | CON-SM-RFT-1020 | RFT for raft foundation | May-26 | 253012048.19 | 217718891.57
Sophia-Mall | CON-SM-CON-1030 | Raft foundation concrete works | May-26 | 253012048.19 | 164616722.89
Sophia-Mall | CON-SM-B1-1040 | Basement B1 columns and walls | May-26 | 253012048.19 | 92928795.18