## Slide 1
SAMCO-PCO PRO-MIL-18 Milestone Status Report
Sophia Mall Mixed-Use Development | 1 data-driven control section | 2026-08-14T03:05:35+00:00

## Slide 2
PRO-MIL-18 | Milestone Status
DATA AVAILABLE
CSV sources
milestones: 01-data/import_templates/milestones.csv (5 rows)
milestone_id | project_id | activity_name | planned_date | forecast_date | actual_date
KD-MS-1000 | Sophia-Mall | Project Start Date | 15-Oct-25 | 15-Oct-25 | 15-Oct-25
KD-MS-1010 | Sophia-Mall | Contract Agreement | 15-Oct-25 | 15-Oct-25 | 15-Oct-25
KD-MS-1020 | Sophia-Mall | IFC Drawing Package | 22-Oct-25 | 27-Oct-25 | 22-Oct-25
KD-MS-5000 | Sophia-Mall | Structural Works Completion | 15-Oct-26 | 30-Oct-26 | 
KD-MS-9000 | Sophia-Mall | Substantial Completion | 31-Jul-27 | 25-Aug-27 |