## Slide 1
SAMCO-PCO PRO-DLY-02 Delay Analysis Report
Suez Tunnel Civil & MEP Works | 1 data-driven control section | 2026-08-14T03:05:41+00:00

## Slide 2
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (5 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
Suez-Tunnel | Delay in employer free issue steel supply | CON-ST-EXC-1010 | Open cut excavation and shoring | 29-Oct-25 | 27-Jan-26
Suez-Tunnel | Late IFC / design clarification | CON-ST-RFT-1020 | RFT for base slab reinforcement | 28-Dec-25 | 25-Jan-26
Suez-Tunnel | Delayed RFI response | CON-ST-CON-1030 | Concrete casting for base slab | 28-Jan-26 | 21-Feb-26
Suez-Tunnel | Access constraint and traffic diversion | CON-ST-WALL-1040 | Tunnel wall reinforcement and formwork | 26-Feb-26 | 27-Apr-26
Suez-Tunnel | MEP sleeve coordination delay | CON-ST-SLAB-1050 | Roof slab reinforcement and concrete | 27-Apr-26 | 1-Jul-26