## Slide 1
SAMCO-PCO PRO-DLY-02 Delay Analysis Report
ROYA-BIG PROJECT PHASE01 (B1-4) | 1 data-driven control section | 2026-08-14T03:05:31+00:00

## Slide 2
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (25 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (0 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | 23-Dec-25 | 29-Dec-25
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | 6-Dec-25 | 18-Dec-25
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 13-Dec-25 | 21-Dec-25
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | 15-Jan-26 | 24-Jan-26
The Big -P.01-UP-20-April-26 | Delay in steel supply by client | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | 21-Jan-26 | 27-Jan-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS02-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 02) | 20-Nov-25 | 16-Feb-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS02-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02) | 30-Nov-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS01-1030 | Submittal for Beams Conc. Dim. & RFT DWGs (B01) (Bas 01) | 2-Nov-25 | 10-Mar-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B01-BAS01-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 01) | 5-Nov-25 | 31-Mar-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B02-BAS02-1020 | Submittal for Beams Conc. Dim.& RFT DWGs (B02) (Bas 02) | 22-Oct-25 | 11-Nov-25
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B02-BAS02-1030 | Submittal for Slabs Conc. Dim.& RFT DWGs (B02) (Bas 02) | 26-Oct-25 | 22-Feb-26
The Big -P.01-UP-20-April-26 | IFC | E-SUB-B02-BAS01-1020 | Submittal for Beams Conc. Dim. & RFT DWGs (B02) (Bas 01) | 2-Nov-25 | 23-Nov-25