## Slide 1
SAMCO-PCO PRO-FLT-17 Float Analysis Report
ROYA-BIG PROJECT PHASE01 (B1-4) | 1 data-driven control section | 2026-08-14T03:05:31+00:00

## Slide 2
PRO-FLT-17 | Float Analysis
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (1363 rows)
activities: 01-data/import_templates/activity_master.csv (1363 rows)
project_id | Activity ID | Activity Name | WBS | Baseline Start | Baseline Finish
The Big -P.01-UP-20-April-26 | KD-MS-1000 | Project Start Date | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1050 | Project Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 10-Apr-27
The Big -P.01-UP-20-April-26 | KD-MS-1040 | Ground Works Finish Date | The Big - P.01 - UP-24-MAY-26.KD.MI |  | 11-May-26
The Big -P.01-UP-20-April-26 | KD-MS-1010 | Contract Agreement | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MS-1020 | IFC Drawing Package | The Big - P.01 - UP-24-MAY-26.KD.MI | 11-Sep-25 | 
The Big -P.01-UP-20-April-26 | KD-MOB-1000 | Surveying Works | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1010 | Equipment Mobilization | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | KD-MOB-1020 | Site Preparation | The Big - P.01 - UP-24-MAY-26.KD.MO | 11-Sep-25 | 28-Sep-25
The Big -P.01-UP-20-April-26 | E-DR-1000 | Design Review | The Big - P.01 - UP-24-MAY-26.EN.1 | 11-Sep-25 | 09-Nov-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-REP-1000 | Submittal for General Replacement Plan & Typical Sections for Replacement / Back | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.1 | 11-Sep-25 | 01-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1000 | Submittal for PC Raft Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 01-Oct-25 | 22-Oct-25
The Big -P.01-UP-20-April-26 | E-SUB-B01-FOOT-1010 | Submittal for RC Raft & Footings Conc. Dim. DWGs (B01) (footing) | The Big - P.01 - UP-24-MAY-26.EN.2.S.P02.B01.SUB.F | 05-Oct-25 | 26-Oct-25