## Slide 1
SAMCO-PCO PRO-RFI-20 RFI & Submittals Report
ROYA-BIG PROJECT PHASE01 (B1-4) | 1 data-driven control section | 2026-08-14T03:05:31+00:00

## Slide 2
PRO-RFI-20 | RFI & Submittals
DATA AVAILABLE
CSV sources
rfi: 02-delay_analysis/unified_tia_csv/09- rfi_status.csv (4 rows)
project_id | RFI | Activity ID | Activity Name | Submittion date | Reply
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-001 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | 16-Feb-26 | 29-Mar-26
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-002 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 17-Feb-26 | 18-Mar-26
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-003 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | 10-Mar-26 | 7-Apr-26
The Big -P.01-UP-20-April-26 | BD-CW-SAMCO-PCO-RFI-MECH-004 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 10-Mar-26 | 5-Apr-26