## Slide 1
SAMCO-PCO Project Controls Report
Nasr city-Tunnel | 30 data-driven control sections | 2026-08-13T19:10:48+00:00

## Slide 2
PRO-TIA-01 | Time Impact & Extension of Time
DATA AVAILABLE
CSV sources
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (6 rows)
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (6 rows)
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
project_id | event_id | activity_id | root_cause | delay_type | entitlement_status
Nasr city-Tunnel | EV-01 | NCT-ST-CLB-RFT-1100 | Employer steel delivery below approved requirement | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-02 | NCT-ST-PMP-RFT-1200 | Late revised IFC bearing-pedestal detail | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-03 | NCT-ST-CLR-RFT-1300 | Clarifier waterstop and embedded-pipe conflict | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-04 | NCT-ST-FLT-RFT-1400 | Delayed response to filter gallery opening RFI | Excusable Compensable | Under Assessment
Nasr city-Tunnel | EV-05 | NCT-ST-RES-RFT-1500 | Outstanding high-diameter employer steel | Excusable Compensable | Potentially Entitled
Nasr city-Tunnel | EV-06 | NCT-ST-ADM-RFT-1600 | Delayed interim payment certification | Commercial / Potential Compensable | Under Assessment

## Slide 3
PRO-DLY-02 | Delay Analysis
DATA AVAILABLE
CSV sources
delay_events: 01-data/import_templates/delay_events.csv (5 rows)
delay_classification: 02-delay_analysis/unified_tia_csv/12_delay_event_classification.csv (6 rows)
project_id | Primary Event ID | Activity ID | Activity Name | BL Start | BL Finish
Nasr city-Tunnel | Late structural shop drawing approval | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Restricted Building B access | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Late utility diversion instruction | NCT-UTL-1140 | Underground Drainage Network | 16-Mar-26 | 14-Apr-26
Nasr city-Tunnel | Concrete plant interruption | NCT-B-CON-1130 | Building B Raft Concrete | 6-Apr-26 | 11-Apr-26
Nasr city-Tunnel | Additional dewatering requirement | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26

## Slide 4
PRO-PRG-03 | Project Progress
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
progress: 01-data/import_templates/progress_updates.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 5
PRO-REC-04 | Recovery & Mitigation
DATA AVAILABLE
CSV sources
tia_recovery: 02-delay_analysis/unified_tia_csv/13_tia_recovery_scenario.csv (6 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | scenario_id | scenario_name | analyst_status | activity_id | status_date
Nasr city-Tunnel | SCN-01 | Steel priority delivery and two reinforcement crews | Approved for Modelling | NCT-ST-CLB-RFT-1100 | 2026-07-31
Nasr city-Tunnel | SCN-02 | Pump hall revised sequence with extended shift | Approved for Modelling | NCT-ST-PMP-RFT-1200 | 2026-07-31
Nasr city-Tunnel | SCN-03 | Clarifier segmented pour and parallel embedded works | Approved for Modelling | NCT-ST-CLR-RFT-1300 | 2026-07-31
Nasr city-Tunnel | SCN-04 | Filter gallery additional fixing gang | Candidate | NCT-ST-FLT-RFT-1400 | 2026-07-31
Nasr city-Tunnel | SCN-05 | Reservoir prioritized steel diameters and night shift | Recommended | NCT-ST-RES-RFT-1500 | 2026-07-31
Nasr city-Tunnel | SCN-06 | Administration foundation subcontract package | Candidate | NCT-ST-ADM-RFT-1600 | 2026-07-31

## Slide 6
PRO-VAR-05 | Variation Report
DATA AVAILABLE
CSV sources
claims: 01-data/import_templates/claims.csv (2 rows)
project_id | claim_id | contract_id | claim_event_ref | claim_title | notice_date
Nasr city-Tunnel | CL-101 | NCT-PKG-01 | DE-101 | Late approval of structural shop drawings | 9-Mar-26
Nasr city-Tunnel | CL-102 | NCT-PKG-01 | DE-102 | Restricted access to Building B workfront | 22-Apr-26

## Slide 7
PRO-IPC-06 | Interim Payment
DATA AVAILABLE
CSV sources
payments: 01-data/import_templates/payments.csv (6 rows)
project_id | payment | contract | project | invoice no | invoice date
Nasr city-Tunnel | 1.0 | NCT-PKG-01 | Nasr city-Tunnel | 101.0 | 31-Jan-26
Nasr city-Tunnel | 2.0 | NCT-PKG-01 | Nasr city-Tunnel | 102.0 | 28-Feb-26
Nasr city-Tunnel | 3.0 | NCT-PKG-01 | Nasr city-Tunnel | 103.0 | 31-Mar-26
Nasr city-Tunnel | 4.0 | NCT-PKG-01 | Nasr city-Tunnel | 104.0 | 30-Apr-26
Nasr city-Tunnel | 5.0 | NCT-PKG-02 | Nasr city-Tunnel | 201.0 | 15-Mar-26
Nasr city-Tunnel | 6.0 | NCT-PKG-02 | Nasr city-Tunnel | 202.0 | 15-May-26

## Slide 8
PRO-RES-07 | Resource & Manpower
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 9
PRO-EQP-08 | Equipment & Plant
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 10
PRO-CST-09 | Cost Control
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
Nasr city-Tunnel | NCT-MS-1000 | Notice to Proceed | May-26 | 4500000.00 | 4635000.00
Nasr city-Tunnel | NCT-MS-1010 | Site Handover | May-26 | 5625000.00 | 5934375.00
Nasr city-Tunnel | NCT-ENG-1020 | Issue IFC Architectural Drawings | May-26 | 6750000.00 | 7290000.00
Nasr city-Tunnel | NCT-ENG-1030 | Approve Structural Shop Drawings | May-26 | 7125000.00 | 7338750.00
Nasr city-Tunnel | NCT-PRC-1040 | Procure Reinforcement Steel | May-26 | 8250000.00 | 8703750.00
Nasr city-Tunnel | NCT-PRC-1050 | Deliver Formwork Materials | May-26 | 9375000.00 | 10125000.00
Nasr city-Tunnel | NCT-A-EXC-1060 | Building A Excavation | May-26 | 9750000.00 | 10042500.00
Nasr city-Tunnel | NCT-A-PC-1070 | Building A Plain Concrete | May-26 | 10875000.00 | 11473125.00
Nasr city-Tunnel | NCT-A-RFT-1080 | Building A Raft Reinforcement | May-26 | 12000000.00 | 12960000.00
Nasr city-Tunnel | NCT-A-CON-1090 | Building A Raft Concrete | May-26 | 12375000.00 | 12746250.00
Nasr city-Tunnel | NCT-B-EXC-1100 | Building B Excavation | May-26 | 13500000.00 | 14242500.00
Nasr city-Tunnel | NCT-B-PC-1110 | Building B Plain Concrete | May-26 | 14625000.00 | 15795000.00

## Slide 11
PRO-EVM-10 | Earned Value
DATA AVAILABLE
CSV sources
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | activity_id | activity_name | period | BAC | AC
Nasr city-Tunnel | NCT-MS-1000 | Notice to Proceed | May-26 | 4500000.00 | 4635000.00
Nasr city-Tunnel | NCT-MS-1010 | Site Handover | May-26 | 5625000.00 | 5934375.00
Nasr city-Tunnel | NCT-ENG-1020 | Issue IFC Architectural Drawings | May-26 | 6750000.00 | 7290000.00
Nasr city-Tunnel | NCT-ENG-1030 | Approve Structural Shop Drawings | May-26 | 7125000.00 | 7338750.00
Nasr city-Tunnel | NCT-PRC-1040 | Procure Reinforcement Steel | May-26 | 8250000.00 | 8703750.00
Nasr city-Tunnel | NCT-PRC-1050 | Deliver Formwork Materials | May-26 | 9375000.00 | 10125000.00
Nasr city-Tunnel | NCT-A-EXC-1060 | Building A Excavation | May-26 | 9750000.00 | 10042500.00
Nasr city-Tunnel | NCT-A-PC-1070 | Building A Plain Concrete | May-26 | 10875000.00 | 11473125.00
Nasr city-Tunnel | NCT-A-RFT-1080 | Building A Raft Reinforcement | May-26 | 12000000.00 | 12960000.00
Nasr city-Tunnel | NCT-A-CON-1090 | Building A Raft Concrete | May-26 | 12375000.00 | 12746250.00
Nasr city-Tunnel | NCT-B-EXC-1100 | Building B Excavation | May-26 | 13500000.00 | 14242500.00
Nasr city-Tunnel | NCT-B-PC-1110 | Building B Plain Concrete | May-26 | 14625000.00 | 15795000.00

## Slide 12
PRO-CFS-11 | Cash Flow
DATA AVAILABLE
CSV sources
planned_cash_flow: 01-data/import_templates/planned_cash_flow.csv (12 rows)
payments: 01-data/import_templates/payments.csv (6 rows)
project_id | period_date | planned_cash_out | planned_cumulative_cash_out | currency | basis
Nasr city-Tunnel | 1-Jan-26 | 45950000.00 | 45950000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Feb-26 | 53900000.00 | 99850000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Mar-26 | 49250000.00 | 149100000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Apr-26 | 57200000.00 | 206300000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-May-26 | 65150000.00 | 271450000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Jun-26 | 60500000.00 | 331950000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Jul-26 | 68450000.00 | 400400000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Aug-26 | 76400000.00 | 476800000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Sep-26 | 71750000.00 | 548550000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Oct-26 | 79700000.00 | 628250000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Nov-26 | 87650000.00 | 715900000.00 | EGP | Approved baseline cash flow
Nasr city-Tunnel | 1-Dec-26 | 83000000.00 | 798900000.00 | EGP | Approved baseline cash flow

## Slide 13
PRO-SCV-12 | S-Curve
DATA AVAILABLE
CSV sources
s_curve: 01-data/import_templates/s_curve.csv (10 rows)
project_id | months | monthly_planned | cumm_monthly_planned | monthly_actual | cumm_monthly_actual
Nasr city-Tunnel | 1-Jan-26 | 30000000.00 | 30000000.00 | 24450000.00 | 24450000.00
Nasr city-Tunnel | 1-Feb-26 | 52000000.00 | 82000000.00 | 41600000.00 | 66050000.00
Nasr city-Tunnel | 1-Mar-26 | 76000000.00 | 158000000.00 | 59432000.00 | 125482000.00
Nasr city-Tunnel | 1-Apr-26 | 94000000.00 | 252000000.00 | 74260000.00 | 199742000.00
Nasr city-Tunnel | 1-May-26 | 116000000.00 | 368000000.00 | 88740000.00 | 288482000.00
Nasr city-Tunnel | 1-Jun-26 | 138000000.00 | 506000000.00 | 105570000.00 | 394052000.00
Nasr city-Tunnel | 1-Jul-26 | 151000000.00 | 657000000.00 | 100408000.00 | 494460000.00
Nasr city-Tunnel | 1-Aug-26 | 164000000.00 | 821000000.00 | 0.00 | 494460000.00
Nasr city-Tunnel | 1-Sep-26 | 173000000.00 | 994000000.00 | 0.00 | 494460000.00
Nasr city-Tunnel | 1-Oct-26 | 181000000.00 | 1175000000.00 | 0.00 | 494460000.00

## Slide 14
PRO-PRC-13 | Procurement Status
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 15
PRO-MAT-14 | Material Status
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 16
PRO-LAH-15 | Labour Hours
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 17
PRO-CPM-16 | Critical Path
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 18
PRO-FLT-17 | Float Analysis
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 19
PRO-MIL-18 | Milestone Status
DATA AVAILABLE
CSV sources
milestones: 01-data/import_templates/milestones.csv (5 rows)
milestone_id | project_id | activity_name | planned_date | forecast_date | actual_date
NCT-MS-1000 | Nasr city-Tunnel | Notice to Proceed | 5-Jan-26 | 5-Jan-26 | 5-Jan-26
NCT-MS-1010 | Nasr city-Tunnel | Site Handover | 8-Jan-26 | 10-Jan-26 | 10-Jan-26
NCT-MS-1020 | Nasr city-Tunnel | IFC Package Complete | 31-Jan-26 | 18-Mar-26 | 18-Mar-26
NCT-MS-1030 | Nasr city-Tunnel | Substructure Completion | 28-May-26 | 19-Jun-26 | 
NCT-MS-1040 | Nasr city-Tunnel | Project Completion | 15-Dec-26 | 12-Jan-27 | 

## Slide 20
PRO-RSK-19 | Risk Report
DATA AVAILABLE
CSV sources
risks: 01-data/import_templates/risks.csv (3 rows)
risk_id | project_id | risk_title | risk_category | probability | time_impact_days
R-101 | Nasr city-Tunnel | Employer-supplied reinforcement steel delivery slippage | Schedule | high | yes
R-102 | Nasr city-Tunnel | Late approval of viaduct bearing-seat details | Engineering | medium | yes
R-103 | Nasr city-Tunnel | Delayed interim payment certification | Commercial | medium | no

## Slide 21
PRO-RFI-20 | RFI & Submittals
AWAITING CONTROLLED CSV DATA
CSV sources
rfi: 02-delay_analysis/unified_tia_csv/09- rfi_status.csv (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 22
PRO-QAQC-21 | QA/QC Performance
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 23
PRO-PROD-22 | Productivity
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
progress: 01-data/import_templates/progress_updates.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 24
PRO-EXE-23 | Executive Report
DATA AVAILABLE
CSV sources
projects: 01-data/import_templates/projects.csv (1 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
evm: 01-data/import_templates/evm.csv (17 rows)
risks: 01-data/import_templates/risks.csv (3 rows)
project_id | project_name | client_name | contractor | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel | Alexandria Transit Development Authority | Delta Rail Builders JV | 12-Jan-26 | 30-Jun-28

## Slide 25
PRO-BLC-24 | Baseline vs Current
DATA AVAILABLE
CSV sources
p6: 02-delay_analysis/unified_tia_csv/04- p6_activity_export.csv (0 rows)
activities: 01-data/import_templates/activities.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 26
PRO-FCF-25 | Forecast Completion
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
evm: 01-data/import_templates/evm.csv (17 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 27
PRO-ML-26 | ML Project Controls
DATA AVAILABLE
CSV sources
activities: 01-data/import_templates/activities.csv (17 rows)
evm: 01-data/import_templates/evm.csv (17 rows)
risks: 01-data/import_templates/risks.csv (3 rows)
project_id | wbs_id | activity_id | activity_name | planned_start | planned_finish
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1000 | Notice to Proceed | 5-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.MILESTONE | NCT-MS-1010 | Site Handover | 8-Jan-26 | 
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1020 | Issue IFC Architectural Drawings | 10-Jan-26 | 23-Jan-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.ENGINEERING | NCT-ENG-1030 | Approve Structural Shop Drawings | 17-Jan-26 | 6-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1040 | Procure Reinforcement Steel | 25-Jan-26 | 28-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.PROCUREMENT | NCT-PRC-1050 | Deliver Formwork Materials | 30-Jan-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-EXC-1060 | Building A Excavation | 9-Feb-26 | 26-Feb-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-PC-1070 | Building A Plain Concrete | 27-Feb-26 | 6-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-RFT-1080 | Building A Raft Reinforcement | 7-Mar-26 | 26-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-A.SUBSTRUCTURE | NCT-A-CON-1090 | Building A Raft Concrete | 27-Mar-26 | 31-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-EXC-1100 | Building B Excavation | 16-Feb-26 | 7-Mar-26
Nasr city-Tunnel | Nasr city-Tunnel.NCT.BLDG-B.SUBSTRUCTURE | NCT-B-PC-1110 | Building B Plain Concrete | 8-Mar-26 | 14-Mar-26

## Slide 28
PRO-CAD-27 | Contract Administration
DATA AVAILABLE
CSV sources
contracts: 01-data/import_templates/contracts.csv (2 rows)
claims: 01-data/import_templates/claims.csv (2 rows)
contract_id | project_id | package | contractor | contract_type | original_value
NCT-PKG-01 | Nasr city-Tunnel | Main Buildings and External Works | Vertex Build JV | Lump sum | 980000000
NCT-PKG-02 | Nasr city-Tunnel | MEP and Utility Networks | Nova MEP Consortium | Unit rate | 310000000

## Slide 29
PRO-CHG-28 | Change Control
DATA AVAILABLE
CSV sources
claims: 01-data/import_templates/claims.csv (2 rows)
project_id | claim_id | contract_id | claim_event_ref | claim_title | notice_date
Nasr city-Tunnel | CL-101 | NCT-PKG-01 | DE-101 | Late approval of structural shop drawings | 9-Mar-26
Nasr city-Tunnel | CL-102 | NCT-PKG-01 | DE-102 | Restricted access to Building B workfront | 22-Apr-26

## Slide 30
PRO-DOC-29 | Document Control
AWAITING CONTROLLED CSV DATA
CSV sources
No mapped source: (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.

## Slide 31
PRO-IFC-30 | Interface Management
AWAITING CONTROLLED CSV DATA
CSV sources
ifc: 02-delay_analysis/unified_tia_csv/07- ifc_conflict.csv (0 rows)
No controlled CSV data is available for this report section. No value or conclusion has been inferred.