## RftActivity_upto_Nov_Relation
Activity ID | Activity Name | Predecessors ID | Predecessors Name | Successors ID | Successors Name
CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | CON-B04-FOOT-1040 | Shuttering for RC Raft & Footings (B04) (footing) | CON-B04-FOOT-1080 | Pouring for RC Raft & Footings (B04) (footing)
CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | E-APP-B04-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B04) (footing) | AB-SUB-B04-FOOT-1020 | Submittal for RC Raft & Footings RFT DWGs As-Built Drawing (B04) (footing)
CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing)
CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | CON-B01-FOOT-1040 | Shuttering for RC Raft & Footings (B01) (footing) | CON-B01-FOOT-1090 | Pouring for RC Raft & Footings (B01) (footing)
CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | E-APP-B01-FOOT-1020 | Approval for RC Raft & Footings RFT DWGs (B01)
CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing)
CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | CON-B03-FOOT-1040 | Shuttering for RC Raft & Footings (B03) (footing) | CON-B03-FOOT-1080 | Pouring for RC Raft & Footings (B03) (footing)
CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | E-APP-B03-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B03) (footing) | AB-SUB-B03-FOOT-1020 | Submittal for RC Raft & Footings RFT DWGs As-Built Drawing (B03) (footing)
CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing)
CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | CON-B02-FOOT-1040 | Shuttering for RC Raft & Footings (B02) (footing) | CON-B02-FOOT-1090 | Pouring for RC Raft & Footings (B02) (footing)
CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | E-APP-B02-FOOT-1020 | Approval for RC Raft & Footings RFT DWGs (B02) (footing) | AB-SUB-B02-FOOT-1020 | Submittal for RC Raft & Footings RFT DWGs As-Built Drawing (B02) (footing)
CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing)
CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | CON-B04-WT-1060 | Shuttering for RC Raft (B04) (Water Tank) | CON-B04-WT-1080 | Pouring for RC Raft (B04) (Water Tank)
CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | E-APP-B04-WT-1020 | Approval for RC Raft RFT DWGs (B04) (Water Tank) | AB-SUB-B04-WT-1020 | Submittal for RC Raft RFT DWGs As-Built Drawing (B04) (Water Tank)
CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank)
CON-B01-FOOT-1070 | RFT for Columns & Walls Below SOG (B01) (footing) | CON-B01-FOOT-1060 | Shuttering for Columns & Walls Below SOG (B01) (footing) | CON-B01-FOOT-1080 | Pouring Columns & Walls Below SOG (B01) (footing)
CON-B01-FOOT-1070 | RFT for Columns & Walls Below SOG (B01) (footing) | E-APP-B01-FOOT-1020 | Approval for RC Raft & Footings RFT DWGs (B01)
CON-B01-FOOT-1070 | RFT for Columns & Walls Below SOG (B01) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B01-FOOT-1070 | RFT for Columns & Walls Below SOG (B01) (footing)
CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | CON-B02-FOOT-1060 | Shuttering for Columns & Walls Below SOG (B01) (footing) | CON-B02-FOOT-1080 | Pouring Columns & Walls Below SOG (B01) (footing)
CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | E-APP-B02-FOOT-1020 | Approval for RC Raft & Footings RFT DWGs (B02) (footing)
CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing)
CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | CON-B04-FOOT-1060 | Shuttering for Columns & Walls Below SOG (B01) (footing) | CON-B04-FOOT-1090 | Pouring Columns & Walls Below SOG (B01) (footing)
CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | E-APP-B04-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B04) (footing)
CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing)
CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | CON-B03-FOOT-1060 | Shuttering for Columns & Walls Below SOG (B01) (footing) | CON-B03-FOOT-1090 | Pouring Columns & Walls Below SOG (B01) (footing)
CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | E-APP-B03-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B03) (footing)
CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing)
CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | CON-B04-WT-1100 | Shuttering for Walls (B04) (Water Tank) | CON-B04-WT-1120 | Installation for Waterstop Insulation (B04) (Water Tank)
CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | E-APP-B04-WT-1030 | Approval for Col. & Walls DWGs (B04) (Water Tank) | CON-B04-WT-1130 | Pouring for Walls (B04) (Water Tank)
CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank) | AB-SUB-B04-WT-1030 | Submittal for Col. & Walls DWGs As-Built Drawing (B04) (Water Tank)
CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank)
CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | CON-B04-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B04) (Bas 02) | CON-B04-BAS02-1020 | Shuttering for Walls, Col. & Cores (B04) (Bas 02)
CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | E-APP-B04-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B04) (Bas 02) | AB-SUB-B04-BAS2-1000 | Submittal for Col. & Walls Conc. Dim. & RFT DWGs As-Built Drawing (B04) (Bas 02)
CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2) | CON-B04-BAS02-1020 | Shuttering for Walls, Col. & Cores (B04) (Bas 02)
CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02)
CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | CON-B02-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B02) (Bas 02) | CON-B02-BAS02-1020 | Shuttering for Walls, Col. & Cores (B02) (Bas 02)
CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | E-APP-B02-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B02) (Bas 02) | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02)
CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2) | CON-B02-BAS02-1020 | Shuttering for Walls, Col. & Cores (B02) (Bas 02)
CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02)
CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | CON-B01-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B01) (Bas 02) | CON-B01-BAS02-1020 | Shuttering for Walls, Col. & Cores (B01) (Bas 02)
CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | E-APP-B01-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B01) (Bas 02) | CON-B01-BAS02-1020 | Shuttering for Walls, Col. & Cores (B01) (Bas 02)
CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02)
CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | CON-B04-WT-1150 | Formwork for Top Slab (B04) (Water Tank) | CON-B04-WT-1170 | Pouring for Top Slab (B04) (Water Tank)
CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | E-APP-B04-WT-1040 | Approval for Slabs DWGs (B04) (Water Tank) | AB-SUB-B04-WT-1040 | Submittal for Slabs DWGs As-Built Drawing (B04) (Water Tank)
CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank)
CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | CON-B03-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B03) (Bas 02) | CON-B03-BAS02-1020 | Shuttering for Walls, Col. & Cores (B03) (Bas 02)
CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | E-APP-B03-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B03) (Bas 02) | CON-B03-BAS02-1020 | Shuttering for Walls, Col. & Cores (B03) (Bas 02)
CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02)
CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | CON-B02-BAS02-1040 | Shuttering for Slabs & Beams (B02) (Bas 02) | CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02)
CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | E-APP-B02-BAS02-1020 | Approval for Beams Conc. Dim. & RFT DWGs (B02) (Bas 02) | CON-B02-BAS02-1100 | Pouring for Slabs & Beams (B02) (Bas 02)
CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | E-APP-B02-BAS02-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B02) (Bas 02)
CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | CON-B04-BAS02-1040 | Shuttering for Slabs & Beams (B04) (Bas 02) | CON-B04-BAS02-1130 | Pouring for Slabs & Beams (B04) (Bas 02)
CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | E-APP-B04-BAS02-1030 | Approval for Beams Conc. Dim. & RFT DWGs (B04) (Bas 02)
CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | E-APP-B04-BAS02-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B04) (Bas 02)
CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | CON-B04-BAS02-1050 | Shuttering for Stairs (B04) (Bas 02) | CON-B04-BAS02-1100 | Pouring for Stairs (B04) (Bas 02)
CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | E-APP-B04-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B04) (Bas 02)
CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02)
CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | CON-B02-BAS02-1050 | Shuttering for Stairs (B02) (Bas 02) | CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02)
CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | E-APP-B02-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B02) (Bas 02) | CON-B02-BAS02-1080 | Pouring for Stairs (B02) (Bas 02)
CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2) | AB-SUB-B02-BAS2-1010 | Submittal for Stairs Conc. Dim.& RFT DWGs As-Built Drawing (B02) (Bas 02)
CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02)
CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | CON-B04-BAS02-1070 | Shuttering for Ramps (B04) (Bas 02) | CON-B04-BAS02-1110 | Pouring for Ramps (B04) (Bas 02)
CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | E-APP-B04-BAS02-1020 | Approval for Ramps Conc. Dim. & RFT DWGs (B04) (Bas 02)
CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02)
CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | CON-B01-BAS02-1040 | Shuttering for Slabs & Beams (B01) (Bas 02) | CON-B01-BAS02-1130 | Pouring for Slabs & Beams (B01) (Bas 02)
CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | E-APP-B01-BAS02-1030 | Approval for Beams Conc. Dim. & RFT DWGs (B01) (Bas 02)
CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | E-APP-B01-BAS02-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02)
CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | CON-B01-BAS02-1050 | Shuttering for Stairs (B01) (Bas 02) | CON-B01-BAS02-1100 | Pouring for Stairs (B01) (Bas 02)
CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | E-APP-B01-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B01) (Bas 02)
CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02)
CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | CON-B01-BAS02-1060 | Shuttering for Ramps (B01) (Bas 02) | CON-B01-BAS02-1110 | Pouring for Ramps (B01) (Bas 02)
CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | E-APP-B01-BAS02-1020 | Approval for Ramps Conc. Dim. & RFT DWGs (B01) (Bas 02)
CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02)
CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | CON-B03-BAS02-1040 | Shuttering for Slabs & Beams (B03) (Bas 02) | CON-B03-BAS02-1100 | Pouring for Slabs & Beams B03) (Bas 02)
CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | E-APP-B03-BAS02-1020 | Approval for Beams Conc. Dim. & RFT DWGs (B03) (Bas 02)
CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | E-APP-B03-BAS02-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 02)
CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | CON-B03-BAS02-1050 | Shuttering for Stairs (B03) (Bas 02) | CON-B03-BAS02-1080 | Pouring for Stairs (B03) (Bas 02)
CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | E-APP-B03-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B03) (Bas 02)
CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02)