## ifc_summary
Period | Claim Treatment
2026-03-18 | A revised IFC drawing package Issued prevented the Contractor from proceeding work
2026-03-24 | Submitted a letter identifying the differences between the revised IFC and the original and requesting the Engineer’s instruction.
2026-04-30 | Engineer issued new IFC drawing package which resulted in re-submission of shop-drawings already approved
2026-05-02 | Contractor started working on shop-drawings and re-submission
2026-06-02 | Contractor finished resubmission of the re-worked shop-drawings
Gross IFC conflict = Issuing of the revised IFC package (18-March-2026) - Finishing re-submission of re-worked sshopd-drawings (02-June-2026) = -59 Days (6DAYS CALENDER)

## ifc_activities_rework
Activity ID | Activity Name | Original Duration | Start | Finish | Rework start | Rework finish
E-SUB-B01-BAS02-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02) | 18 | 2025-11-30 | 2026-02-22 | 2026-05-03 | 2026-05-12
E-SUB-B01-BAS01-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 01) | 18 | 2025-11-05 | 31-Mr-26 | 2026-05-17 | 2026-05-21
E-SUB-B02-BAS02-1030 | Submittal for Slabs Conc. Dim.& RFT DWGs (B02) (Bas 02) | 18 | 2025-10-26 | 2026-02-22 | 2026-05-03 | 2026-05-12
E-SUB-B02-BAS01-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B02) (Bas 01) | 18 | 2025-11-05 | 31-Mr-26 | 2026-05-17 | 2026-05-21
E-SUB-B03-BAS02-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 02) | 18 | 01-Mr-26 | 10-Mr-26 | 2026-05-02 | 2026-05-03
E-SUB-B03-BAS01-1030 | Submittal for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 01) | 10 | 02-Mr-26 | 12-Mr-26 | 2026-06-02 | 2026-06-16
E-SUB-B04-BAS02-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B04) (Bas 02) | 18 | 2026-02-09 | 2026-02-26 | 2026-05-02 | 2026-05-03
E-SUB-B04-BAS01-1040 | Submittal for Slabs Conc. Dim. & RFT DWGs (B04) (Bas 01) | 18 | 2026-02-09 | 46079 | 2026-06-02 | 2026-06-16
E-APP-B01-BAS02-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02) | 10 | 01-Mar-26 A | 02-Mar-26 A | 2026-05-12 | 2026-05-18
E-APP-B01-BAS01-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 01) | 10 | 15-Mar-26 A | 02-Apr-26 A | 2026-05-21 | 2026-06-01
E-APP-B02-BAS02-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B02) (Bas 02) | 10 | 01-Feb-26 A | 17-Feb-26 A | 2026-05-12 | 2026-05-18
E-APP-B02-BAS01-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B02) (Bas 01) | 10 | 01-Feb-26 A | 17-Feb-26 A | 2026-05-21 | 2026-06-01
E-APP-B03-BAS02-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 02) | 10 | 01-Feb-26 A | 12-Feb-26 A | 2026-05-03 | 2026-05-10
E-APP-B03-BAS01-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 01) | 10 | 01-Feb-26 A | 11-Feb-26 A | 2026-06-16 | 2026-06-21
E-APP-B04-BAS02-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B04) (Bas 02) | 10 | 01-Mar-26 A | 05-Mar-26 A | 2026-05-03 | 2026-05-10
E-APP-B04-BAS01-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B04) (Bas 01) | 10 | 01-Mar-26 A | 05-Mar-26 A | 2026-06-16 | 2026-06-21