## 06- RFI_Status
RFI | Activity ID | Activity Name | Submittion date | Reply | Delay beyond 10d | Note
BD-CW-SAMCO-PCO-RFI-MECH-001 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | 2026-02-16 | 2026-03-29 | -31 | Reply required before installing sump pit boxes, earthing network, and casting raft concrete
BD-CW-SAMCO-PCO-RFI-MECH-002 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 2026-02-17 | 2026-03-18 | -19 | Reply required before crane anchors, sleeves/openings coordination, reinforcement closure, and casting
BD-CW-SAMCO-PCO-RFI-MECH-003 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | 2026-03-10 | 2026-04-07 | -18 | Final sump pit and penetration details required before embedded MEP and raft casting
BD-CW-SAMCO-PCO-RFI-MECH-004 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 2026-03-10 | 2026-04-05 | -16 | Reply required before fixing wall penetrations, closing shuttering, casting wall side 2, and external pipe installation