CONSOLIDATED CONTRACTOR'S CLAIM No. 1

For Extension of Time and Additional Payment

Construction Works of the Civil Works for Buildings B1, B2, B3 and B4 at The Big Project

Roya-Big-2025-01

Between:

Samco Al-Wataniya for Construction

(the “Contractor”)

and

Roya for Real Estate Investment

(the “Employer”)

Cut-off Date:

25th May 2026

Table of Contents

1.	Preamble	3

1.1.	Purpose of the Submission	3

1.2.	Contractual Framework	3

1.3.	Scope of the Project	4

1.4.	Contract Data	5

1.5.	Priority of Contract Documents	6

1.6.	Without Prejudice and Reservation of Rights	6

2.	Interim Particulars	7

2.1.	Claim No. (01): Delayed Supply of Free-Issue Steel Reinforcement by the Employer	7

2.2.	Claim No. (02): Change in Issued for Construction (IFC) Drawing Packages	10

2.3.	Claim No. (03): Delayed Payment of Interim Payment Certificates (IPCs 1 through 5)	12

2.4.	Claim No. (04): Water leakage in Project Site	18

2.5.	Claim No. (05): Exceptionally Adverse Climatic Conditions	22

2.1.	Claim No. (06): Engineer’s Delayed Reply to the Contractor’s Documents	24

3.	Consolidated Summary of Entitlements	27

4.	Caveat	27

# Preamble

## Purpose of the Submission

- Samco Al-Wataniya for Construction (hereinafter the "Contractor") hereby submits this Consolidated Contractor's Claim to the Engineer in accordance with Sub-Clause 20.1 [Contractor's Claims] of the Conditions of Contract. This submission sets out the Contractor's entitlement to an Extension of Time for Completion arising from five distinct events and circumstances that have materially impacted the progress and cost of the Works.

- This consolidated submission comprises the following 6 separate claims:

- Claim 1:  Delayed Supply of Free-Issue Steel Reinforcement by the Employer

- Claim 2:  Changes in Issued for Construction (IFC) Drawing Packages

- Claim 3:  Delayed Payment of Interim Payment Certificates (IPCs 1 through 5)

- Claim 4:  Water leakage pipe break

- Claim 5:  Exceptionally Adverse Climatic Conditions

- Claim 6: Engineer’s Delayed Reply to the Contractor’s Documents

- During the course of the Works, the Contractor has encountered a series of events and circumstances arising from actions and omissions attributable to the Employer and/or the Engineer, and from events beyond the Contractor's control, which have materially impacted the progress, cost, and Time for Completion of the Works. Pursuant to the applicable provisions of the Conditions of Contract, the Contractor hereby formally submits this Consolidated Contractor's Claim setting out its entitlements to an Extension of Time for Completion and associated additional payment.

- The Contractor's entitlement to an extension of Time for Completion gives rise to a corresponding entitlement to prolongation costs. Given the ongoing nature of several delay events and the requirement to complete the delay analysis, prolongation costs will be quantified in full in a separate dedicated submission to be served on the Engineer in due course.

- By virtue of this submission, and to the cut-off date of 05 May 2026, the Contractor claims an extension of the Time for Completion for 164 days, modifying the completion date of the Project to be on 21 Sep 27, as derived from the delay analysis prepared by the Contractor and attached to the submission.

- Additionally, the Contractor claims an additional payment of EGP 232,772.84 (One Hundred Fourteen Thousand, Six Hundred and Eighty-Three Egyptian Pounds and 25/100) as interests on delayed payments up to the cut-off date of this submission.

## Contractual Framework

- This submission arises out of Contract Reference Roya-Big-2025-01 (the "Contract") between Roya for Real Estate Investment (the "Employer") and Samco Al-Wataniya for Construction (the "Contractor") for the Construction Works of the Civil Works for Buildings B1, B2, B3 and B4 at The Big Project.

- The Contract was made effective on 30 April 2025. According to Sub-Clause 8.1 [Commencement of Works] of the Particular Conditions of Contract, the Commencement Date is the latest of the following:

- Letter of Acceptance

- Site Handover

- Receipt of undertaking letter that the Employer is responsible for all permits

- Receipt of the advance payment

- Pursuant to the letter received from the Employer on 11 September 2025, it was confirmed that the Commencement Date for the Project is 11 September 2025, being the date on which all the requirements under Sub-Clause 8.1 were satisfied.

- The Works are required to be completed within 19 months from the Commencement Date, subject to such Extensions of Time as may be granted under the Contract. Therefore, the original completion date was set to be 11 April 2027.

## Scope of the Project

- The Big Project is a development comprising four (4) buildings designated Buildings B1, B2, B3 and B4. Under Contract Reference Roya-Big-2025-01, the Contractor is engaged by the Employer to carry out the Engineering, Procurement and Construction of the Civil Works for all four buildings on a fixed-price, lump-sum basis in accordance with the Contract and the Conditions of Contract.

- The Works are designed by the Employer and are executed in accordance with the IFC drawing packages and specifications issued by or on behalf of the Employer through the Engineer. The Conditions of Contract adopted are the FIDIC Conditions of Contract for Building and Engineering Works Designed by the Employer, First Edition 1999 (the "Red Book"), as modified by the Particular Conditions.

## Contract Data

- The key data and particulars of the Contract are set out in the table below, as derived from the Contract Agreement, Appendix to Tender, and associated contract documents.

| Contract Title | Construction Works of the Civil Works for Buildings B1, B2, B3 and B4 at The Big Project |
| --- | --- |
| Contract Reference | Roya-Big-2025-01 |
| Conditions of Contract | FIDIC Conditions of Contract for Building and Engineering Works Designed by the Employer, First Edition 1999 (The Red Book), as amended by the Particular Conditions |
| Commencement Date | 11 September 2025 |
| Time for Completion | 19 Months from the Commencement Date |
| Original Completion Date | 11 April 2027 |
| Employer | Roya for Real Estate Investment Block 1150/3, Abdelhamid Badawy Street, Sheraton, Heliopolis, Cairo, Egypt |
| Contractor | Samco Al-Wataniya for Construction 7b El Tayaran Street, Maniegel Al Cinema, Nasr City, Cairo Governorate 4450106 |
| Engineer | ACE Project Management - Moharram Bakhoum |
| Accepted Contract Amount | EGP 367,286,025 (Three Hundred Sixty-Seven Million, Two Hundred Eighty-Six Thousand and Twenty-Five Egyptian Pounds) |
| Performance Security | 5% of the Accepted Contract Amount |
| Advance Payment | 25% of the Accepted Contract Amount (30% Cash / 70% Free-Issue Steel Reinforcement supplied by the Employer) |
| Delay Damages | 1% per week of the value of outstanding Works |
| Maximum Delay Damages | 10% of the Contract Price |
| Governing Law | Laws of the Arab Republic of Egypt |
| Language of Contract | English |

## Priority of Contract Documents

- In the event of ambiguity or discrepancy between any of the documents forming part of the Contract, precedence shall be determined in accordance with Sub-Clause 1.5 [Priority of Documents] of the Particular Conditions of Contract and Clause 2 of the Contract Agreement. The order of priority is as follows:

- The Agreement

- The Appendix to Tender

- The Particular Conditions

- The General Conditions

- General Requirements

- The Bill of Quantities

- Drawings

- Soil Report

- Site Layout

## Without Prejudice and Reservation of Rights

- This submission is made without prejudice to any of the Contractor's other rights or remedies under the Contract or at law. The entitlement figures presented herein represent the Contractor's best assessment as at the cut-off date of this submission, being 25 May 2026. The Contractor expressly reserves the right to supplement, amend, and update this submission as further information becomes available, including the results of the ongoing delay analyses and the quantification of prolongation costs associated with each head of claim.

- The Contractor's entitlement to an extension of Time for Completion gives rise to a corresponding entitlement to prolongation costs. Given the ongoing nature of several delay events and the requirement to complete the delay analysis, prolongation costs will be quantified in full in a separate dedicated submission to be served on the Engineer in due course.

- Nothing contained in this submission shall be construed as a waiver of any right or remedy available to the Contractor under the Contract or applicable law, and all rights are expressly reserved.

# Interim Particulars

## Claim No. (01): Delayed Supply of Free-Issue Steel Reinforcement by the Employer

Executive Summary

- In accordance with Sub-Clause 14.2 of the Appendix to Tender, it is the Employer’s responsibility to supply the required steel reinforcement as part of the Advance payment; however, the Employer significantly delayed the supply of the required steel reinforcement, which has significantly delayed the Works as shown in the table below:

Contractual Basis

- Sub-Clause 4.20 [Employer’s Equipment and Free-Issue Material] of the Particular Conditions

“The Contractor shall promptly give notice to the Engineer of any shortage, defect or default in these Materials”

“the Contractor shall submit to the Engineer, for approval, a 1-month prior look-ahead schedule, in the form accepted by the Engineer, for the required free-issue Materials and Plant that covers the Contractor’s consumption during a one month duration”

- Sub-Clause 14.2 [Advance Payment] of the Appendix to Tender provides that:

“25% of the Accepted Contract Amount to be paid as follows

- 30% Cash against Bank Check.

- 70% Steel supplied by Employer according to the approved Programme”

- In light of the above, and since the Employer’s supply of steel has been significantly delayed, with the third batch of steel reinforcement still not delivered as of the date of this submission, the Contractor’s progress has been materially affected.

- Accordingly, the Contractor is entitled to an Extension of Time for Completion together with the associated Costs pursuant to Sub-Clause 8.4(e) [Extension of Time for Completion] and Sub-Clause 20.1 [Contractor’s Claims] of the Conditions of Contract.

Factual Background

- On 27 September 2025, the Contractor submitted the required quantities of reinforcement steel for the first batch.

- On 30 September 2025, the Contractor reduced the quantity of the first batch due to changes in the Site conditions to allow to ensure smooth progress of the excavation and replacement soil works.

- On 26 November 2025, the Contractor submitted the required quantities of reinforcement steel for the second batch with a total of 726 tons.

- On 9 December 2025, the Employer supplied 440.2 Ton of the first batch required quantity.

- On 6 January 2026, the Contractor submitted the required quantities of reinforcement steel for the third batch.

- On 15 January 2026, the Contractor submitted a notice of claim regarding the delay in supplying the second batch and highlighted that such delay shall delay the progress of the Works. Also, the Contractor informed the Engineer that, as a gesture of goodwill, it has supplied 120 tons of the required quantity to prevent the suspension of the Works.

- On 26 January 2026, the Contractor submitted a further notice of claim regarding the delay of the second batch to inform the Engineer of the continuous delay to supply the quantity of the second batch and to notify the Engineer that all the available steel, whether supplied by the Employer or the Contractor, have already been incorporated in the Works, and accordingly the Works shall be suspended.

- On 7 February 2026, the Contractor submitted a further notice of claim to notify the Engineer of the delay to receive the second and third batches of reinforcement steel and that the Contractor shall not be held liable for any suspension of the Works accordingly.

- On 16 February 2026, the Engineer provided that the steel reinforcement required for the relevant Works has already been delivered and that the Contractor already tried to mitigate the delay by supplying an amount of the required steel reinforcement.

- On 24 February 2026, the Contractor clarified that the quantities supplied by the Employer till the date of the Contractor’s letter are not compatible with the Site requirements and the quantities requested by the Contractor. Moreover, the Contractor asserted that the Contractor’s efforts and mitigation measures to supply some of the required steel reinforcement quantity, shall not be considered a waiver by the Contractors of its rights and accordingly, the Contractor shall not be held responsible for the occurring disruption and the delays resulting from the irregular supply of steel by the Employer.

- On 31 March 2026, the Contractor notified the Engineer that, till the date of its letter, merely half of the second batch has been delivered, and none of the third batch has been delivered. Also, the Contractor notified the Engineer that the available reinforcement steel at Site is insufficient to complete the planned Works.

- On 19 April 2026, the Contractor reiterated the content of its previous letter and urged the Engineer to expedite the process of supplying the steel reinforcement to prevent any further delays.

Entitlement

- Notwithstanding the Contractor’s mitigation measures and its efforts to progressively secure and make available approximately 565.5 tons of steel reinforcement to minimize the impact on the Works, such measures do not negate the fact that substantial disruption to the construction activities has occurred as a direct result of the inconsistent and delayed supply of steel reinforcement by the Employer, which remains the Employer’s responsibility under the Contract. The Contractor exerted all possible efforts to maintain progress and ensure continuity of the Works, and any temporary procurement or arrangement of steel quantities by the Contractor was undertaken solely for the benefit of the Project and as a gesture of good faith, without prejudice to its contractual entitlements.

- following the delay analysis performed, the Employer’s delayed and inconsistent supply of steel reinforcement was found to have impacted the critical path and resulted in a delay to completion equal to 111 days.

- In accordance with the SCL Delay and Disruption Protocol, Guidance to Core Principle 4, paragraph 4.6, which states that:

“The goal of the EOT procedure is the ascertainment of the appropriate contractual entitlement to an EOT; the analysis should not start from a position of considering whether the Contractor needs an EOT in order not to be liable for liquidated damages”.

- The Contractor is fully entitled to an Extension of Time together with all associated prolongation costs.

## Claim No. (02): Change in Issued for Construction (IFC) Drawing Packages

Executive Summary

- The Engineer issued numerous IFC drawing packages at various stages of the Project, which created confusing to the Contractor, in addition to the last one issued on the 18th of March 2026, which led to a suspension of the Project Works.

Contractual Basis

- As per Sub-Clause 1.9 [Delayed Drawings or Instructions] of the Conditions of the Contract, which states that:

“The Contractor shall give notice to the Engineer whenever the Works are likely to be delayed or disrupted if any necessary drawing or instruction is not issued to the Contractor within a particular time….”

- In addition to Sub-Clause 8.4 [Extension of Time for Completion] of the Conditions of the Contract, which states that:

“The Contractor shall be entitled, subject to Sub-Clause 20.1 [Contractor’s Claims], to an extension of the Time for Completion if and to the extent that completion for the purposes of Sub-Clause 10.1 [Taking Over of the Works and Sections] is or will be delayed by any of the following causes:

(b) a cause of delay giving an entitlement to extension of time under a Sub-Clause of these Conditions.”

- And as per Sub-Clause 20.1 [Contractor’s Claims] of the Conditions of the Contract, which stipulates that:

If the Contractor considers himself to be entitled to any extension of the Time for Completion and/or any additional payment, under any Clause of these Conditions or otherwise in connection with the Contract, the Contractor shall give notice to the Engineer, describing the event or circumstance giving rise to the claim. The notice shall be given as soon as practicable, and not later than 28 days after the Contractor became aware, or should have become aware, of the event or circumstance.

Factual Background

- At the outset, the Contractor from the Commencement Date is working on the IFC package submitted on the 4th of August 2025, which is different from the IFT drawing. However, it had not stopped the Contractor from performing his obligations.

- It shall be noted that the IFC drawing provided on the 4th of August 2025 contained only structural drawings.

- Then, on the 27th of October 2025, the Engineer issued an updated IFC drawing package, which contains the same structural drawings in addition to the architectural and electromechanical drawings.

- On the 18th of March 206, and after 6 months from the Commencement Date, the Engineer issued a new version of the IFC drawing, which is different from the IFC issued on the 27th of October 2025 to the extent that it prohibited the Contractor from performing his obligations.

- On the 31st of March 2026, the Contractor sent a letter to the Engineer explaining the differences between the two revisions of the IFC drawings and asking for the Engineer’s advice, but without any response from the Engineer.

- On the 4th of April 2026, the Contractor sent a Request for Information (RFI) No. 16, asking again for the Engineer’s advice.

- On the 11th of April 2026, the Contractor sent a letter to the Engineer stating that the column activities are suspended due to differences between the two revisions of the IFC drawings packages.

- On the same day, 11th of April 2026, the Contractor sent RFI No. 17, continuing with the same inquiries stated on the RFI No. 16.

- On the 14th of April 2026, the Engineer replied to the Contractor’s RFI No. 16, informing the Contractor to neglect the column’s size mentioned on the IFC package submitted on the 18th of March 2026.

- On the 16th of April 2026, the Contractor sent another letter to the Engineer inquiring about clarifications regarding the horizontal elements (slabs), as the Engineer instructed the Contractor to proceed with the columns as per the IFC package issued on the 27th of October 2025, while the slabs were to be in accordance with the IFC package issued on the 18th of March 2026.

- In addition, the Contractor, in his letter, clarified that he cannot work on two different IFC packages, one for the vertical elements and the other for the horizontal, and the Contractor needs one complete and final IFC package.

- On the 30th of April 2026, the Engineer issued a new IFC drawing package to the Contractor.

- On the 4th of May 2026, the Engineer replied to the Contractor’s RFI No. 17, informing him to follow the IFC package issued on the 30th of April 2026.

Entitlement

- Accordingly, by virtue of this Claim, the Contractor hereby claims its entitlement to an Extension of Time for Completion for the period of delayed payments, pursuant to Sub-Clause 14.8 and Sub-Clause 8.4 of the Particular Conditions of Contract, for 37 days.

## Claim No. (03): Delayed Payment of Interim Payment Certificates (IPCs 1 through 5)

Executive Summary

- The Contractor hereby submits this claim for financing charges, interest, and extension of Time for Completion arising from the persistent delayed payment of Interim Payment Certificates (IPCs) across 5 consecutive billing cycles, covering the period from December 2025 through March 2026.

- According to the Contract, the Employer is obligated to pay certified amounts within 45 days of the Engineer receiving the Contractor's statement and supporting documents. The Contract further provides that where payment is delayed beyond 60 days from the date of submission, the Contractor is entitled to both interest at 5% of the amounts due and an extension of Time for Completion.

- A review of the first five invoices submitted as of the cut-off date of the Claim reveals a consistent pattern of delayed payment:

| IPC No. | Submission Date | Payment Due (Day 45) | Day 60 | Actual Payment | Days Elapsed | Delay Beyond 45 Days | Delay Beyond 60 Days |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 06 Dec 2025 | 20 Jan 2026 | 04 Feb 2026 | 10 Feb 2026 | 66 | 21 | 6 |
| 2 | 29 Dec 2025 | 12 Feb 2026 | 27 Feb 2026 | 10 Mar 2026 | 71 | 26 | 11 |
| 3 | 24 Jan 2026 | 10 Mar 2026 | 25 Mar 2026 | 19 Apr 2026 | 85 | 40 | 25 |
| 4 | 25 Feb 2026 | 11 Apr 2026 | 26 Apr 2026 | 04 May 2026 | 68 | 23 | 8 |
| 5 | 25 Mar 2026 | 09 May 2026 | 24 May 2026 | Pending | 61+ | 16 | 1 |

- According to the payment details in the table above, it is evident that IPCs 1 through 4 were paid with delays of 21 to 40 days beyond the contractual deadline, while IPC 5 remains pending despite being submitted by the Contractor on 25 March 2026. Critically, as of the cut-off date of this submission, all five of these IPCs exceeded the 60-day threshold from submission, triggering entitlement to both interest and extension of Time for Completion under Sub-Clause 14.8 of the Particular Condition of the Contract.

- Such pattern of delay constitutes a material and ongoing breach of the Employer's payment obligations under the Contract. The consequences for the Contractor are severe, leading to significant cash flow disruption, incurring financing costs, and compromising the ability to sustain the required rate of progress.

- The Contractor has issued several notices requesting the Employer to timely disburse the outstanding and upcoming payments, while expressly reserving its rights to claim interest and an extension of the Time for Completion arising from the delayed payments, as further detailed in the Factual Background section of this Claim. Nevertheless, the Employer persistently continued to delay subsequent payments.

- Accordingly, by virtue of this Claim, the Contractor hereby claims its entitlement to the following:

- Financing charges and interest on all late payments at 5% of overdue certified amounts per Sub-Clause 14.8 of the Particular Conditions of Contract, calculated from Day 60 of submission, amounting to EGP 232,772.84.

- Extension of Time for Completion for the period of delayed payments, pursuant to Sub-Clause 14.8 and Sub-Clause 8.4 of the Particular Conditions of Contract, for 60 days.

Contractual Basis

- Sub-Clause 14.7 of the Particular Conditions establishes the Employer's payment obligation:

"The Employer shall pay to the Contractor: ... (b) the amount certified in each Interim Payment Certificate within 45 days after the Engineer receives the Statement and supporting documents."

- Sub-Clause 14.8 of the Particular Conditions establishes a tiered entitlement mechanism:

"If the Contractor does not receive payment in accordance with Sub-Clause 14.7 [Payment], the Contractor shall be entitled to interest on the amounts due which is equivalent to 5% of the amounts due and in accordance with the Egyptian Civil Law for the period of the delay in payment.

"If the payment is delayed a period between 15 days and 60 days, the Contractor shall be entitled to interest and Extension of Time subject to submitting a detailed claim to the Engineer for review and approval."

- Under this head of claim, the Contractor applies the 60-day threshold as measured from the date of submission of each IPC. According to the said Sub-Clause, the Day 60 threshold has been exceeded by all five IPCs that have reached that milestone (IPCs 1 through 5). Accordingly, the Contractor is entitled to both interest and an extension of Time for Completion in respect of the 5 delayed payments.

- Sub-Clause 8.4(e) of the Particular Conditions provides an independent entitlement to Extension of Time for Employer-caused delay:

“The Contractor shall be entitled subject to Sub-Clause 20.1 [Contractor's Claims] to an extension of the Time for Completion if and to the extent that completion for the purposes of Sub-Clause 10.1 [Taking Over of the Works and Sections] is or will b e delayed by any of the following causes:

- a Variation (unless an adjustment to the Time for Completion has been agreed under Sub-Clause 13.3 [Variation Procedure]) or other substantial change in the quantity of an item of work included in the Contract,

- a cause of delay giving an entitlement to extension of time under a Sub-Clause of these Conditions,

- exceptionally adverse climatic conditions,

- Unforeseeable shortages in the availability of personnel or Goods caused by epidemic or governmental actions, or

- any delay, impediment or prevention caused by or attributable to the Employer, the Employer's Personnel, or the Employer's other contractors on the Site.”

- Delayed payment, which directly impairs the Contractor's ability to fund, resource, and sustain activities, constitutes an Employer default giving rise to this entitlement.

- According to Articles 226 and 227 of the Egyptian Civil Code, a creditor is entitled to interest on overdue amounts as agreed by the Parties under the Contract.

Factual Background

- On 6 December 2025, the Contractor submitted the Statement for Interim Payment Certificate No. 1 to the Engineer. The contractual payment deadline, being 45 days thereafter, fell on 20 January 2026.

- On 28 January 2026, the Employer issued a cheque in respect of IPC 1 in the amount of EGP 18,299,639. However, the cheque was not physically delivered to the Contractor on that date.

- On 29 December 2025, the Contractor submitted the Statement for Interim Payment Certificate No. 2 to the Engineer. The contractual payment deadline fell on 12 February 2026.

- On 10 February 2026, the Contractor physically received the cheque issued in respect of IPC 1. The Contractor notes that while the cheque bore the issue date of 28 January 2026, the operative date of payment for all contractual and legal purposes is 10 February 2026, being the date on which the Contractor was effectively placed in possession of the payment instrument. Accordingly, IPC 1 was paid 66 days after submission and 21 days after the contractual payment deadline, thereby exceeding the Day 60 interest and Extension of Time threshold under Sub-Clause 14.8.

- On 24 January 2026, the Contractor submitted the Statement for Interim Payment Certificate No. 3 to the Engineer. The contractual payment deadline fell on 10 March 2026.

- On 24 February 2026, the Contractor issued a letter to the Engineer, drawing attention to the payment status of IPCs 1, 2, and 3. The letter confirmed that IPC 1 had been paid 21 days after the contractual due date, that IPC 2 remained outstanding beyond its contractual deadline, and that IPC 3 was approaching its payment due date. The Contractor expressly reserved its contractual entitlement to delay interest and its right to submit claims for extension of Time for Completion and associated costs where applicable.

- On the same date, 24 February 2026, the Contractor issued letter Ref. BD-CW-SAMCO-ACE-LET-STR-055 to the Engineer, confirming for the record that the cheque issued in respect of IPC 1 was physically received by the Contractor's authorized representative on 10 February 2026, notwithstanding the cheque's issue date of 28 January 2026. The letter attached a copy of the received cheque and the relevant authorization letter as supporting evidence, and was issued without prejudice to the Contractor's rights.

- On 25 February 2026, the Contractor submitted the Statement for Interim Payment Certificate No. 4 to the Engineer. The contractual payment deadline fell on 11 April 2026.

- On 10 March 2026, the Contractor received payment in respect of IPC 2, being 71 days after submission and 26 days after the contractual payment deadline.

- On 25 March 2026, the Contractor submitted the Statement for Interim Payment Certificate No. 5 to the Engineer. The contractual payment deadline fell on 9 May 2026.

- On 19 April 2026, the Contractor received payment in respect of IPC 3, being 85 days after submission and 40 days after the contractual payment deadline.

- On 16 April 2026, the Contractor issued a letter to the Engineer, providing a follow-up on the settlement status of all outstanding IPCs from IPC 1 to IPC 4. The Contractor again expressly reserved its entitlement to delay interest on IPCs 1, 2, and 3, warned that IPC 4 would become subject to the same if payment was not received within the contractual timeframe, and reserved its right to submit claims for delay interest and an extension of Time for Completion and associated costs.

- On 19 April 2026, the Engineer replied to the Contractor’s letters STR-054 (dated 24 February 2026) and STR-068 (dated 16 April 2026) rejecting the Contractor's assertion that payments had exceeded contractual due dates, characterizing it as based on an incorrect interpretation of the Contract. The Engineer raised two specific objections: first, that IPCs 1, 2, and 3 did not meet the minimum IPC threshold of 70% of the monthly cash flow as required by Sub-Clause 14.6 of the Appendix to Tender, and that any payments made against those submissions were administrative in nature and did not constitute acceptance or waiver; and second, that IPC 2, submitted on 29 December 2025, was submitted less than one month after IPC 1 on 6 December 2025, contrary to the contractual requirement for monthly submission.

- In this regard, the Contractor records its position as follows:

  - The Engineer did not, at the time of submission of IPCs 1, 2 or 3 issue any notice, query, or rejection on the grounds that the submissions failed to meet the minimum threshold. The first time this objection appears is in the Engineer's letter of 19 April 2026, which is more than 4 months after IPC 1 was submitted, and after all three IPCs had already been certified and paid in full by the Employer.

  - Sub-Clause 14.6 of the General Conditions of Contract expressly provides that where the Engineer decides not to issue an Interim Payment Certificate failing to achieve the threshold, he shall give notice to the Contractor. The decision to withhold certification on minimum threshold grounds is therefore not an automatic or self-executing right; it must be exercised promptly and communicated to the Contractor at the time the relevant IPC is received and assessed.

The Engineer did not issue any such notice in respect of IPCs 1, 2 or 3. Having failed to notify the Contractor of any objection within the 30-day certification window prescribed by Sub-Clause 14.6, and having proceeded to certify all three IPCs, the Engineer forfeited his entitlement to withhold certification on minimum threshold grounds in respect of those submissions. That right, once lost through the Engineer's own inaction, cannot be revived at a later stage as a retrospective justification for the delayed payment of those certificates.

  - Regarding the submission of IPC #2 in less than a month after IPC#1, the Contractor notes that both submissions were made during the Project's early establishment phase, prior to the regular monthly billing cycle being stabilised from IPC 3 onwards. IPC 1 itself was not submitted on the 25th of the month, reflecting the practical realities of the Project's commencement period. Furthermore, the purpose of the monthly submission cycle is to provide the Engineer with a regular and manageable assessment cadence and to prevent the Contractor from flooding the Engineer with multiple overlapping statements. A gap of 23 days versus a full calendar month caused no prejudice whatsoever to the Engineer's ability to assess, certify, or pay IPC 2.

  - It shall also be noted that payment of IPC 2 was received 71 days after submission and 26 days after the contractual payment deadline. Accordingly, even if calculated 30 days after IPC 1 (on 6 January 2026), payment would still be considered late.

- On 4 May 2026, the Contractor received payment in respect of IPC 4, being 68 days after submission and 23 days after the contractual payment deadline.

- On 25 May 2026, being the cut-off date of this claim, IPC 5 has been outstanding for 61 days since submission with no payment received.

Entitlement

- Quantum

- Based on the foregoing, the Contractor is entitled to payment of interest arising from the delayed payment of Interim Payment Certificates Nos. 1 through 5, at the rate of 5% per annum, calculated from Day 60 of each submission date to the cut-off date of this claim being 25 May 2026, in accordance with Sub-Clause 14.8 of the Particular Conditions and Article 226 of the Egyptian Civil Code, as detailed in the table below:

| INVOICE NO. | Date of submission to the consultant | Delay beyond 60 days | Net value of the payment certificate | Notes |
| --- | --- | --- | --- | --- |
| 1 | December 6, 2025 | 7 | 18,299,639.37 EGP | 17,547.60 |
| 2 | December 29, 2025 | 26 | 20,510,785.22 EGP | 73,052.11 |
| 3 | January 24, 2026 | 40 | 11,540,721.07 EGP | 63,236.83 |
| 4 | February 25, 2026 | 23 | 25,053,696.48 EGP | 78,936.30 |
| Total |  |  |  | 232,772.84 |

- Extension of Time for Completion

- Following the delay analysis performed, the Employer’s persistent delay in payment of the Contractor’s IPCs 1 to 5 was found to have impacted the critical path and resulted in a delay to completion equal to 50 days.

## Claim No. (04): Water leakage in Project Site

Executive Summary

- Multiple water leakage incidents occurred within Project Site during the early stage of the Project, which affected the Site conditions and disrupted the Contractor’s Works. Although the damaged pipes were repaired by the Employer, the resulting impacts continued beyond the repair dates, including issues affecting the boundary areas, which led to the Contractor being unable to proceed the planned Works. Consequently, the progress of the Works was disrupted, resulting in delays beyond the Contractor’s control.

Contractual Basis

- As per Sub-Clause 4.12 [Unforeseeable Physical Conditions] of the Conditions of the Contracts, which states that:

“In this Sub-Clause, "physical conditions" means natural physical conditions and manmade and other physical obstructions and pollutants, which the Contractor encounters at the Site when executing the Works, including sub-surface and hydro logical conditions but excluding climatic conditions. If the Contractor encounters adverse physical conditions which he considers to have been Unforeseeable, the Contractor shall give notice to the Engineer as soon as practicable.

…. In case there is any fault, discrepancy, or any other defect in the subsoil conditions, the Contractor shall be under the obligation to give notice to the Engineer, within the said 30 days”.

- As per Sub-Clause 8.4 [Extension of Time for Completion] of the Conditions of the Contract, which states that:

“The Contractor shall be entitled, subject to Sub-Clause 20.1 [Contractor’s Claims], to an extension of the Time for Completion if and to the extent that completion for the purposes of Sub-Clause 10.1 [Taking Over of the Works and Sections] is or will be delayed by any of the following causes:

(e) any delay, impediment or prevention caused by or attributable to the Employer, the Employer's Personnel, or the Employer's other contractors on the Site.”

- As per Sub-Clause 20.1 [Contractor’s Claims] of the Conditions of the Contract, which stipulates that:

If the Contractor considers himself to be entitled to any extension of the Time for Completion and/or any additional payment, under any Clause of these Conditions or otherwise in connection with the Contract, the Contractor shall give notice to the Engineer, describing the event or circumstance giving rise to the claim. The notice shall be given as soon as practicable, and not later than 28 days after the Contractor became aware, or should have become aware, of the event or circumstance.

Factual Background

- During the early stage of the Project, multiple water leakage incidents occurred within the Project Site, which affected the Site conditions.

- On 09 September 2025, the Contractor notified the Employer that a further water leakage incident occurred within the Site, which disrupted the ongoing DCPT and prevented the completion of the required test points.  The Contractor also notified the Employer that the survey team was unable to proceed with the boundary marking works for the tank area.

- On 17th September 2025, the Engineer issued letter stated that the water leakage incidents of 02 September 2025 and 09 September 2025 were minor and had been resolved on the same day and on 10 September 2025 respectively, and also state that the Contractor’s statement regarding the Site handed over on 07 September 2025 is inaccurate and the official records that the hand over for B1 and B2 were in 29 June 2025 while the handed over of B3 and B4 were in 07 September 2025, which is contradict the Employer’s Letter stated that the official Commencement Date for the Works is fixed as 11 September 2025.

- During the period from 11th September 2025 until 28th September 2025, the Contractor repeatedly notified the Employer that the excavation works could not properly proceed due to the condition of the soil following multiple water leakage incidents, which resulted in soil instability and collapse risk that affected the excavation activity.

- Although the Contractor suggested carrying out excavation side support works to mitigate the affected conditions; however, such suggestion was not accepted by the Employer.

- On 30th September 2025, the Contractor issued Minutes of Meeting confirming that during the meeting held on 25 September 2025, it was agreed that a separate excavation contractor appointed by the Employer would carry out the boundary marking works for Building B1, B2, B3& B4, and the works commencing on 28 September 2025. Also, the Contractor reported that the water tank area affected by a break in two pipes on 29 September 2025, which resulted in the suspension of excavation waste removal activities. In addition, the Contractor refer to the soil replacement sample has been sent to the laboratories of Cairo University.

- On 30th September 2025, the Contractor issued additional letter to document the occurrence of a break in two water pipes at the Project Site on 29 September 2025, which resulted in the suspension of excavation spoil removal works. Also, the Contractor state that the incident caused additional impacts in the surrounding area, including cracks and collapse at the rear of the Project.

- On 4th October 2025, the Engineer response to the Contractor stated that the water leakage incident which occurred on 29 September 2025 had been resolved on the same day.

- On 12th October 2025, the Engineer issue a letter state that the handing over certificate for the boundary excavation works of Buildings B1 and B2 were issued on 7th October 2025, and instructed the Contractor to commence the supply and execution of the soil replacement.

- On 13th October 2025, the Contractor clarified that the excavation boundaries for Buildings B1 and B2 were handed over on 7th October 2025, while the remaining building boundaries had not yet been handed over in accordance with the confirmation from the Employer. Furthermore, the Contractor stated that the soil replacement samples had already been submitted to Cairo University laboratories on 25 September 2025; however, the test result had not been received.

- On 15th October 2025, the Engineer response and state that, following the meeting held on 28 September 2025, the earthworks related to building B1 and B2 would be completed by the Employer, while the excavation works for building B1 and B2 will be under the Contractor responsibility, which is contradict with the agreement with the Employer in the mentioned meeting. Also, the Engineer confirms that the Contractor was permitted to proceed with the delivery of soil replacement material prior to the issuance of the laboratory test results, subject to the Contractor’s responsibility.

- On 27th October 2025, the Contractor issued a letter for Project status update, and mentioned that the DCPT had completed for building B1 to B4, but the IFC architectural and MEP drawings are still missing. In addition, the excavation works for building B3 and B4 were of hold until completion of the tank and pump room.

Entitlement

- Based on the aforementioned facts and the contractual basis, the Contractor is entitled to an Accordingly, by virtue of this Claim, the Contractor hereby claims its entitlement to an Extension of Time for Completion for the period of delayed payments, pursuant to Sub-Clause 14.8 and Sub-Clause 8.4 of the Particular Conditions of Contract, for 12 days.

## Claim No. (05): Exceptionally Adverse Climatic Conditions

Executive Summary

- The Contractor stopped working on the Site several times due to exceptional adverse climatic conditions, which could not have been predicted by the Contractor.

Contractual Basis

- As per Sub-Clause 8.4 [Extension of Time for Completion] of the Conditions of the Contract, which states that:

“The Contractor shall be entitled, subject to Sub-Clause 20.1 [Contractor’s Claims], to an extension of the Time for Completion if and to the extent that completion for the purposes of Sub-Clause 10.1 [Taking Over of the Works and Sections] is or will be delayed by any of the following causes:

(c) exceptionally adverse climatic conditions.”

- And virtue of Sub-Clause 8.4 [Extension of Time for Completion] of the Particular Conditions of the Contract, it states that

“In the event the Contractor can clearly demonstrate that the occurrence of such conditions is exceptional as compared to events recorded in official weather records for the area of the project over the last 5 years”.

- And as per Sub-Clause 20.1 [Contractor’s Claims] of the Conditions of the Contract, which stipulates that:

If the Contractor considers himself to be entitled to any extension of the Time for Completion and/or any additional payment, under any Clause of these Conditions or otherwise in connection with the Contract, the Contractor shall give notice to the Engineer, describing the event or circumstance giving rise to the claim. The notice shall be given as soon as practicable, and not later than 28 days after the Contractor became aware, or should have become aware, of the event or circumstance.

Factual Background

- The Contractor faced changes in the climatic conditions, which were different from those of the past five years, in which the Contractor could not have predicted.

- The graph below shows the rainfall over the past five years, which demonstrates that the year of 2026 was the heaviest year of rainfall.

- Therefore, the Contractor sent letters to the Engineer demonstrating the heavy rainfall, which forced the Contractor to stop the Works.

- In addition to the rainfall, the Contractor faced strong winds and heavy dust, which reached an average of 21.5 mph on the 14th of March 2026.

- It shall be highlighted that this number was not reached, nor was it even close to it, for the past five years. Therefore, the Contractor notified the Engineer of this issue.

Entitlement

- Accordingly, by virtue of this Claim, the Contractor hereby claims its entitlement to an Extension of Time for Completion for the period of delayed payments, pursuant to Sub-Clause 14.8 and Sub-Clause 8.4 of the Particular Conditions of Contract, for 5 days.

## Claim No. (06): Engineer’s Delayed Reply to the Contractor’s Documents

Executive Summary

- The Contractor submitted numerous submittals, for which the Engineer delayed the reply for a period longer than the contractual period, thereby affecting the Works of the Project.

Contractual Basis

- Sub-Claus 1.8 [Care and Supply of Documents]

The Contractor shall submit all submittals/transmittals 14 days before the start of any construction activity. The Engineer shall review and respond within 10 days. The Contractor shall resubmit within 3 days

- And virtue of Sub-Clause 8.4 [Extension of Time for Completion] of the Particular Conditions of the Contract, it states that

“In the event the Contractor can clearly demonstrate that the occurrence of such conditions is exceptional as compared to events recorded in official weather records for the area of the project over the last 5 years”.

- And as per Sub-Clause 20.1 [Contractor’s Claims] of the Conditions of the Contract, which stipulates that:

If the Contractor considers himself to be entitled to any extension of the Time for Completion and/or any additional payment, under any Clause of these Conditions or otherwise in connection with the Contract, the Contractor shall give notice to the Engineer, describing the event or circumstance giving rise to the claim. The notice shall be given as soon as practicable, and not later than 28 days after the Contractor became aware, or should have become aware, of the event or circumstance.

Factual Background

- The Contractor has several documents, which take more than 10 days, as per Sub-Clause 1.8 [Care and Supply of Documents], as stated above. Therefore, it affected the progress of the Project and delayed the Project’s overall duration.

- The table below shows the documents for which the Engineer was in delay in replying to them.

| # | Coding No. | Reference |  | Submitted Date | Received Date | Difference | Contractual Replaying Date | Over Due Period |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | NO. | Rev. |  |  |  |  |  |
| 1 | SAMCO-PCO-DS-STR-001-R00 | 1 | 0 | 28-08-2025 | 20-09-2025 | 23 | 10 | 13 |
| 2 | SAMCO-PCO-DS-STR-002-R00 | 2 | 0 | 20-09-2025 | 16-10-2025 | 26 | 10 | 16 |
| 3 | SAMCO-PCO-DS-STR-004-R01 | 4 | 1 | 05-11-2025 | 16-11-2025 | 11 | 10 | 1 |
| 4 | SAMCO-PCO-DS-STR-013-R00 | 13 | 0 | 22-10-2025 | 02-11-2025 | 11 | 10 | 1 |
| 5 | SAMCO-PCO-DS-STR-014-R00 | 14 | 0 | 22-10-2025 | 02-11-2025 | 11 | 10 | 1 |
| 6 | SAMCO-PCO-DS-STR-016-R00 | 16 | 0 | 03-11-2025 | 26-11-2025 | 23 | 10 | 13 |
| 7 | SAMCO-PCO-DS-STR-059-R01 | 59 | 1 | 30-12-2025 | 11-01-2026 | 12 | 10 | 2 |
| 8 | SAMCO-PCO-DS-STR-066-R01 | 66 | 1 | 06-01-2026 | 18-01-2026 | 12 | 10 | 2 |
| 9 | SAMCO-PCO-DS-STR-067-R01 | 67 | 1 | 06-01-2026 | 18-01-2026 | 12 | 10 | 2 |
| 10 | SAMCO-PCO-DS-STR-072-R00 | 72 | 0 | 29-12-2025 | 12-01-2026 | 14 | 10 | 4 |
| 12 | SAMCO-PCO-DS-STR-076-R00 | 76 | 0 | 06-01-2026 | 20-01-2026 | 14 | 10 | 4 |
| 13 | SAMCO-PCO-DS-STR-077-R00 | 77 | 0 | 06-01-2026 | 18-01-2026 | 12 | 10 | 2 |
| 14 | SAMCO-PCO-DS-STR-078-R00 | 78 | 0 | 06-01-2026 | 18-01-2026 | 12 | 10 | 2 |
| 15 | SAMCO-PCO-DS-STR-079-R00 | 79 | 0 | 06-01-2026 | 17-01-2026 | 11 | 10 | 1 |
| 16 | SAMCO-PCO-DS-STR-168-R00 | 168 | 0 | 06-05-2026 | ---- | 19 | 10 | 9 |
| 18 | BD-CW-SAMCO-PCO-RFI-STR-002-R01 | 2 | 1 | 08-12-2025 | 21-12-2025 | 13 | 10 | 3 |
| 19 | BD-CW-SAMCO-PCO-RFI-STR-008-R00 | 8 | 0 | 05-11-2025 | 16-11-2025 | 11 | 10 | 1 |
| 20 | BD-CW-SAMCO-PCO-RFI-STR-009-R00 | 9 | 0 | 05-11-2025 | 17-11-2025 | 12 | 10 | 2 |
| 21 | BD-CW-SAMCO-PCO-RFI-STR-013-R00 | 13 | 0 | 27-01-2026 | 10-02-2026 | 14 | 10 | 4 |
| 22 | BD-CW-SAMCO-PCO-RFI-STR-014-R00 | 14 | 0 | 02-02-2026 | 18-02-2026 | 16 | 10 | 6 |
| 23 | BD-CW-SAMCO-PCO-RFI-STR-016-R00 | 16 | 0 | 02-04-2026 | 14-04-2026 | 12 | 10 | 2 |
| 24 | BD-CW-SAMCO-PCO-RFI-STR-017-R00 | 17 | 0 | 12-04-2026 | 04-05-2026 | 22 | 10 | 12 |
| 25 | SAMCO-PCO-SDW-STR-004-R00 | 4 | 0 | 24-09-2025 | 07-10-2025 | 13 | 10 | 3 |
| 26 | SAMCO-PCO-SDW-STR-005-R00 | 5 | 0 | 14-10-2025 | 28-10-2025 | 14 | 10 | 4 |
| 27 | SAMCO-PCO-SDW-STR-006-R00 | 6 | 0 | 14-10-2025 | 28-10-2025 | 14 | 10 | 4 |
| 28 | SAMCO-PCO-SDW-STR-009-R00 | 9 | 0 | 26-10-2025 | 12-11-2025 | 17 | 10 | 7 |
| 29 | SAMCO-PCO-SDW-STR-009-R01 | 9 | 1 | 12-01-2026 | 26-01-2026 | 14 | 10 | 4 |
| 30 | SAMCO-PCO-SDW-STR-013-R01 | 13 | 1 | 18-12-2025 | 04-01-2026 | 17 | 10 | 7 |
| 31 | SAMCO-PCO-SDW-STR-014-R00 | 14 | 0 | 09-12-2025 | 21-12-2025 | 12 | 10 | 2 |
| 32 | SAMCO-PCO-SDW-STR-015-R00 | 15 | 0 | 16-12-2025 | 01-01-2026 | 16 | 10 | 6 |
| 33 | SAMCO-PCO-SDW-STR-016-R01 | 16 | 1 | 30-12-2025 | 13-01-2026 | 14 | 10 | 4 |
| 34 | SAMCO-PCO-SDW-STR-019-R00 | 19 | 0 | 13-01-2026 | 26-01-2026 | 13 | 10 | 3 |
| 36 | SAMCO-PCO-SDW-STR-055-R00 | 55 | 0 | 25-03-2026 | 05-04-2026 | 11 | 10 | 1 |
| 37 | SAMCO-PCO-SDW-STR-056-R00 | 56 | 0 | 25-03-2026 | 05-04-2026 | 11 | 10 | 1 |

Entitlement

- Accordingly, by virtue of this Claim, the Contractor hereby claims its entitlement to an Extension of Time for Completion for the period of delayed payments, pursuant to Sub-Clause 14.8 and Sub-Clause 8.4 of the Particular Conditions of Contract, for 49 days

# Consolidated Summary of Entitlements

- Extension of Time for Completion

[to be provided by the planning team]

- Additional Costs

The Contractor hereby claims an additional payment of EGP 232,772.84 (One Hundred Fourteen Thousand, Six Hundred and Eighty-Three Egyptian Pounds and 25/100) as interest on delayed payments up to the cut-off date of this submission in accordance with Sub-Clause 14.8 of the Particular Conditions of Contract.

The Contractor's entitlement to an extension of Time for Completion gives rise to a corresponding entitlement to prolongation costs. Given the ongoing nature of several delay events and the requirement to complete the delay analysis, prolongation costs will be quantified in full in a separate dedicated submission to be served on the Engineer in due course.

The Contractor respectfully requests the Engineer to determine and certify the Contractor's entitlements set out in this submission in accordance with Sub-Clause 3.5 [Determinations] and Sub-Clause 20.1 [Contractor's Claims] of the Conditions of Contract, without delay.

# Caveat

This is a claim submission for the purpose of providing a supported case for the Contractor’s entitlement to extension of Time for Completion and the associated cost as a result of the events detailed in this submission. The Contractor reserves its rights to amend, supplement, omit, or provide further information at any time should this be considered appropriate by either Party.

Neither the adopted methodology nor the claim generally takes into account any events taking place for reasons other than the subject matter of the claim or for events occurring during the period of time not considered under the claim. Contractor reserves all rights to pursue such matters separately.

Employer’s letter ref. BIG.P02_ROYA_LT_SAMCO_Commencement Date_002_00

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-010 dated 27 September 2025.

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-011 dated 30 September 2025

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-025 dated 26 November 2025

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-042 dated 6 January 2026

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-044 dated 15 January 2026

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-048 dated 26 January 2026

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-051 dated 7 February 2026

Engineer’s letter ref. BD-ACEPM-SAMCO-LET-028 dated 16 February 2026.

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-053 dated 24 February 2026

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-062 dated 31 March 2026

Contractor’s letter no.BD-CW-SAMCO-ACE-LET-STR-069 dated 24 February 2026

Transmittal Sheet (TRA) No. 006, dated 4th of August 2025

Transmittal Sheet (TRA) No. 013, dated 27th of October 2025

Transmittal Sheet (TRA) No. 017, dated 18th of March 2026

Contractor’s letter No. BD-CW-SAMCO-ACE-LET-STR-063, dated 31st of March 2026

Contractor’s Request for Information (RFI) No. 16, dated 4th of April 2026

Contractor’s letter No. BD-CW-SAMCO-ACE-LET-STR-066, dated 11th of April 2026

Contractor’s Request for Information (RFI) No. 17, dated 11th of April 2026

Engineer’s reply to the Contractor’s RFI No. 16, dated 14th of April 2026

Contractor’s letter No. BD-CW-SAMCO-ACE-LET-STR-067, dated 16th of April 2026

Contractor’s letter No. BD-CW-SAMCO-ACE-LET-STR-067, dated 16th of April 2026

Transmittal Sheet (TRA) No. 018, dated 30th of April 2026

Contractor’s letter ref. BD-CW-SAMCO-ACE-LET-STR-028 dated 6/12/2025

Contractor’s letter ref. BD-CW-SAMCO-ACE-LET-STR-046 dated 24/1/2026

Contractor’s letter ref. BD-CW-SAMCO-ACE-LET-STR-054 dated 24/2/2026

Contractor’s letter ref. BD-CW-SAMCO-ACE-LET-STR-055 dated 24/2/2026

Contractor’s letter ref. BD-CW-SAMCO-ACE-LET-STR-056 dated 25/2/2026

Contractor’s letter ref. BD-CW-SAMCO-ACE-LET-STR-059 dated 25/3/2026

Contractor’s letter ref. BD-CW-SAMCO-ACE-LET-STR-068 dated 16/4/2026

The Engineer’s letter ref. BD-ACEPM-SAMCO-LET-031 dated 19/4/2026

Contractor’s letter, No. BD-CW-SAMCO-ACE-LET-STR-005, dated: 10th September 2025

Engineer’s letter, No. BD-ACEPM-SAMCO-LET-005, dated: 17th September 2025

Employer’s Letter, No. BIG.P02_ROYA_LT_SAMCO_Commencement Date_002_00

Contractor’s letter, No. BD-CW-SAMCO-ACE-LET-STR-012, dated: 30th September 2025

Engineer’s letter, No. BD-ACEPM-SAMCO-LET-011, dated: 4th October 2025

Engineer’s letter, No. BD-ACEPM-SAMCO-LET-014, dated: 12th October 2025

Contractor’s letter, No. BD-CW-SAMCO-ACE-LET-018, dated: 13th October 2025

Engineer’s letter, No. BD-ACEPM-SAMCO-LET-015, dated: 15th October 2025

Contractor’s letter, No. BD-CW-SAMCO-ACE-LET-020, dated: 27th October 2025

Contractor’s Letter No. BD-CW-SAMCO-ACE-LET-STR-060, dated 25th of March 2026, Contractor’s Letter No. BD-CW-SAMCO-ACE-LET-STR-061, dated 29th of March 2026, and Contractor’s Letter No. BD-CW-SAMCO-ACE-LET-STR-065, dated 2nd of April 2026

https://www.wunderground.com/history/monthly/eg/al-nozha/HECA/date/2026-3

Contractor’s Letter No. BD-CW-SAMCO-ACE-LET-STR-058, dated 14th of March 2026