## WBS Flow Gantt
MEP WBS Flow Schedule — Same Page Gantt
Required Flow: Engineering → Submittal by Building → Approval by Building → Procurement PO/Delivery → Construction. Edit Start/Finish only; Duration and Gantt recalculate automatically.
Project ID | Total Activities | Schedule Start | Schedule Finish | Gantt Basis | [9 empty] | AUTO GANTT — formula-driven from Start / Finish Date
The Big -P.01-UP-20-April-26 | 85 | 2025-09-13 | 2026-10-24 | Weekly ¦ Auto from dates
WBS Code | Phase | Workstream | Building / Zone | Activity ID | Activity Name | Duration | Start Date | Finish Date | Predecessor | Successor | Related Civil Activity | Source WBS | Insertion / Planning Note | time axis 2025-09-13 to 2026-10-31
01. ENGINEERING ¦ SUBMITTAL
B01 — Activities
ENG-SUBMIT-B01-001 | Engineering | Submittal | B01 | MEP-SUB-B01-003 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B01-003 | CON-B01-1ST-1040 | Approved Baseline.EN.2.S.P02.B01.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B01-002 | Engineering | Submittal | B01 | MEP-SUB-B01-004 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B01-004 | CON-B01-1ST-1040 | Approved Baseline.EN.2.S.P02.B01.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B01-003 | Engineering | Submittal | B01 | MEP-SUB-B01-001 | Submittal of pipes shopdrawings | 18 | 2025-11-24 | 2025-12-12 |  | MEP-APP-B01-001 | CON-B01-SOG-1040 | Approved Baseline.EN.2.S.P02.B01.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-22 to 2025-12-06
ENG-SUBMIT-B01-004 | Engineering | Submittal | B01 | MEP-SUB-B01-002 | Submittal of pipes shopdrawings | 18 | 2025-12-01 | 2025-12-19 |  | MEP-APP-B01-002 | CON-B01-GR-1040 | Approved Baseline.EN.2.S.P02.B01.SUP.GF | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-29 to 2025-12-13
B02 — Activities
ENG-SUBMIT-B02-001 | Engineering | Submittal | B02 | MEP-SUB-B02-003 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B02-003 | CON-B02-1ST-1040 | Approved Baseline.EN.2.S.P02.B02.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B02-002 | Engineering | Submittal | B02 | MEP-SUB-B02-004 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B02-004 | CON-B02-1ST-1040 | Approved Baseline.EN.2.S.P02.B02.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B02-003 | Engineering | Submittal | B02 | MEP-SUB-B02-001 | Submittal of pipes shopdrawings | 18 | 2025-11-20 | 2025-12-08 |  | MEP-APP-B02-001 | CON-B02-SOG-1040 | Approved Baseline.EN.2.S.P02.B02.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-15 to 2025-12-06
ENG-SUBMIT-B02-004 | Engineering | Submittal | B02 | MEP-SUB-B02-002 | Submittal of pipes shopdrawings | 18 | 2025-12-06 | 2025-12-24 |  | MEP-APP-B02-002 | CON-B02-GR-1040 | Approved Baseline.EN.2.S.P02.B02.SUP.GF | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-12-06 to 2025-12-20
B03 — Activities
ENG-SUBMIT-B03-001 | Engineering | Submittal | B03 | MEP-SUB-B03-003 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B03-003 | CON-B03-1ST-1040 | Approved Baseline.EN.2.S.P01.B03.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B03-002 | Engineering | Submittal | B03 | MEP-SUB-B03-004 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B03-004 | CON-B03-1ST-1040 | Approved Baseline.EN.2.S.P01.B03.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B03-003 | Engineering | Submittal | B03 | MEP-SUB-B03-001 | Submittal of pipes shopdrawings | 18 | 2025-11-20 | 2025-12-08 |  | MEP-APP-B03-001 | CON-B03-SOG-1040 | Approved Baseline.EN.2.S.P01.B03.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-15 to 2025-12-06
ENG-SUBMIT-B03-004 | Engineering | Submittal | B03 | MEP-SUB-B03-002 | Submittal of pipes shopdrawings | 18 | 2025-12-10 | 2025-12-28 |  | MEP-APP-B03-002 | CON-B03-GR-1040 | Approved Baseline.EN.2.S.P01.B03.SUP.GF | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-12-06 to 2025-12-27
B04 — Activities
ENG-SUBMIT-B04-001 | Engineering | Submittal | B04 | MEP-SUB-B04-003 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B04-003 | CON-B04-1ST-1040 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B04-002 | Engineering | Submittal | B04 | MEP-SUB-B04-004 | Submittal of pipes shopdrawings | 18 | 2025-11-13 | 2025-12-01 |  | MEP-APP-B04-004 | CON-B04-1ST-1040 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-08 to 2025-11-29
ENG-SUBMIT-B04-003 | Engineering | Submittal | B04 | MEP-SUB-B04-001 | Submittal of pipes shopdrawings | 18 | 2025-11-24 | 2025-12-12 |  | MEP-APP-B04-001 | CON-B04-SOG-1040 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-11-22 to 2025-12-06
ENG-SUBMIT-B04-004 | Engineering | Submittal | B04 | MEP-SUB-B04-002 | Submittal of pipes shopdrawings | 18 | 2025-12-25 | 2026-01-12 |  | MEP-APP-B04-002 | CON-B04-GR-1040 | Approved Baseline.EN.2.S.P01.B04.SUP.GF | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-12-20 to 2026-01-10
Pump Room — Activities
ENG-SUBMIT-PumpRoom-001 | Engineering | Submittal | Pump Room | MEP-SUB-PUMPROOM-001 | Submittal of pipes shopdrawings | 18 | 2025-09-13 | 2025-10-01 |  | MEP-APP-PUMPROOM-001 | CON-B04-WT-1020 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB.1 | Submittal duration fixed at 18 days. Connected to approval by SS +12 days and FF +10 days. | bar: 2025-09-13 to 2025-09-27
02. ENGINEERING ¦ APPROVAL
B01 — Activities
ENG-APPROV-B01-001 | Engineering | Approval | B01 | MEP-APP-B01-003 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B01-003 | MEP-CON-B01-003 | CON-B01-1ST-1040 | Approved Baseline.EN.2.S.P02.B01.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B01-002 | Engineering | Approval | B01 | MEP-APP-B01-004 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B01-004 | MEP-CON-B01-004 | CON-B01-1ST-1040 | Approved Baseline.EN.2.S.P02.B01.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B01-003 | Engineering | Approval | B01 | MEP-APP-B01-001 | Approval of pipes shopdrawings | 10 | 2025-12-12 | 2025-12-22 | MEP-SUB-B01-001 | MEP-CON-B01-001 | CON-B01-SOG-1040 | Approved Baseline.EN.2.S.P02.B01.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-12-06 to 2025-12-20
ENG-APPROV-B01-004 | Engineering | Approval | B01 | MEP-APP-B01-002 | Approval of pipes shopdrawings | 10 | 2025-12-19 | 2025-12-29 | MEP-SUB-B01-002 | MEP-CON-B01-002 | CON-B01-GR-1040 | Approved Baseline.EN.2.S.P02.B01.SUP.GF | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-12-13 to 2025-12-27
B02 — Activities
ENG-APPROV-B02-001 | Engineering | Approval | B02 | MEP-APP-B02-003 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B02-003 | MEP-CON-B02-003 | CON-B02-1ST-1040 | Approved Baseline.EN.2.S.P02.B02.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B02-002 | Engineering | Approval | B02 | MEP-APP-B02-004 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B02-004 | MEP-CON-B02-004 | CON-B02-1ST-1040 | Approved Baseline.EN.2.S.P02.B02.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B02-003 | Engineering | Approval | B02 | MEP-APP-B02-001 | Approval of pipes shopdrawings | 10 | 2025-12-08 | 2025-12-18 | MEP-SUB-B02-001 | MEP-CON-B02-001 | CON-B02-SOG-1040 | Approved Baseline.EN.2.S.P02.B02.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-12-06 to 2025-12-13
ENG-APPROV-B02-004 | Engineering | Approval | B02 | MEP-APP-B02-002 | Approval of pipes shopdrawings | 10 | 2025-12-24 | 2026-01-03 | MEP-SUB-B02-002 | MEP-CON-B02-002 | CON-B02-GR-1040 | Approved Baseline.EN.2.S.P02.B02.SUP.GF | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-12-20 to 2026-01-03
B03 — Activities
ENG-APPROV-B03-001 | Engineering | Approval | B03 | MEP-APP-B03-003 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B03-003 | MEP-CON-B03-003 | CON-B03-1ST-1040 | Approved Baseline.EN.2.S.P01.B03.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B03-002 | Engineering | Approval | B03 | MEP-APP-B03-004 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B03-004 | MEP-CON-B03-004 | CON-B03-1ST-1040 | Approved Baseline.EN.2.S.P01.B03.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B03-003 | Engineering | Approval | B03 | MEP-APP-B03-001 | Approval of pipes shopdrawings | 10 | 2025-12-08 | 2025-12-18 | MEP-SUB-B03-001 | MEP-CON-B03-001 | CON-B03-SOG-1040 | Approved Baseline.EN.2.S.P01.B03.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-12-06 to 2025-12-13
ENG-APPROV-B03-004 | Engineering | Approval | B03 | MEP-APP-B03-002 | Approval of pipes shopdrawings | 10 | 2025-12-28 | 2026-01-07 | MEP-SUB-B03-002 | MEP-CON-B03-002 | CON-B03-GR-1040 | Approved Baseline.EN.2.S.P01.B03.SUP.GF | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-12-27 to 2026-01-03
B04 — Activities
ENG-APPROV-B04-001 | Engineering | Approval | B04 | MEP-APP-B04-003 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B04-003 | MEP-CON-B04-003 | CON-B04-1ST-1040 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B04-002 | Engineering | Approval | B04 | MEP-APP-B04-004 | Approval of pipes shopdrawings | 10 | 2025-12-01 | 2025-12-11 | MEP-SUB-B04-004 | MEP-CON-B04-004 | CON-B04-1ST-1040 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-11-29 to 2025-12-06
ENG-APPROV-B04-003 | Engineering | Approval | B04 | MEP-APP-B04-001 | Approval of pipes shopdrawings | 10 | 2025-12-12 | 2025-12-22 | MEP-SUB-B04-001 | MEP-CON-B04-001 | CON-B04-SOG-1040 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-12-06 to 2025-12-20
ENG-APPROV-B04-004 | Engineering | Approval | B04 | MEP-APP-B04-002 | Approval of pipes shopdrawings | 10 | 2026-01-12 | 2026-01-22 | MEP-SUB-B04-002 | MEP-CON-B04-002 | CON-B04-GR-1040 | Approved Baseline.EN.2.S.P01.B04.SUP.GF | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2026-01-10 to 2026-01-17
Pump Room — Activities
ENG-APPROV-PumpRoom-001 | Engineering | Approval | Pump Room | MEP-APP-PUMPROOM-001 | Approval of pipes shopdrawings | 10 | 2025-10-01 | 2025-10-11 | MEP-SUB-PUMPROOM-001 | MEP-CON-PUMPROOM-001 | CON-B04-WT-1020 | Approved Baseline.EN.2.S.P01.B04.SUB.2ndB.1 | Approval duration fixed at 10 days and linked to pipe shopdrawing submittal. | bar: 2025-09-27 to 2025-10-11
03. PROCUREMENT ¦ PO CREATION
B01 — Activities
PRO-POCREA-B01-001 | Procurement | PO Creation | B01 | MEP-PO-B01-003 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B01-003 | MEP-DEL-B01-003 | CON-B01-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B01-002 | Procurement | PO Creation | B01 | MEP-PO-B01-004 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B01-004 | MEP-DEL-B01-004 | CON-B01-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B01-003 | Procurement | PO Creation | B01 | MEP-PO-B01-001 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B01-001 | MEP-DEL-B01-001 | CON-B01-SOG-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
PRO-POCREA-B01-004 | Procurement | PO Creation | B01 | MEP-PO-B01-002 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B01-002 | MEP-DEL-B01-002 | CON-B01-GR-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
B02 — Activities
PRO-POCREA-B02-001 | Procurement | PO Creation | B02 | MEP-PO-B02-003 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B02-003 | MEP-DEL-B02-003 | CON-B02-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B02-002 | Procurement | PO Creation | B02 | MEP-PO-B02-004 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B02-004 | MEP-DEL-B02-004 | CON-B02-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B02-003 | Procurement | PO Creation | B02 | MEP-PO-B02-001 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B02-001 | MEP-DEL-B02-001 | CON-B02-SOG-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
PRO-POCREA-B02-004 | Procurement | PO Creation | B02 | MEP-PO-B02-002 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B02-002 | MEP-DEL-B02-002 | CON-B02-GR-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
B03 — Activities
PRO-POCREA-B03-001 | Procurement | PO Creation | B03 | MEP-PO-B03-003 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B03-003 | MEP-DEL-B03-003 | CON-B03-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B03-002 | Procurement | PO Creation | B03 | MEP-PO-B03-004 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B03-004 | MEP-DEL-B03-004 | CON-B03-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B03-003 | Procurement | PO Creation | B03 | MEP-PO-B03-001 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B03-001 | MEP-DEL-B03-001 | CON-B03-SOG-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
PRO-POCREA-B03-004 | Procurement | PO Creation | B03 | MEP-PO-B03-002 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B03-002 | MEP-DEL-B03-002 | CON-B03-GR-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
B04 — Activities
PRO-POCREA-B04-001 | Procurement | PO Creation | B04 | MEP-PO-B04-003 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B04-003 | MEP-DEL-B04-003 | CON-B04-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B04-002 | Procurement | PO Creation | B04 | MEP-PO-B04-004 | PO creation | 2 | 2025-10-21 | 2025-10-23 | MEP-APP-B04-004 | MEP-DEL-B04-004 | CON-B04-1ST-1040 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-10-18
PRO-POCREA-B04-003 | Procurement | PO Creation | B04 | MEP-PO-B04-001 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B04-001 | MEP-DEL-B04-001 | CON-B04-SOG-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
PRO-POCREA-B04-004 | Procurement | PO Creation | B04 | MEP-PO-B04-002 | PO creation | 2 | 2026-02-25 | 2026-02-27 | MEP-APP-B04-002 | MEP-DEL-B04-002 | CON-B04-GR-1040 | Approved Baseline.P.PC.DS.DR | PO creation duration fixed at 2 days. | bar: 2026-02-21
Pump Room — Activities
PRO-POCREA-PumpRoom-001 | Procurement | PO Creation | Pump Room | MEP-PO-PUMPROOM-001 | PO creation | 2 | 2025-12-03 | 2025-12-05 | MEP-APP-PUMPROOM-001 | MEP-DEL-PUMPROOM-001 | CON-B04-WT-1020 | Approved Baseline.P.PC.DS | PO creation duration fixed at 2 days. | bar: 2025-11-29
04. PROCUREMENT ¦ DELIVERY
B01 — Activities
PRO-DELIVE-B01-001 | Procurement | Delivery | B01 | MEP-DEL-B01-003 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B01-003 | MEP-CON-B01-003 | CON-B01-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B01-002 | Procurement | Delivery | B01 | MEP-DEL-B01-004 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B01-004 | MEP-CON-B01-004 | CON-B01-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B01-003 | Procurement | Delivery | B01 | MEP-DEL-B01-001 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B01-001 | MEP-CON-B01-001 | CON-B01-SOG-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
PRO-DELIVE-B01-004 | Procurement | Delivery | B01 | MEP-DEL-B01-002 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B01-002 | MEP-CON-B01-002 | CON-B01-GR-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
B02 — Activities
PRO-DELIVE-B02-001 | Procurement | Delivery | B02 | MEP-DEL-B02-003 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B02-003 | MEP-CON-B02-003 | CON-B02-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B02-002 | Procurement | Delivery | B02 | MEP-DEL-B02-004 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B02-004 | MEP-CON-B02-004 | CON-B02-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B02-003 | Procurement | Delivery | B02 | MEP-DEL-B02-001 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B02-001 | MEP-CON-B02-001 | CON-B02-SOG-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
PRO-DELIVE-B02-004 | Procurement | Delivery | B02 | MEP-DEL-B02-002 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B02-002 | MEP-CON-B02-002 | CON-B02-GR-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
B03 — Activities
PRO-DELIVE-B03-001 | Procurement | Delivery | B03 | MEP-DEL-B03-003 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B03-003 | MEP-CON-B03-003 | CON-B03-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B03-002 | Procurement | Delivery | B03 | MEP-DEL-B03-004 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B03-004 | MEP-CON-B03-004 | CON-B03-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B03-003 | Procurement | Delivery | B03 | MEP-DEL-B03-001 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B03-001 | MEP-CON-B03-001 | CON-B03-SOG-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
PRO-DELIVE-B03-004 | Procurement | Delivery | B03 | MEP-DEL-B03-002 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B03-002 | MEP-CON-B03-002 | CON-B03-GR-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
B04 — Activities
PRO-DELIVE-B04-001 | Procurement | Delivery | B04 | MEP-DEL-B04-003 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B04-003 | MEP-CON-B04-003 | CON-B04-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B04-002 | Procurement | Delivery | B04 | MEP-DEL-B04-004 | Delivery | 3 | 2025-10-23 | 2025-10-26 | MEP-PO-B04-004 | MEP-CON-B04-004 | CON-B04-1ST-1040 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-10-18 to 2025-10-25
PRO-DELIVE-B04-003 | Procurement | Delivery | B04 | MEP-DEL-B04-001 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B04-001 | MEP-CON-B04-001 | CON-B04-SOG-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
PRO-DELIVE-B04-004 | Procurement | Delivery | B04 | MEP-DEL-B04-002 | Delivery | 3 | 2026-02-27 | 2026-03-02 | MEP-PO-B04-002 | MEP-CON-B04-002 | CON-B04-GR-1040 | Approved Baseline.P.PC.DS.DR | Delivery duration fixed at 3 days after PO creation. | bar: 2026-02-21 to 2026-02-28
Pump Room — Activities
PRO-DELIVE-PumpRoom-001 | Procurement | Delivery | Pump Room | MEP-DEL-PUMPROOM-001 | Delivery | 3 | 2025-12-05 | 2025-12-08 | MEP-PO-PUMPROOM-001 | MEP-CON-PUMPROOM-001 | CON-B04-WT-1020 | Approved Baseline.P.PC.DS | Delivery duration fixed at 3 days after PO creation. | bar: 2025-11-29 to 2025-12-06
05. CONSTRUCTION ¦ CONSTRUCTION ACTIVITIES
B01 — Activities
CON-CONSTR-B01-001 | Construction | Construction Activities | B01 | MEP-CON-B01-002 | Construction : installation of sleeves for ground floor Slab (+214.7) | 2 | 2026-09-07 | 2026-09-09 | MEP-APP-B01-002, MEP-DEL-B01-002, E-APP-B01-GR-1030, E-APP-B01-GR-1020, CON-B01-GR-1030, CON-B01-BAS01-1140 | CON-B01-GR-1060, CON-B01-GR-1060 | CON-B01-GR-1040 | Approved Baseline.CON.P02.B01.SUP.GF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-09-05
CON-CONSTR-B01-002 | Construction | Construction Activities | B01 | MEP-CON-B01-001 | Construction : installation of sleeves for basement (1) Slab (+210m) | 2 | 2026-10-04 | 2026-10-06 | MEP-APP-B01-001, MEP-DEL-B01-001, CON-B01-SOG-1030, CON-B01-SOG-1030, E-APP-B01-SOG-1010, E-APP-B01-SOG-1000, P-MDEL-1150 | CON-B01-SOG-1050, CON-B01-SOG-1050, CON-B02-SOG-1040, AB-SUB-B01-SOG-1000 | CON-B01-SOG-1040 | Approved Baseline.CON.P02.B01.SUB.2ndB.SOG | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-03
CON-CONSTR-B01-003 | Construction | Construction Activities | B01 | MEP-CON-B01-003 | Construction : installation of pVC conduits and boxes for stair 05 from (+205m to +210m) | 2 | 2026-10-13 | 2026-10-15 | MEP-APP-B01-003, MEP-DEL-B01-003, E-APP-B01-1ST-1030, E-APP-B01-1ST-1020, E-APP-B01-1ST-1010, CON-B01-1ST-1030, CON-B01-GR-1110, E-APP-B01-1ST-1010 | CON-B01-1ST-1050, CON-B01-1ST-1050 | CON-B01-1ST-1040 | Approved Baseline.CON.P02.B01.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-10
CON-CONSTR-B01-004 | Construction | Construction Activities | B01 | MEP-CON-B01-004 | Construction : installation of pVC conduits and boxes for stair 05 from (+210m to +214.7m) | 2 | 2026-10-13 | 2026-10-15 | MEP-APP-B01-004, MEP-DEL-B01-004, E-APP-B01-1ST-1030, E-APP-B01-1ST-1020, E-APP-B01-1ST-1010, CON-B01-1ST-1030, CON-B01-GR-1110, E-APP-B01-1ST-1010 | CON-B01-1ST-1050, CON-B01-1ST-1050 | CON-B01-1ST-1040 | Approved Baseline.CON.P02.B01.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-10
B02 — Activities
CON-CONSTR-B02-001 | Construction | Construction Activities | B02 | MEP-CON-B02-002 | Construction : installation of sleeves for ground floor Slab (+214.7) | 2 | 2026-08-10 | 2026-08-12 | MEP-APP-B02-002, MEP-DEL-B02-002, CON-B02-GR-1030, CON-B02-BAS01-1110, E-APP-B02-GR-1020, E-APP-B02-GR-1030 | CON-B02-GR-1060, CON-B02-GR-1060 | CON-B02-GR-1040 | Approved Baseline.CON.P02.B02.SUP.GF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-08-08
CON-CONSTR-B02-002 | Construction | Construction Activities | B02 | MEP-CON-B02-003 | Construction : installation of pVC conduits and boxes for stair 02 (+205m to +210m) | 2 | 2026-10-05 | 2026-10-07 | MEP-APP-B02-003, MEP-DEL-B02-003, E-APP-B02-1ST-1030, E-APP-B02-1ST-1020, E-APP-B02-1ST-1010, CON-B02-1ST-1030, CON-B02-GR-1110 | CON-B02-1ST-1050, CON-B02-1ST-1050 | CON-B02-1ST-1040 | Approved Baseline.CON.P02.B02.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-03
CON-CONSTR-B02-003 | Construction | Construction Activities | B02 | MEP-CON-B02-004 | Construction : installation of pVC conduits and boxes for stair 02 from (+210m to +214.7m) | 2 | 2026-10-05 | 2026-10-07 | MEP-APP-B02-004, MEP-DEL-B02-004, E-APP-B02-1ST-1030, E-APP-B02-1ST-1020, E-APP-B02-1ST-1010, CON-B02-1ST-1030, CON-B02-GR-1110 | CON-B02-1ST-1050, CON-B02-1ST-1050 | CON-B02-1ST-1040 | Approved Baseline.CON.P02.B02.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-03
CON-CONSTR-B02-004 | Construction | Construction Activities | B02 | MEP-CON-B02-001 | Construction : installation of sleeves for basement (1) Slab (+210m) | 2 | 2026-10-22 | 2026-10-24 | MEP-APP-B02-001, MEP-DEL-B02-001, CON-B02-SOG-1030, CON-B02-SOG-1030, CON-B01-SOG-1040, E-APP-B02-SOG-1010, E-APP-B02-SOG-1000, E-APP-B02-SOG-1010, P-MDEL-1150 | CON-B02-SOG-1050, CON-B02-SOG-1050, AB-SUB-B02-SOG-1000, AB-SUB-B02-SOG-1010 | CON-B02-SOG-1040 | Approved Baseline.CON.P02.B02.SUB.2ndB.1 | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-17 to 2026-10-24
B03 — Activities
CON-CONSTR-B03-001 | Construction | Construction Activities | B03 | MEP-CON-B03-001 | Construction : installation of sleeves for basement (1) Slab (+210m) | 2 | 2026-08-05 | 2026-08-07 | MEP-APP-B03-001, MEP-DEL-B03-001, CON-B03-SOG-1030, CON-B03-SOG-1030, E-APP-B03-SOG-1010, E-APP-B03-SOG-1000, P-MDEL-1150 | CON-B03-SOG-1050, CON-B03-SOG-1050, CON-B04-SOG-1040, AB-SUB-B03-SOG-1000 | CON-B03-SOG-1040 | Approved Baseline.CON.P01.B03.SUB.2ndB.SOG | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-08-01
CON-CONSTR-B03-002 | Construction | Construction Activities | B03 | MEP-CON-B03-002 | Construction : installation of sleeves for ground floor Slab (+214.7) | 2 | 2026-08-16 | 2026-08-18 | MEP-APP-B03-002, MEP-DEL-B03-002, E-APP-B03-GR-1030, E-APP-B03-GR-1020, CON-B03-GR-1030, CON-B03-BAS01-1110 | CON-B03-GR-1050, CON-B03-GR-1060, CON-B03-GR-1070 | CON-B03-GR-1040 | Approved Baseline.CON.P01.B03.SUP.GF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-08-15
CON-CONSTR-B03-003 | Construction | Construction Activities | B03 | MEP-CON-B03-003 | Construction : installation of pVC conduits and boxes for stair 07 (+205m to +210m) | 2 | 2026-10-14 | 2026-10-16 | MEP-APP-B03-003, MEP-DEL-B03-003, E-APP-B03-1ST-1030, E-APP-B03-1ST-1020, E-APP-B03-1ST-1010, CON-B03-1ST-1030, CON-B03-GR-1110 | CON-B03-1ST-1050, CON-B03-1ST-1050 | CON-B03-1ST-1040 | Approved Baseline.CON.P01.B03.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-10
CON-CONSTR-B03-004 | Construction | Construction Activities | B03 | MEP-CON-B03-004 | Construction : installation of pVC conduits and boxes for stair 07 from (+210m to +214.7m) | 2 | 2026-10-14 | 2026-10-16 | MEP-APP-B03-004, MEP-DEL-B03-004, E-APP-B03-1ST-1030, E-APP-B03-1ST-1020, E-APP-B03-1ST-1010, CON-B03-1ST-1030, CON-B03-GR-1110 | CON-B03-1ST-1050, CON-B03-1ST-1050 | CON-B03-1ST-1040 | Approved Baseline.CON.P01.B03.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-10
B04 — Activities
CON-CONSTR-B04-001 | Construction | Construction Activities | B04 | MEP-CON-B04-001 | Construction : installation of sleeves for basement (1) Slab (+210m) | 2 | 2026-08-17 | 2026-08-19 | MEP-APP-B04-001, MEP-DEL-B04-001, CON-B04-SOG-1030, CON-B04-SOG-1030, CON-B03-SOG-1040, E-APP-B04-SOG-1010, E-APP-B04-SOG-1000, P-MDEL-1150 | CON-B04-SOG-1050, CON-B04-SOG-1050, AB-SUB-B04-SOG-1000, AB-SUB-B04-SOG-1010 | CON-B04-SOG-1040 | Approved Baseline.CON.P01.B04.SUB.3.1 | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-08-15
CON-CONSTR-B04-002 | Construction | Construction Activities | B04 | MEP-CON-B04-002 | Construction : installation of sleeves for ground floor Slab (+214.7) | 2 | 2026-08-20 | 2026-08-22 | MEP-APP-B04-002, MEP-DEL-B04-002, E-APP-B04-GR-1030, E-APP-B04-GR-1020, CON-B04-GR-1030, CON-B04-BAS01-1140 | CON-B04-GR-1050, CON-B04-GR-1060, CON-B04-GR-1060 | CON-B04-GR-1040 | Approved Baseline.CON.P01.B04.SUP.GF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-08-15 to 2026-08-22
CON-CONSTR-B04-003 | Construction | Construction Activities | B04 | MEP-CON-B04-003 | Construction : installation of pVC conduits and boxes for stair 02 (+205m to +210m) | 2 | 2026-10-10 | 2026-10-12 | MEP-APP-B04-003, MEP-DEL-B04-003, E-APP-B04-1ST-1030, E-APP-B04-1ST-1020, E-APP-B04-1ST-1010, CON-B04-1ST-1030, CON-B04-GR-1110 | CON-B04-1ST-1050, CON-B04-1ST-1050 | CON-B04-1ST-1040 | Approved Baseline.CON.P01.B04.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-10
CON-CONSTR-B04-004 | Construction | Construction Activities | B04 | MEP-CON-B04-004 | Construction : installation of pVC conduits and boxes for stair 02 from (+210m to +214.7m) | 2 | 2026-10-10 | 2026-10-12 | MEP-APP-B04-004, MEP-DEL-B04-004, E-APP-B04-1ST-1030, E-APP-B04-1ST-1020, E-APP-B04-1ST-1010, CON-B04-1ST-1030, CON-B04-GR-1110 | CON-B04-1ST-1050, CON-B04-1ST-1050 | CON-B04-1ST-1040 | Approved Baseline.CON.P01.B04.SUP.1stF | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2026-10-10
Pump Room — Activities
CON-CONSTR-PumpRoom-001 | Construction | Construction Activities | Pump Room | MEP-CON-PUMPROOM-001 | Construction : installation of 2 tanks puddle flanges Installation of trench drain pipe | 4 | 2025-10-12 | 2025-10-16 | MEP-APP-PUMPROOM-001, MEP-DEL-PUMPROOM-001, CON-B04-WT-1010, E-APP-B04-WT-1000, P-MDEL-1020 | CON-B04-WT-1030, AB-SUB-B04-WT-1000 | CON-B04-WT-1020 | Approved Baseline.CON.P01.B04.SUB.3.2 | MEP construction inserted within related civil activity; civil duration increases by the MEP inserted duration. | bar: 2025-10-11
Planning Control: keep WBS order. Update only Start Date / Finish Date where required. Duration and Gantt are formulas and will recalculate.