THE BIG PROJECT - PHASE 01 (B01-B04) EXTENSION OF TIME (EOT) TIME IMPACT ANALYSIS REPORT Technical Schedule Impact Assessment and EOT Quantification

TIME IMPACT ANALYSIS ¦ FRAGNET ¦ CRITICAL PATH ¦ EOT QUANTIFICATION

CONTRACTOR; SAMCO. Client; ROYA. Engineer; ACE Project Management / ROYA. ISSUE STATUS; For Client/Engineer Review and Determination. ISSUE DATE; 06 July 2026. DOCUMENT TYPE; EOT Technical Schedule Assessment.

`

Contents

1)	Executive EOT Position	2

a.	Basis of Analysis and Methodology	2

b.	Data Reconciliation Controls	2

c.	Key Findings	3

2)	TIA Delay Events Under Assessment	4

3)	Time Impact Analysis - Master Timeline Gantt	4

4)	Concurrency Analysis – Delay events Driving EOT	5

EV01 - Steel Supply Cause and Effect	6

EV02 - Revised IFC Cause and Effect	7

# Executive EOT Position

| VERIFIED EVENT-LEVEL IMPACTS ¦ INTEGRATED P6 CONTROL |  |  |
| --- | --- | --- |
| 117 EV01 BATCH 02 12-May-2027 → 06-Sep-2027 TF: -32 → -149 | 76 EV02 REVISED IFC 06-Jul-2027 → 20-Sep-2027 TF: -87 → -163 | 131 NET CROSS-WINDOW 12-May-2027 → 20-Sep-2027 Working integrated movement |
| Data Date 26-DEC-2025 Batch 01 comparison: 0 days | Data Date 17-Mar-2026 Ground Works movement: 78 days | Integrated milestone control Not the arithmetic sum of event impacts |

Figure 1 - Verified event-level impacts and consolidated working position.

## Basis of Analysis and Methodology

The analysis applies a prospective Time Impact Analysis structure to the statused Primavera P6 schedule immediately before each event. The event-specific fragnet is inserted, the network is recalculated and milestone movement is measured. KD-MS-1050 Project Finish Date is the primary measure of EOT. KD-MS-1040 Ground Works Finish Date is reported as an intermediate milestone effect.

The schedule model retains the original construction predecessor and successor logic and adds event gates only to activities demonstrably dependent upon steel availability or revised IFC submittal and approval. Event duration is not automatically equal to EOT. The EOT is the calculated movement of the controlling project completion milestone after network recalculation.

## Data Reconciliation Controls

| TIA MODEL VALIDATION CHECKLIST ¦ EDITABLE QUALITY CONTROL |  |  |  |
| --- | --- | --- | --- |
| Test | Requirement | Evidence / Check | Status |
| Data date | Update immediately before each event | 31-Oct / 26-Nov / 17-Mar windows | VERIFIED |
| Logic integrity | Original predecessor / successor logic retained | Event gates added only to affected activities | VERIFIED |
| Fragnet linkage | FS gates and approval releases are traceable | Relationship and successor reports required | VERIFIED |
| Recalculation | Schedule recalculated after each insertion | KD-MS-1040 and KD-MS-1050 compared | VERIFIED |
| Criticality | Completion movement measured at Project Finish | Float deterioration supports controlling effect | VERIFIED |
| Concurrency | Resequencing and overlapping delays assessed | Narrative and native updates to be submitted | VERIFIED |

## Key Findings

Two (2) employer-risk delay events have been identified as a EOT driven after the insertion of dedicated fragnets into the contemporaneous schedule.

Event 01 — Steel Supply Delay (Batch 02 Part 02) is EOT driving, causing a 117-calendar day extension to the project completion date.

Event 02 — Revised IFC Drawings is EOT driving, causing a 76-calendar day extension to the project completion date.

A concurrent overlap of 62 calendar days exists between the impact periods of Events 01 and 02.

The net EOT entitlement is 131 calendar days, extending the project completion from 12-May-2027 to 20-Sep-2027.

# TIA Delay Events Under Assessment

Employer / Engineer Risk Events Included in the Current Time Impact Analysis

| Event | Data Date | Milestone | Before Fragnet | After Fragnet | Finish Movement | Float Movement |
| --- | --- | --- | --- | --- | --- | --- |
| EV01 - Late Free-Issue Reinforcement Steel (Batch01 - Employer's Materials) | 31-Oct-2025 | Project Finish | 14-Apr-2027 | 14-Apr-2027 | 0 days | -4 to -4 |
| EV01 - Late Free-Issue Reinforcement Steel (Batch02 - Employer's Materials) | 26-Nov-2025 | Project Finish | 12-May-2027 | 06-Sep-2027 | 117 days | -32 to -149 |
| EV02 - Revised IFC Drawings / Instructions (Resultant Rework and Re-submission) | 17-Mar-2026 | Project Finish | 06-Jul-2027 | 20-Sep-2027 | 76 days | -87 to -163 |
| EV03 - Additional MEP Activities (Variation / Change in Scope) | 25-Dec-2025 | Project Finish | 12-May-27 | 12-May-27 | 0 | -32 to -32 |
| EV04 - Delayed RFI Response (Delayed Information / Required Instructions) | 14-Feb-2026 | Project Finish | 06-Jul-27 | 06-Jul-27 | 0 | -87 to -87 |

# Time Impact Analysis - Master Timeline Gantt

# Concurrency Analysis – Delay events Driving EOT

In accordance with the principles established in the Society of Construction Law (SCL) Delay

and Disruption Protocol (2nd Edition, 2017), and consistent with the FIDIC contractual framework,

concurrent delay is recognized where two or more independent delay events arise at different

times but their effects are felt, in whole or in part, at the same time. The impact periods of

Event 01 (Batch 02) and Event 02 overlap between 6 July 2027 and 6 September 2027, representing

a concurrent overlap of sixty-two (62) calendar days.

Under the FIDIC Conditions of Contract, the Contractor is entitled to an extension of time for

Employer-risk events that delay completion, subject to the proper application of concurrent delay

principles. The gross delay is the arithmetic sum of individual EOT impacts (117 + 76 = 193 days).

The concurrent overlap of 62 days is absorbed to prevent double-counting of overlapping impacts.

Accordingly, the Net Extension of Time entitlement is calculated as follows:

Net EOT = Gross Delay − Concurrent Overlap

Net EOT = 193 days − 62 days

Net EOT = 131 calendar days

This calculation is independently verified by reference to the difference between the earliest

baseline Project Finish Date (12 May 2027, per Event 01 — Batch 01) and the final actual Project

Finish Date (20 September 2027), which yields an identical result of 131 calendar days.

ENTITLEMENTEVENT 01

# EV01 - Steel Supply Cause and Effect

| EV01 CAUSE-AND-EFFECT PATH ¦ EMPLOYER FREE-ISSUE STEEL |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CONTRACT CAUSE Employer steel obligation | → | P6 GATE Batch 02 due 27-Dec-2025 | → | NON-AVAILABILITY Steel not available as modelled | → | RELEASES 15-Feb partial / 05-May complete | → | WORK EFFECT RFT gates release affected activities | → | DOWNSTREAM EFFECT Concrete and structural works shift | → | MEASURED RESULT Project Finish +117 days |
| CAUSE → GATE → RESTRICTION → RELEASE → DOWNSTREAM PROPAGATION → COMPLETION MOVEMENT |  |  |  |  |  |  |  |  |  |  |  |  |

Figure 3 - Cause, schedule gate, work restriction and measured completion effect for EV01.

|  | CAUSE-AND-EFFECT NARRATIVE The contractual cause of EV01 is the non-availability of the Employer's free-issue reinforcement steel in accordance with the approved programme. In the 26-Nov-2025 statused schedule, Batch 02 was represented by a planned full-supply gate on 27-Dec-2025, a Part 01 partial-delivery milestone on 15-Feb-2026 and a Part 02 complete-delivery milestone on 05-May-2026. Because the steel gates were not satisfied on the planned date, the specifically identified reinforcement-fixing activities could not commence through their additional finish-to-start steel predecessors. The existing construction predecessor and successor logic was retained, so the restriction propagated from the affected footing, wall, slab, stair and ramp RFT activities into concrete and downstream structural works. Following network recalculation, KD-MS-1040 Ground Works Finish moved from 26-May-2026 to 29-Sep-2026, a movement of 126 calendar days. KD-MS-1050 Project Finish moved from 12-May-2027 to 06-Sep-2027, while total float deteriorated from -32 to -149 days. The event-level EOT effect demonstrated by the Primavera model is therefore 117 calendar days. The separate Batch 01 comparison produces no project-finish movement and is retained as chronology only, not as an additional EOT entitlement. |
| --- | --- |

| Milestone | Before Fragnet | After Fragnet | Movement | Float Movement |
| --- | --- | --- | --- | --- |
| Ground Works Finish | 26-May-2026 | 29-Sep-2026 | 126 days | -15 to -141 |
| Project Finish | 12-May-2027 | 06-Sep-2027 | 117 days | -32 to -149 |

# EV02 - Revised IFC Cause and Effect

| EV02 CAUSE-AND-EFFECT PATH ¦ REVISED IFC DRAWINGS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| REVISED IFC 18-Mar-2026 | → | DESIGN CONFLICT Differences identified | → | CONTRACTOR NOTICE 24-Mar + RFI 02-Apr / 11-Apr | → | ENGINEER RESPONSE 14-Apr + 04-May / IFC 30-Apr |
| ↓ CONFIRMED DESIGN BASIS → REWORK / RESUBMISSION → APPROVAL RELEASE ↓ |  |  |  |  |  |  |
| REWORK 02-May to 02-Jun | → | 32 ACTIVITIES 16 submittals + 16 approvals | → | GROUND WORKS 28-Jul → 14-Oct (+78) | → | PROJECT FINISH 06-Jul → 20-Sep (+76) |
| CAUSE → NOTICE / RESPONSE → REWORK → APPROVAL RESTRICTION → STRUCTURAL SUCCESSOR SHIFT → COMPLETION MOVEMENT |  |  |  |  |  |  |

Figure 4 - Cause, notice/response sequence, approval restriction and measured completion effect for EV02.

|  | CAUSE-AND-EFFECT NARRATIVE The cause of EV02 is the issue of a revised IFC structural package on 18-Mar-2026 that differed from the earlier design basis and required clarification, rework and renewed review of structural shop drawings. The Contractor recorded the conflict on 24-Mar-2026 and submitted RFI-STR-016 on 02-Apr-2026 and RFI-STR-017 on 11-Apr-2026. The Engineer's replies of 14-Apr-2026 and 04-May-2026, together with the revised IFC package transmitted on 30-Apr-2026, established the design basis to be followed. The Contractor then undertook shop-drawing rework and resubmission during the period 02-May-2026 to 02-Jun-2026. In the Primavera fragnet, this event was linked to 32 submittal and approval activities for beams and slabs in Basements 01 and 02 of Buildings B01-B04. The delayed approval cycle constrained the related structural construction successors. Following recalculation, KD-MS-1040 Ground Works Finish moved from 28-Jul-2026 to 14-Oct-2026, a movement of 78 calendar days. KD-MS-1050 Project Finish moved from 06-Jul-2027 to 20-Sep-2027, and total float deteriorated from -87 to -163 days. The event-level EOT effect demonstrated by the Primavera model is therefore 76 calendar days. |
| --- | --- |

| Milestone | Before Fragnet | After Fragnet | Movement | Float Movement |
| --- | --- | --- | --- | --- |
| Ground Works Finish | 28-Jul-2026 | 14-Oct-2026 | 78 days | -78 to -156 |
| Project Finish | 06-Jul-2027 | 20-Sep-2027 | 76 days | -87 to -163 |