PLANNER HANDOVER GUIDE

Maintaining Project Data, Vercel Charts, Validation, and Publishing

| Calculation source Canonical project engines | Data boundary project_id + project_key | Publication standard Evidence first |
| --- | --- | --- |

1. Project Operating Rule

A project is identified by its manifest project_id and project_key. The folder may be renamed, but the project_id must remain stable. Never copy rows, reports, letters, contracts, or outputs from one project into another project folder.

2. Where to Update Data

| Folder | What belongs there | What the app does |
| --- | --- | --- |
| 01-data/import_templates | Project, WBS, activities, milestones, S-curve, EVM, contracts, payments, risks, and claims source tables. | Provides the primary source pipeline for workspace metrics and charts. |
| 02-delay_analysis | P6/XER, relationships, event register, concurrency, evidence, and canonical TIA inputs. | Builds the governed internal delay-analysis payload for that project only. |
| 05-contracts and 06-evidence | Authorized contract text, clauses, notices, evidence, and claim support. | Feeds the project-local Contract & Claims and AI evidence context. |
| 07-letters_intelligence | Incoming/outgoing letters and correspondence registers. | Feeds the project-local letters detector, thread, and evidence outputs. |
| vercel | Only optional missing-data CSV templates listed below. | Overrides the matching legacy source only when it has valid selected-project rows. |

3. Vercel Template Rules

The `vercel` folder is created automatically for every current and future project, including `_PROJECT_TEMPLATE`. Templates are header-only and non-destructive. Do not add sample rows. Every populated row must contain the owning project_id.

| Template | Use | Validation and precedence |
| --- | --- | --- |
| phase_progress.csv | Phase-level progress history for executive phase and completion views. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |
| discipline_progress_history.csv | Dated planned, actual, and forecast progress by discipline. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |
| activity_completion_history.csv | Dated started and completed activity counts. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |
| evm_period_history.csv | Dated BAC, PV, EV, AC, SPI, and CPI where the standard EVM register has no period series. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |
| planned_cash_flow.csv | Planned cash out series for the cash-flow comparison; payment/certification remains in the normal payments source. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |
| risk_assessment_history.csv | Dated risk snapshots and before/after mitigation scores. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |
| delay_event_classification.csv | Verified delay-event classification linked to an existing event; it cannot create an event. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |
| tia_recovery_scenario.csv | P6 and evidence-backed baseline, impacted, and recovery comparison scenario. | Valid Vercel rows win. A header-only file falls back to the normal project source. If both have rows, the app uses Vercel and reports a duplicate-source warning. |

4. Update and Publish Sequence

| Step | Planner action | Expected control |
| --- | --- | --- |
| 1 | Update only the owning project folder and retain project_id on each imported row. | No data is silently taken from another project. |
| 2 | Run the local generator and validation before publishing. | The generator refreshes selected-project JSON and output artifacts; the validator checks isolation and source contracts. |
| 3 | Review chart readiness cards and the data-quality findings for that project. | Missing input is visible as an action, never plotted as zero or substituted. |
| 4 | Run the Vercel publisher/watch workflow after validation passes. | The publisher regenerates, builds, synchronizes, deploys, and checks public assets. |
| 5 | Use Output Studio to issue formal outputs. | HTML, PDF, PowerPoint, and supporting files remain project-scoped and traceable. |

5. Chart-to-Source Checklist

| Tab | Chart source priority | Missing-data message |
| --- | --- | --- |
| Overview | s_curve.csv | Same-sized readiness card naming the required source. |
| Overview | projects.csv, progress_updates.csv | Same-sized readiness card naming the required source. |
| Overview | activities.csv | Same-sized readiness card naming the required source. |
| Overview | vercel/discipline_progress_history.csv | Same-sized readiness card naming the required source. |
| Overview | evm.csv, vercel/evm_period_history.csv | Same-sized readiness card naming the required source. |
| Overview | evm.csv, vercel/evm_period_history.csv | Same-sized readiness card naming the required source. |
| WBS | wbs.csv | Same-sized readiness card naming the required source. |
| WBS | wbs.csv | Same-sized readiness card naming the required source. |
| Activities | activities.csv | Same-sized readiness card naming the required source. |
| Activities | activities.csv | Same-sized readiness card naming the required source. |
| Activities | activities.csv | Same-sized readiness card naming the required source. |
| Activities | vercel/activity_completion_history.csv | Same-sized readiness card naming the required source. |
| Activities | activities.csv | Same-sized readiness card naming the required source. |
| Milestones | milestones.csv | Same-sized readiness card naming the required source. |
| Milestones | milestones.csv | Same-sized readiness card naming the required source. |
| Milestones | milestones.csv | Same-sized readiness card naming the required source. |
| S-Curve | s_curve.csv | Same-sized readiness card naming the required source. |
| S-Curve | vercel/discipline_progress_history.csv | Same-sized readiness card naming the required source. |
| S-Curve | s_curve.csv | Same-sized readiness card naming the required source. |
| EVM Analysis | evm.csv, vercel/evm_period_history.csv | Same-sized readiness card naming the required source. |
| EVM Analysis | evm.csv, projects.csv | Same-sized readiness card naming the required source. |
| EVM Analysis | evm.csv, vercel/evm_period_history.csv | Same-sized readiness card naming the required source. |
| EVM Analysis | evm.csv, vercel/evm_period_history.csv | Same-sized readiness card naming the required source. |
| Contracts | payments.csv | Same-sized readiness card naming the required source. |
| Contracts | vercel/planned_cash_flow.csv, planned_cash_flow.csv, payments.csv | Same-sized readiness card naming the required source. |
| Contracts | payments.csv | Same-sized readiness card naming the required source. |
| Contracts | contracts.csv | Same-sized readiness card naming the required source. |
| Risks | risks.csv | Same-sized readiness card naming the required source. |
| Risks | risks.csv | Same-sized readiness card naming the required source. |
| Risks | vercel/risk_assessment_history.csv | Same-sized readiness card naming the required source. |
| Risks | vercel/risk_assessment_history.csv | Same-sized readiness card naming the required source. |
| Delay Analysis - Time Impact Analysis | delay_events.csv | Same-sized readiness card naming the required source. |
| Delay Analysis - Time Impact Analysis | vercel/delay_event_classification.csv, 14-delay_event_classification.csv | Same-sized readiness card naming the required source. |
| Delay Analysis - Time Impact Analysis | vercel/delay_event_classification.csv, 14-delay_event_classification.csv | Same-sized readiness card naming the required source. |
| Delay Analysis - Time Impact Analysis | vercel/delay_event_classification.csv, delay_events.csv | Same-sized readiness card naming the required source. |
| Delay Analysis - Time Impact Analysis | vercel/tia_recovery_scenario.csv, 15-tia_recovery_scenario.csv | Same-sized readiness card naming the required source. |

6. Troubleshooting

A chart shows awaiting data: complete the named source for the selected project; do not copy a row from another project.

A chart data warning appears: check project_id, date format, duplicate periods, event/activity references, and required verification status.

A Vercel template does not appear: re-run project discovery/generation; it creates missing templates without overwriting user files.

A TIA result is not final: check the P6 reference, relationship evidence, concurrency, authorized contract route, and evidence reference.

A public site value is stale: run the generator, the validation script, and then the Vercel publisher. Confirm the project JSON timestamp before reviewing the website.