# Delay Analysis - Time Impact Analysis

ROYA-BIG PROJECT PHASE01 (B1-4)

Not calculated - individual indicative movements must not be summed without validated overlap, concurrency, and entitlement analysis.

# Source Pair and Event Register

| Event Id | Analysis Status | Before Data Date | After Data Date | Indicative Finish Movement Days | Blocking Reason |
| --- | --- | --- | --- | --- | --- |
| EV01-B01 | indicative_ready | 2025-10-31 | 2025-10-31 | 8.0 |  |
| EV01-B02 | indicative_ready | 2025-11-26 | 2025-11-26 | 117.0 |  |
| EV02-IFC | indicative_ready | 2026-03-17 | 2026-03-17 | 76.0 |  |
| EV03-MEP | blocked | 2025-12-25 | 2026-03-17 |  | Before/after XER internal P6 data dates are not a validated same-date comparison. |

# Evidence Gaps

Resolve blocked XER pairs before using all submitted events in a consolidated EOT position.