## Slide 1
Executive Dashboard
LMD Bridge & Road Interchange | LMD-Bridge
PROJECT
LMD Bridge & Road Interchange
PROJECT ID
LMD-Bridge
SECTOR
Bridges
STATUS
Delayed
CONTRACT VALUE
EGP 850,000,000
PAID AMOUNT
EGP 327,454,000
ACTUAL PROGRESS
31.0%
PLANNED PROGRESS
38.0%
BAC / PV / EV / AC
EGP 850,000,000 / EGP 343,174,699 / EGP 294,306,867 / EGP 311,965,280
SPI / CPI
0.86 / 0.94
Generated 01 Aug 2026 | Source-controlled selected-project output