## 01 Executive Finding
Item | Finding
Event | Event 01 - Employer late supply of free-issue reinforcement steel
Employer / Client Responsibility | The steel supply records identify Roya / Client supplied reinforcement steel quantities and delivery dates.
Primary Delay Evidence | Patch 02 Part 02 was delivered on 05-May-2026 against a 27-Nov-2025 BL/reference date, indicating 159 calendar days slippage against the supply reference.
TIA Finding Used in Charts | EV01 Batch 01 is treated as absorbed by float / no project completion impact; EV01 Batch 02 is treated as EOT-driving with 117 calendar days impact.
Affected Scope | 38 RFT activities identified across Batch 01, Batch 02, and Batch 03 files.
Relationship Evidence | RFT activities are linked to predecessor approvals / delivery activities and successor pouring, submittal, or as-built activities in the relationship workbook.
Risk / Reservation | Patch 03 is recorded as continuing delay event with no delivered quantity/date in the correspondence summary; keep it as pending unless formally assessed in a separate TIA event.

## 02 Steel Chronology
Event | Patch | Planned / BL Date | Actual Delivery Date | Delay Days vs BL | Quantity Ton | TIA Treatment | Remarks
Baseline / BL date |  | 2025-11-03 |  | 0 | 586.98 | Baseline supply requirement date | Reference date for client free-issue reinforcement steel supply.
Delivery of Patch01 - Part01 | Patch 01 Part 01 | 2025-11-03 | 2025-10-27 | -7 | 146.8 | Steel delivered by client | Assess delay against affected RFT activity sequence and available float.
Delivery of Patch01 - Part02 | Patch 01 Part 02 | 2025-11-03 | 2025-12-09 | 36 | 440.18 | Steel delivered by client | Assess delay against affected RFT activity sequence and available float.
Baseline / BL date |  | 2025-11-27 |  | 0 | 726.955 | Baseline supply requirement date | Reference date for client free-issue reinforcement steel supply.
Delivery of Patch02 - Part01 | Patch 02 Part 01 | 2025-11-27 | 2026-02-14 | 79 | 371.115 | Steel delivered by client | Assess delay against affected RFT activity sequence and available float.
Delivery of Patch02 - Part02 | Patch 02 Part 02 | 2025-11-27 | 2026-05-05 | 159 | 355.84 | Steel delivered by client | Assess delay against affected RFT activity sequence and available float.
Baseline / BL date |  | 2026-01-13 |  | 0 | 524 | Baseline supply requirement date | Reference date for client free-issue reinforcement steel supply.
Delivery of Patch03 | Patch 03 | 2026-01-13 |  |  | 0 | Pending / continuing delay | Assess delay against affected RFT activity sequence and available float.

## 03 MIR Supply Records
SR | Coding No. | Referance | Supplier | Unit/Bundle | Total Quantity | Date of delivery | Submitted date | Received Date | Admin Lag: Delivery to Submitted | Admin Lag: Delivery to Received
15 | SAMCO-PCO-MIR-STR-015-R00 | 15 | Roya | TON | 146.8 | 2025-10-28 | 2025-10-29 | 2025-10-29 | 1 | 1
50 | SAMCO-PCO-MIR-STR-050-R00 | 50 | Roya | TON | 440.18 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 0 | 0
70 | SAMCO-PCO-MIR-STR-067-R00 | 67 | Roya | TON | 52.71 | 2026-02-12 | 2026-02-14 | 2026-02-16 | 2 | 4
71 | SAMCO-PCO-MIR-STR-068-R00 | 68 | Roya | TON | 181.73 | 2026-02-13 | 2026-02-14 | 2026-02-16 | 1 | 3
72 | SAMCO-PCO-MIR-STR-069-R00 | 69 | Roya | TON | 60.425 | 2026-02-13 | 2026-02-14 | 2026-02-16 | 1 | 3
73 | SAMCO-PCO-MIR-STR-070-R00 | 70 | Roya | TON | 76.25 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 1 | 2
83 | SAMCO-PCO-MIR-STR-080-R00 | 80 | Roya | TON | 355.84 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 1 | 2

## 04 Affected Activities
Batch | Part | Building | Activity ID | Activity Name | Work Area
Batch 01 | Part01 | B04 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | Water Tank
Batch 01 | Part01 | B03 | CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | footing
Batch 01 | Part02 | B02 | CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | footing
Batch 01 | Part02 | B03 | CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | footing
Batch 01 | Part02 | B02 | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | footing
Batch 01 | Part02 | B04 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | Water Tank
Batch 02 | Part01 | B04 | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | footing
Batch 02 | Part01 | B04 | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | footing
Batch 02 | Part01 | B03 | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | footing
Batch 02 | Part02 | B02 | CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | Water Tank
Batch 02 | Part02 | B02 | CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | Bas 02
Batch 02 | Part02 | B02 | CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | Bas 02
Batch 02 | Part02 | B03 | CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | Bas 02
Batch 02 | Part02 | B03 | CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | Bas 02
Batch 03 | Delivery | B04 | CON-B04-BAS01-1010 | RFT for Walls, Col. & Cores (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B03 | CON-B03-BAS01-1010 | RFT for Walls, Col. & Cores (B03) (Bas 01) | Bas 01
Batch 03 | Delivery | B02 | CON-B02-BAS01-1060 | RFT for Slabs & Beams (B02) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1010 | RFT for Walls, Col. & Cores (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B02 | CON-B02-BAS01-1070 | RFT for Stairs (B02) (Bas 01) | Bas 01
Batch 03 | Delivery | B04 | CON-B04-BAS01-1070 | RFT for Slabs & Beams (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B04 | CON-B04-BAS01-1080 | RFT for Ramps (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B04 | CON-B04-BAS01-1090 | RFT for Stairs (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B03 | CON-B03-BAS01-1050 | RFT for Slabs & Beams (B03) (Bas 01) | Bas 01
Batch 03 | Delivery | B03 | CON-B03-BAS01-1070 | RFT for Stairs (B03) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1060 | RFT for Slabs & Beams (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1080 | RFT for Stairs (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1090 | RFT for Ramps (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B02 | CON-B02-BAS01-1010 | RFT for Walls, Col. & Cores (B02) (Bas 01) | Bas 01

## 05 Activity Breakdown
Batch | Part | Building | Affected_Activities
Batch 01 | Part01 | B03 | 1
Batch 01 | Part01 | B04 | 1
Batch 01 | Part02 | B02 | 2
Batch 01 | Part02 | B03 | 1
Batch 01 | Part02 | B04 | 1
Batch 02 | Part01 | B03 | 1
Batch 02 | Part01 | B04 | 2
Batch 02 | Part02 | B01 | 5
Batch 02 | Part02 | B02 | 3
Batch 02 | Part02 | B03 | 2
Batch 02 | Part02 | B04 | 5
Batch 03 | Delivery | B01 | 4
Batch 03 | Delivery | B02 | 3
Batch 03 | Delivery | B03 | 3
Batch 03 | Delivery | B04 | 4

## 06 Linked Relationships
Batch | Part | Building | Activity ID | Activity Name | Work Area | Predecessors ID | Predecessors Name | Successors ID | Successors Name
Batch 01 | Part01 | B04 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | Water Tank | CON-B04-WT-1060 | Shuttering for RC Raft (B04) (Water Tank) | CON-B04-WT-1080 | Pouring for RC Raft (B04) (Water Tank)
Batch 01 | Part01 | B04 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | Water Tank | E-APP-B04-WT-1020 | Approval for RC Raft RFT DWGs (B04) (Water Tank) | AB-SUB-B04-WT-1020 | Submittal for RC Raft RFT DWGs As-Built Drawing (B04) (Water Tank)
Batch 01 | Part01 | B04 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | Water Tank | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 01 | Part01 | B04 | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | Water Tank
Batch 01 | Part01 | B03 | CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | footing | CON-B03-FOOT-1040 | Shuttering for RC Raft & Footings (B03) (footing) | CON-B03-FOOT-1080 | Pouring for RC Raft & Footings (B03) (footing)
Batch 01 | Part01 | B03 | CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | footing | E-APP-B03-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B03) (footing) | AB-SUB-B03-FOOT-1020 | Submittal for RC Raft & Footings RFT DWGs As-Built Drawing (B03) (footing)
Batch 01 | Part01 | B03 | CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | footing | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 01 | Part01 | B03 | CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | footing
Batch 01 | Part02 | B02 | CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | footing | CON-B02-FOOT-1040 | Shuttering for RC Raft & Footings (B02) (footing) | CON-B02-FOOT-1090 | Pouring for RC Raft & Footings (B02) (footing)
Batch 01 | Part02 | B02 | CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | footing | E-APP-B02-FOOT-1020 | Approval for RC Raft & Footings RFT DWGs (B02) (footing) | AB-SUB-B02-FOOT-1020 | Submittal for RC Raft & Footings RFT DWGs As-Built Drawing (B02) (footing)
Batch 01 | Part02 | B02 | CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | footing | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 01 | Part02 | B02 | CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | footing
Batch 01 | Part02 | B03 | CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | footing | CON-B03-FOOT-1060 | Shuttering for Columns & Walls Below SOG (B01) (footing) | CON-B03-FOOT-1090 | Pouring Columns & Walls Below SOG (B01) (footing)
Batch 01 | Part02 | B03 | CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | footing | E-APP-B03-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B03) (footing)
Batch 01 | Part02 | B03 | CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | footing | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 01 | Part02 | B03 | CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | footing
Batch 01 | Part02 | B02 | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | footing | CON-B02-FOOT-1060 | Shuttering for Columns & Walls Below SOG (B01) (footing) | CON-B02-FOOT-1080 | Pouring Columns & Walls Below SOG (B01) (footing)
Batch 01 | Part02 | B02 | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | footing | E-APP-B02-FOOT-1020 | Approval for RC Raft & Footings RFT DWGs (B02) (footing)
Batch 01 | Part02 | B02 | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | footing | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 01 | Part02 | B02 | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | footing
Batch 01 | Part02 | B04 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | Water Tank | CON-B04-WT-1100 | Shuttering for Walls (B04) (Water Tank) | CON-B04-WT-1120 | Installation for Waterstop Insulation (B04) (Water Tank)
Batch 01 | Part02 | B04 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | Water Tank | E-APP-B04-WT-1030 | Approval for Col. & Walls DWGs (B04) (Water Tank) | CON-B04-WT-1130 | Pouring for Walls (B04) (Water Tank)
Batch 01 | Part02 | B04 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | Water Tank | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank) | AB-SUB-B04-WT-1030 | Submittal for Col. & Walls DWGs As-Built Drawing (B04) (Water Tank)
Batch 01 | Part02 | B04 | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | Water Tank
Batch 02 | Part01 | B04 | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | footing | CON-B04-FOOT-1040 | Shuttering for RC Raft & Footings (B04) (footing) | CON-B04-FOOT-1080 | Pouring for RC Raft & Footings (B04) (footing)
Batch 02 | Part01 | B04 | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | footing | E-APP-B04-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B04) (footing) | AB-SUB-B04-FOOT-1020 | Submittal for RC Raft & Footings RFT DWGs As-Built Drawing (B04) (footing)
Batch 02 | Part01 | B04 | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | footing | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 02 | Part01 | B04 | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | footing
Batch 02 | Part01 | B04 | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | footing | CON-B04-FOOT-1060 | Shuttering for Columns & Walls Below SOG (B01) (footing) | CON-B04-FOOT-1090 | Pouring Columns & Walls Below SOG (B01) (footing)
Batch 02 | Part01 | B04 | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | footing | E-APP-B04-FOOT-1030 | Approval for RC Raft & Footings RFT DWGs (B04) (footing)
Batch 02 | Part01 | B04 | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | footing | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 02 | Part01 | B04 | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | footing
Batch 02 | Part01 | B03 | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | Bas 02 | CON-B03-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B03) (Bas 02) | CON-B03-BAS02-1020 | Shuttering for Walls, Col. & Cores (B03) (Bas 02)
Batch 02 | Part01 | B03 | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | Bas 02 | E-APP-B03-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B03) (Bas 02) | CON-B03-BAS02-1020 | Shuttering for Walls, Col. & Cores (B03) (Bas 02)
Batch 02 | Part01 | B03 | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part01 | B03 | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | footing | CON-B01-FOOT-1040 | Shuttering for RC Raft & Footings (B01) (footing) | CON-B01-FOOT-1090 | Pouring for RC Raft & Footings (B01) (footing)
Batch 02 | Part02 | B01 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | footing | E-APP-B01-FOOT-1020 | Approval for RC Raft & Footings RFT DWGs (B01)
Batch 02 | Part02 | B01 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | footing | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 02 | Part02 | B01 | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | footing
Batch 02 | Part02 | B02 | CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | Bas 02 | CON-B02-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B02) (Bas 02) | CON-B02-BAS02-1020 | Shuttering for Walls, Col. & Cores (B02) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | Bas 02 | E-APP-B02-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B02) (Bas 02) | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2) | CON-B02-BAS02-1020 | Shuttering for Walls, Col. & Cores (B02) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | Bas 02 | CON-B04-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B04) (Bas 02) | CON-B04-BAS02-1020 | Shuttering for Walls, Col. & Cores (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | Bas 02 | E-APP-B04-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B04) (Bas 02) | AB-SUB-B04-BAS2-1000 | Submittal for Col. & Walls Conc. Dim. & RFT DWGs As-Built Drawing (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2) | CON-B04-BAS02-1020 | Shuttering for Walls, Col. & Cores (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1010 | RFT for Walls, Col. & Cores (B04) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | Bas 02 | CON-B01-BAS02-1000 | Scaffolding works for Walls, Col. & Cores (B01) (Bas 02) | CON-B01-BAS02-1020 | Shuttering for Walls, Col. & Cores (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | Bas 02 | E-APP-B01-BAS02-1000 | Approval for Col. & Walls Conc. Dim. & RFT DWGs (B01) (Bas 02) | CON-B01-BAS02-1020 | Shuttering for Walls, Col. & Cores (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1010 | RFT for Walls, Col. & Cores (B01) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | Water Tank | CON-B04-WT-1150 | Formwork for Top Slab (B04) (Water Tank) | CON-B04-WT-1170 | Pouring for Top Slab (B04) (Water Tank)
Batch 02 | Part02 | B04 | CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | Water Tank | E-APP-B04-WT-1040 | Approval for Slabs DWGs (B04) (Water Tank) | AB-SUB-B04-WT-1040 | Submittal for Slabs DWGs As-Built Drawing (B04) (Water Tank)
Batch 02 | Part02 | B04 | CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | Water Tank | P-MDEL-1000 | Delivery for Rebar Patch#1 (Footing & Water tank)
Batch 02 | Part02 | B04 | CON-B04-WT-1160 | RFT for Top Slab (B04) (Water Tank) | Water Tank
Batch 02 | Part02 | B02 | CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | Bas 02 | CON-B02-BAS02-1040 | Shuttering for Slabs & Beams (B02) (Bas 02) | CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | Bas 02 | E-APP-B02-BAS02-1020 | Approval for Beams Conc. Dim. & RFT DWGs (B02) (Bas 02) | CON-B02-BAS02-1100 | Pouring for Slabs & Beams (B02) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | Bas 02 | E-APP-B02-BAS02-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B02) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1060 | RFT for Slabs & Beams (B02) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | Bas 02 | CON-B04-BAS02-1040 | Shuttering for Slabs & Beams (B04) (Bas 02) | CON-B04-BAS02-1130 | Pouring for Slabs & Beams (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | Bas 02 | E-APP-B04-BAS02-1030 | Approval for Beams Conc. Dim. & RFT DWGs (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | Bas 02 | E-APP-B04-BAS02-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1060 | RFT for Slabs & Beams (B04) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | Bas 02 | CON-B04-BAS02-1050 | Shuttering for Stairs (B04) (Bas 02) | CON-B04-BAS02-1100 | Pouring for Stairs (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | Bas 02 | E-APP-B04-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1080 | RFT for Stairs (B04) (Bas 02) | Bas 02
Batch 02 | Part02 | B02 | CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | Bas 02 | CON-B02-BAS02-1050 | Shuttering for Stairs (B02) (Bas 02) | CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | Bas 02 | E-APP-B02-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B02) (Bas 02) | CON-B02-BAS02-1080 | Pouring for Stairs (B02) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2) | AB-SUB-B02-BAS2-1010 | Submittal for Stairs Conc. Dim.& RFT DWGs As-Built Drawing (B02) (Bas 02)
Batch 02 | Part02 | B02 | CON-B02-BAS02-1070 | RFT for Stairs (B02) (Bas 02) | Bas 02
Batch 02 | Part02 | B04 | CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | Bas 02 | CON-B04-BAS02-1070 | Shuttering for Ramps (B04) (Bas 02) | CON-B04-BAS02-1110 | Pouring for Ramps (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | Bas 02 | E-APP-B04-BAS02-1020 | Approval for Ramps Conc. Dim. & RFT DWGs (B04) (Bas 02)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B04 | CON-B04-BAS02-1090 | RFT for Ramps (B04) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | Bas 02 | CON-B01-BAS02-1040 | Shuttering for Slabs & Beams (B01) (Bas 02) | CON-B01-BAS02-1130 | Pouring for Slabs & Beams (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | Bas 02 | E-APP-B01-BAS02-1030 | Approval for Beams Conc. Dim. & RFT DWGs (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | Bas 02 | E-APP-B01-BAS02-1040 | Approval for Slabs Conc. Dim. & RFT DWGs (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1070 | RFT for Slabs & Beams (B01) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | Bas 02 | CON-B01-BAS02-1050 | Shuttering for Stairs (B01) (Bas 02) | CON-B01-BAS02-1100 | Pouring for Stairs (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | Bas 02 | E-APP-B01-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1080 | RFT for Stairs (B01) (Bas 02) | Bas 02
Batch 02 | Part02 | B01 | CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | Bas 02 | CON-B01-BAS02-1060 | Shuttering for Ramps (B01) (Bas 02) | CON-B01-BAS02-1110 | Pouring for Ramps (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | Bas 02 | E-APP-B01-BAS02-1020 | Approval for Ramps Conc. Dim. & RFT DWGs (B01) (Bas 02)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B01 | CON-B01-BAS02-1090 | RFT for Ramps (B01) (Bas 02) | Bas 02
Batch 02 | Part02 | B03 | CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | Bas 02 | CON-B03-BAS02-1040 | Shuttering for Slabs & Beams (B03) (Bas 02) | CON-B03-BAS02-1100 | Pouring for Slabs & Beams B03) (Bas 02)
Batch 02 | Part02 | B03 | CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | Bas 02 | E-APP-B03-BAS02-1020 | Approval for Beams Conc. Dim. & RFT DWGs (B03) (Bas 02)
Batch 02 | Part02 | B03 | CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | Bas 02 | E-APP-B03-BAS02-1030 | Approval for Slabs Conc. Dim. & RFT DWGs (B03) (Bas 02)
Batch 02 | Part02 | B03 | CON-B03-BAS02-1060 | RFT for Slabs & Beams (B03) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B03 | CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | Bas 02 | CON-B03-BAS02-1050 | Shuttering for Stairs (B03) (Bas 02) | CON-B03-BAS02-1080 | Pouring for Stairs (B03) (Bas 02)
Batch 02 | Part02 | B03 | CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | Bas 02 | E-APP-B03-BAS02-1010 | Approval for Stairs Conc. Dim. & RFT DWGs (B03) (Bas 02)
Batch 02 | Part02 | B03 | CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | Bas 02 | P-MDEL-1170 | Delivery for Rebar Patch#2 (Basement 2)
Batch 02 | Part02 | B03 | CON-B03-BAS02-1070 | RFT for Stairs (B03) (Bas 02) | Bas 02
Batch 03 | Delivery | B04 | CON-B04-BAS01-1010 | RFT for Walls, Col. & Cores (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B03 | CON-B03-BAS01-1010 | RFT for Walls, Col. & Cores (B03) (Bas 01) | Bas 01
Batch 03 | Delivery | B02 | CON-B02-BAS01-1060 | RFT for Slabs & Beams (B02) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1010 | RFT for Walls, Col. & Cores (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B02 | CON-B02-BAS01-1070 | RFT for Stairs (B02) (Bas 01) | Bas 01
Batch 03 | Delivery | B04 | CON-B04-BAS01-1070 | RFT for Slabs & Beams (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B04 | CON-B04-BAS01-1080 | RFT for Ramps (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B04 | CON-B04-BAS01-1090 | RFT for Stairs (B04) (Bas 01) | Bas 01
Batch 03 | Delivery | B03 | CON-B03-BAS01-1050 | RFT for Slabs & Beams (B03) (Bas 01) | Bas 01
Batch 03 | Delivery | B03 | CON-B03-BAS01-1070 | RFT for Stairs (B03) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1060 | RFT for Slabs & Beams (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1080 | RFT for Stairs (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B01 | CON-B01-BAS01-1090 | RFT for Ramps (B01) (Bas 01) | Bas 01
Batch 03 | Delivery | B02 | CON-B02-BAS01-1010 | RFT for Walls, Col. & Cores (B02) (Bas 01) | Bas 01