## ifc_summary
Period | Claim Treatment
2026-03-18 | A revised IFC drawing package Issued prevented the Contractor from proceeding work
2026-03-24 | Submitted a letter identifying the differences between the revised IFC and the original and requesting the Engineer’s instruction.
2026-04-30 | Engineer issued new IFC drawing package which resulted in re-submission of shop-drawings already approved
2026-05-02 | Contractor started working on shop-drawings and re-submission
2026-06-02 | Contractor finished resubmission of the re-worked shop-drawings
Gross IFC conflict = Issuing of the revised IFC package (18-March-2026) - Finishing re-submission of re-worked sshopd-drawings (02-June-2026) = -59 Days (6DAYS CALENDER)