## Plumbing First Fix
Activities — Water Tank MEP First Fix
Activity ID | Activity Name | Civil Activity Related | MEP Duration
Engineering
Submission
WT-Plmb-ENG-Pips | Submission of embedded pipes, washout/drain Shop-drawings |  | 18
WT-Plmb-ENG-SL | Submission of sleeves, puddle flanges Shop-drawings |  | 18
WT-ELEC-ENG | Submission of conduits and sleeves for level sensors and control cables Shop-drawings |  | 18
Approval
APP-WT-Plmb-ENG-Pips | Approval of embedded pipes, washout/drain Shop-drawings |  | 10
APP-WT-Plmb-ENG-SL | Approval of sleeves, puddle flanges Shop-drawings |  | 10
APP-WT-ELEC-ENG | Approval of conduits and sleeves for level sensors and control cables Shop-drawings |  | 10
Procurement
PRO-MEP | Fabrication & Supply of Material |  | 4
Construction
CON-WT-PLMB-RFT | Installation of embedded pipes, washout/drain | RFT for RC Raft (B04) (Water Tank) | 5
CON-WT-PLMB-Walls | Installation of sleeves, puddle flanges | RFT for Walls (B04) (Water Tank) | 4
CON-WT-ELEC-Walls | Installation of conduits and sleeves for level sensors and control cables | RFT for Walls (B04) (Water Tank) | 4