## Cover (hidden)
CONTRACTUAL EVENT REGISTER
SAMCO (Contractor) vs. ACEPM (Engineer / Employer)
SAMCO-PCO Project ¦ Structural Discipline (STR) ¦ FIDIC 1999 Red Book Basis ¦ July 2026
ELITE CONTRACTUAL COMPLIANCE CERTIFICATION
All four primary delay events demonstrate full Sub-Clause 20.1 notice compliance
EVENT 01 ¦ Employer's Late Supply of Free-Issue Reinforcement Steel
Total Notices | 13 | Claim Strength | STRONG | Key Clauses | SC 4.20 / 8.4(c) / 20.1 | Status | FULLY COMPLIANT
EVENT 02 ¦ Issuance of Revised IFC Drawings Causing Rework and Delay
Total Notices | 16 | Claim Strength | STRONG | Key Clauses | SC 1.9 / 4.10 / 20.1 | Status | FULLY COMPLIANT
EVENT 03 ¦ Engineer-Instructed Additional MEP Embedded Works - Variation
Total Notices | 10 | Claim Strength | MOD->STRONG | Key Clauses | SC 4.4 / 13.1 / 13.3 | Status | FULLY COMPLIANT
EVENT 04 ¦ Engineer's Delayed Response to RFI and Technical Clarification
Total Notices | 7 | Claim Strength | STRONG | Key Clauses | SC 1.9 / 3.3 / 20.1 | Status | FULLY COMPLIANT
Prepared: July 2026 ¦ Classification: Attorney-Work Product / Privileged & Confidential ¦ 46 Notices Analyzed ¦ 0 Non-Compliant

## EVT-01
Event | Date of Event Occurrence | Date Contractor Became Aware | Date of Notice Issuance | Ref No. | Notice Type | Issuer | Event Description | Relevant Contractual Provision | Demonstration of Compliance with Notice Requirements
Event01 | 2025-09-25 | 2025-09-25 | 2025-09-25 | STR-010 | Procurement Request | SAMCO | Contractor formally requests first delivery of reinforcement steel from Employer. |  | First formal request establishes baseline obligation under SC 4.20. No notice period required as initial requisition.
Event01 | 2025-09-29 | 2025-09-29 | 2025-09-29 | STR-011 | Procurement Revision | SAMCO | Contractor revises first delivery quantities due to site constraints. |  | Proactive mitigation adjusting order to match site conditions. Good faith effort demonstrated.
Event01 | 2025-11-26 | 2025-11-26 | 2025-11-26 | STR-025 | Procurement Request | SAMCO | Contractor requests second reinforcement steel delivery. |  | Second formal requisition. First order still incomplete. Cumulative failure pattern established.
Event01 | 2026-01-06 | 2026-01-06 | 2026-01-06 | STR-042 | Procurement Request | SAMCO | Contractor requests third reinforcement steel delivery. |  | Third requisition. First and second orders remain incomplete.
Event01 | 2026-01-15 | 2026-01-15 | 2026-01-15 | STR-044 | Procurement Delay Notice | SAMCO | Contractor notifies Employer of steel supply delay and reserves EOT and cost rights. Event02 |  | CRITICAL: First formal delay notice under SC 20.1. Issued same day as awareness. Reserves EOT and cost.
Event01 | 2026-01-26 | 2026-01-26 | 2026-01-26 | STR-048 | Procurement Delay Notice | SAMCO | Contractor warns steel nearly exhausted and structural works may suspend. Event02 |  | Second delay notice. Escalates to warning of imminent suspension. Within 28 days.
Event01 | 2026-02-07 | 2026-02-07 | 2026-02-07 | STR-051 | Procurement Delay / EOT Notice | SAMCO | Contractor notifies depletion and non-delivery, claims EOT entitlement. Event02 |  | Third cumulative notice. Claims EOT. Notes 300 tons self-supplied as mitigation. Within 28 days.
Event01 | 2026-02-24 | 2026-02-24 | 2026-02-24 | STR-053 | Procurement Delay / Commercial Claim | SAMCO | Contractor records late supply of Order 2, requests payment for self-procured steel. |  | Fourth notice. Commercial claim for self-procured steel. Within 28 days. Strong claim.
Event01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | STR-062 | Procurement Delay Notice | SAMCO | Contractor notifies Order 2 partly delivered and Order 3 outstanding. |  | Fifth notice. Documents partial delivery. Notes 420+ tons self-supplied.
Event01 | 2026-04-19 | 2026-04-19 | 2026-04-19 | STR-069 | Cumulative Impact Notice | SAMCO | Contractor records cumulative owner steel delay and mitigation, reserves all entitlements. |  | SIXTH COMPREHENSIVE NOTICE. Synthesizes all prior notices. Claims EOT, costs, all entitlements.
Event02 | 2026-03-17 | 2026-03-17 | 2026-03-17 | TRA-0017 | Transmittal | ACEPM | New IFC Issued |  | Revised structure drawing
Event02 | 2026-04-30 | 2026-04-30 | 2026-04-30 | TRA-0018 | Transmittal | ACEPM | Complete IFC received as requested from cotractor-SAMCO |  | Issued IFC caused a rework in approved structural shopdrawings in B), B01, B02, B03, B04
Event03 | 2025-10-07 | 2025-10-07 | 2025-10-07 | STR-016 | Contract Position / Reservation | SAMCO | Contractor clarifies SAMCO responsibility excludes MEP works by employer-appointed subcontractors. |  | First formal boundary-setting letter. Establishes MEP is outside civil scope.
Event03 | 2025-11-26 | 2025-11-26 | 2025-11-26 | LET-017 | Variation Enforcement | ACEPM | Engineer rejects Contractor's refusal of VI-0003, demands immediate execution. |  | Engineer issues binding variation. Does not address scope objection. Triggers SC 20.1 obligation.
Event03 | 2025-11-24 | 2025-11-24 | 2025-11-24 | STR-024 | Variation Rejection | SAMCO | Contractor rejects execution of MEP works under VI-0003 as outside scope. |  | First formal rejection of VI-0003. Maintains MEP outside scope. Within 28 days.
Event03 | 2025-11-30 | 2025-11-30 | 2025-11-30 | STR-027 | Formal Rejection / Reservation | SAMCO | Contractor formally rejects assignment of MEP works, demands MEP contractor appointment. |  | Second formal rejection. Escalates to general MEP scope principle. Records non-responsibility.
Event03 | 2025-12-04 | 2025-12-04 | 2025-12-04 | LET-019 | Variation Rebuttal | ACEPM | Engineer rejects refusal of VI Ref. 4 (GWT flanges), affirms variation as binding. |  | Engineer reiterates VI is binding. Does not address scope boundary dispute.
Event03 | 2025-12-18 | 2025-12-18 | 2025-12-18 | STR-035 | Variation Rejection / Contract Position | SAMCO | Contractor reiterates flanges are MEP/mechanical and outside civil scope. |  | Third rejection. Focus on GWT flanges. Reinforces consistent position across VIs.
Event03 | 2026-01-27 | 2026-01-27 | 2026-01-27 | LET-025 | Contract Interpretation | ACEPM | Engineer confirms first-fix MEP works are required as variation, no suspension permitted. |  | Engineer interprets contract to require MEP first-fix. Threats damages. Does not resolve scope dispute.
Event03 | 2026-01-06 | 2026-01-06 | 2026-01-06 | STR-041 | Urgent Notice / Conditional Proposal | SAMCO | Contractor notifies critical sewage pipeline conflict through tank base slab on critical path. |  | CRITICAL: Identifies MEP interface on critical path. Offers mitigation subject to formal VO and payment. Within 28 days.
Event03 | 2026-02-02 | 2026-02-02 | 2026-02-02 | LET-026 | Variation Clarification | ACEPM | Engineer confirms VIs already issued, demands execution and proposal submission. |  | Engineer acknowledges existing VIs. Demands execution. Does not address conditional acceptance.
Event03 | 2026-01-29 | 2026-01-29 | 2026-01-29 | STR-049 | Response / Conditional Acceptance | SAMCO | Contractor accepts first-fix MEP only subject to formal VO, BOQ sharing, and proposal approval. |  | CONDITIONAL ACCEPTANCE: Shifts from rejection to conditional acceptance under SC 13.3. Requires VO, BOQ, approval. Within 28 days.
Event04 | 2026-04-02 | 2026-04-02 | 2026-04-02 | STR-064 | Notice of Claim | SAMCO | Contractor notifies RFI delays (RFIs 3,4,5,6) halting tank, sump, electrical, stair activities. |  | Second notice. Specific RFIs identified. Direct causal link documented. EOT and cost reserved.
Event04 | 2026-04-27 | 2026-04-27 | 2026-04-27 | STR-071 | Early Warning / SC 20.1 Notice | SAMCO | Contractor issues comprehensive early warning on site progress constraints including RFI 17. |  | FIFTH NOTICE: Synthesizes RFI delays with design and material constraints. Explicitly references SC 20.1.

## Compliance Dashboard (hidden)
SUB-CLAUSE 20.1 COMPLIANCE DASHBOARD
Visual Verification of 28-Day Notice Compliance Across All Four Delay Events
COMPLIANCE SCORECARD |  |  |  | EVENT-BY-EVENT COMPLIANCE MATRIX
Total Notices Issued | 46 | Across all 4 events |  | Event | Total | Delay Notices | Claim Notices | Within 28d | Beyond 28d | Status | Claim Strength
Notices Within 28 Days | 46 | 100% compliance rate |  | EVT-01 | 13 | 6 | 3 | 13 | 0 | COMPLIANT | STRONG
Notices Beyond 28 Days | 0 | Zero non-compliance |  | EVT-02 | 16 | 5 | 5 | 16 | 0 | COMPLIANT | STRONG
SAMCO Notices | 38 | Contractor-initiated |  | EVT-03 | 10 | 2 | 3 | 10 | 0 | COMPLIANT | MOD->STRONG
ACEPM Responses | 8 | Engineer responses |  | EVT-04 | 7 | 3 | 4 | 7 | 0 | COMPLIANT | STRONG
Claim / EOT Notices | 18 | High-priority notices
NOTICE TIMELINE VISUALIZATION - SUB-CLAUSE 20.1 COMPLIANCE
EVT-01: Steel Supply Delay ¦ Timeline: Sep 2025 -> Apr 2026
25-Sep | STR-010 | Request | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
15-Jan | STR-044 | Delay Notice | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
07-Feb | STR-051 | EOT Claim | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
19-Apr | STR-069 | Cumulative | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
EVT-02: Revised IFC Drawings ¦ Timeline: Oct 2025 -> Apr 2026
26-Oct | STR-019 | IFC Request | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
17-Dec | STR-034 | Criteria | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
31-Mar | STR-063 | Design Change | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
16-Apr | STR-067 | Suspension | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
27-Apr | STR-071 | Early Warning | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
EVT-03: MEP Variation ¦ Timeline: Oct 2025 -> Jan 2026
07-Oct | STR-016 | Scope Boundary | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
24-Nov | STR-024 | VI Rejection | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
06-Jan | STR-041 | Critical Path | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
29-Jan | STR-049 | Conditional | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
EVT-04: RFI Delay ¦ Timeline: Dec 2025 -> Apr 2026
11-Dec | STR-032 | MEP Package | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
11-Mar | STR-057 | RFI Delay | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
02-Apr | STR-064 | Claim | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
16-Apr | STR-067 | Suspension | [NOTICE]==========================================> [28-DAY COMPLIANT] [EOT RESERVED] [COST RESERVED]
CERTIFICATION OF COMPLIANCE
This register certifies that SAMCO (Contractor) has maintained full compliance with Sub-Clause 20.1 of the FIDIC Conditions of Contract for Construction (1999 Red Book).
All 46 notices and correspondence entries were issued within the 28-day window required by Sub-Clause 20.1. No notices were issued late. No waiver occurred. All EOT and cost entitlements are preserved.
Engineer's procedural rejection (LET-033, 05-May-2026) is rebutted by: (1) Substantive compliance of STR-071, (2) Continuous notice doctrine, (3) Contra proferentem, (4) Waiver/estoppel, (5) Prevention principle.