Ref No.: BD-CW-SAMCO-ACE-LET-STR-089                                                                   12-July-2026

To: ACE Project Management | Moharram Bakhoum

Attention: Eng. Shady Elkersh (Project Manager)

Project Name: The Big Business District.

Contract/Package:  Construction Works of the Civil Works for Buildings B1, B2, B3 and B4 – Phase 1.

Subject: Submission of Revised Interim Particulars for Contractor's Claim No. (01) for Extension of Time.

Dear Sir,

| Reference 1 | Engineer's Letter Ref. BD-ACEPM-SAMCO-LET-039 dated 23-Jun-2026 |
| --- | --- |
| Reference 2 | Contractor's Letter Ref. BD-CW-SAMCO-ACE-LET-STR-086 dated 17-Jun-2026 |

Dear Sir,

With reference to the Engineer's above-referenced letter requesting additional supporting documents and particulars in respect of the Contractor's Interim Claim No. 1 for Extension of Time.

In compliance with the Engineer's request, the Contractor hereby submits this formal response together with the supporting particulars identified herein. The response is structured to address each of the five matters raised by the Engineer, namely: (i) the notice and correspondence register; (ii) cause-and-effect analysis; (iii) event-specific Time Impact Analysis; (iv) comparison against the contractual milestones and Time for Completion; and (v) clarification of the stated cut-off date.

The Contractor has distinguished between verified contractual and schedule records, the Contractor's entitlement position, and matters that require confirmation by the governing native Primavera P6 files or contemporaneous records. Where the available records do not support a definitive statement, the matter is expressly identified rather than presented as an established fact.

Best Regards,

Eng. Mohammed Sami Mohammed

Project Manager

`

# Summary of Findings

The Contractor hereby submits comprehensive supporting documentation demonstrating that:

(a) all contractual notice requirements under Sub-Clause 20.1 have been fully complied with

(b) the cause-and-effect nexus between each employer-risk event and the resultant delay is clearly established through the TIA methodology

(c) the steel reinforcement delay is the primary EOT-driving event (117 days)

(d) the revised IFC drawings constitute a secondary EOT-driving event (71 days)

(e) the net EOT entitlement, after absorption of the 62-day concurrent overlap, is 126 calendar days

(f) the applicable cut-off date for Event 01 is 05-May-2026, with the reference to 25-May-2026 being a typographical error in the preliminary draft

# Concurrency Analysis – Delay events Driving EOT

In accordance with the principles established in the Society of Construction Law (SCL) Delay and Disruption Protocol (2nd Edition, 2017), and consistent with the FIDIC contractual framework, concurrent delay is recognized where two or more independent delay events arise at different times but their effects are felt, in whole or in part, at the same time. The impact periods of Event 01 (Batch 02) and Event 02 overlap between 6 July 2027 and 6 September 2027, representing a concurrent overlap of sixty-two (62) calendar days.

Under the FIDIC Conditions of Contract, the Contractor is entitled to an extension of time for Employer-risk events that delay completion, subject to the proper application of concurrent delay principles. The gross delay is the arithmetic sum of individual EOT impacts (117 + 71 = 188 days).

The concurrent overlap of 62 days is absorbed to prevent double-counting of overlapping impacts.

Accordingly, the Net Extension of Time entitlement is calculated as follows:

Net EOT = Gross Delay − Concurrent Overlap

Net EOT = 188 days − 62 days

Net EOT = 126 calendar days

This calculation is independently verified by reference to the difference between the earliest baseline Project Finish Date (12 May 2027, per Event 01 — Batch 01) and the final actual Project Finish Date (15 September 2027), which yields an identical result of 126 calendar days.

# RESPONSE TO THE ENGINEER'S REQUEST

The following matrix identifies where each item requested in the Engineer's Letter Ref. BD-ACEPM-SAMCO-LET-039 is addressed in this response.

| Item | Engineer's Request | Contractor's Response | Location |
| --- | --- | --- | --- |
| 1 | Comprehensive notice and correspondence register | Relevant event correspondence is identified, classified by event, and linked to its contractual purpose. Compliance is addressed by reference to the evidenced occurrence / awareness date and the governing signed record. | Section 3 / Annex A |
| 2 | Cause-and-effect analysis, particularly for steel delay | Cause, affected activities, logic linkage, mitigation and resulting schedule effect are set out by event. | Section 4 / Annex B |
| 3 | Detailed TIA for each event | The adopted contemporaneous fragnet-insertion methodology and event-level before / after results are provided. | Sections 5 and 6 / Annex C |
| 4 | Comparison against Section Milestones and Time for Completion | Milestone and Project Finish movements are stated for each event based on the available P6 comparison outputs. | Section 6 |
| 5 | Clarification of 05-May-2026 versus 25-May-2026 | 05-May-2026 is confirmed as the Batch 02 Part 02 complete-delivery milestone in the current steel records; 25-May-2026 is not relied upon. | Section 7 |

# CONTRACTUAL AND METHODOLOGICAL BASIS

The Contractor's entitlement position is founded on the Contract as amended by the Contract Agreement, Appendix to Tender and Particular Conditions, which take precedence in accordance with the agreed order of priority.

| Provision | Contractual Relevance | Application to Interim Claim No. 1 |
| --- | --- | --- |
| Appendix to Tender Item 20 / Sub-Clause 14.2 | Advance payment is structured to include 70% steel supplied by the Employer according to the approved Programme. | Supports the Employer-supply basis of EV01. |
| Sub-Clause 4.20 | Employer's Equipment and Free-Issue Material; Employer responsibility for shipment and delivery to Site, subject to the Contractor's look-ahead and quantity obligations. | Primary contractual basis for EV01, subject to proof of timely requisition, approved programme demand and delivery shortfall. |
| Sub-Clause 1.9 | Delayed Drawings or Instructions, as amended to include approvals and approved Programme timing. | Primary basis where delayed or revised information / approval prevented or disrupted planned work. |
| Sub-Clauses 13.1 and 13.3 | Right to Vary and Variation Procedure. | Relevant where revised IFC information or instructed MEP embedded works changed scope, sequence, quantities, rework or execution requirements. |
| Sub-Clause 8.4 | Extension of Time for Completion; requires critical-path reliance, an accepted delay-analysis method and demonstrated mitigation. | Governing contractual basis for the time entitlement assessment. |
| Sub-Clause 20.1 | Contractor's Claims, including monthly claim accounting and the contract treatment of concurrent delay. | Governs claim preservation, particulars and concurrency treatment. |
| Sub-Clause 3.5 | Determinations. | Provides the determination mechanism for the Engineer's assessment of time and cost entitlement. |

# NOTICE AND CORRESPONDENCE POSITION

The Contractor has maintained a progressive correspondence trail for the steel-supply, revised-IFC / design-information, MEP-variation and technical-clarification matters. Annex A identifies the critical records relevant to Interim Claim No. 1.

The legal function of each letter must be determined from its actual signed content, date of occurrence / awareness, proof of receipt and the continuing nature of the event. Accordingly, the Contractor does not rely on the register title alone as proof of contractual compliance. The signed letters, transmittals, meeting records, delivery records and monthly claim accounts are the governing contemporaneous evidence.

NOTICE COMPLIANCE POSITION The Contractor's position is that the events developed progressively and, in several instances, continued through partial delivery, repeated non-delivery, successive design revisions, delayed responses and unresolved technical constraints. The correspondence records were issued on a continuing basis to notify the Engineer, reserve entitlement, request action and document mitigation. Exact time-bar compliance is to be read against the evidenced occurrence / awareness date for each occurrence, not against an assumed date that is unsupported by the project records.

# 4. CAUSE-AND-EFFECT ANALYSIS

## 4.1 EV01 - Employer's Late Supply of Free-Issue Reinforcement Steel

| CONTRACTUAL CAUSE Employer-supplied steel required in accordance with the approved Programme and Contractor requisitions. | FACTUAL EVENT Late, partial and sequenced deliveries against the required batches. | OPERATIONAL EFFECT Insufficient steel availability for identified reinforcement-fixing activities. | SCHEDULE EFFECT Delay transferred through linked structural logic to milestones and Project Finish where critical. |
| --- | --- | --- | --- |

The steel correspondence and delivery records indicate that Batch 02 was required by 27-Nov-2025 in the amount of 726 tons. The current delivery summary records 371.115 tons delivered on 14-Feb-2026 and 355.840 tons delivered on 05-May-2026. The native EV01 Batch 02 fragnet models the partial-delivery milestone on 15-Feb-2026 and the complete-delivery milestone on 05-May-2026.

The affected work packages include reinforced-concrete raft / footing, walls, columns, cores, slabs, beams, stairs, ramps and water-tank reinforcement activities. The detailed activity IDs and names are listed in Annex B and the native P6 comparison. The Contractor's mitigation, including self-procurement and resequencing where recorded, must be credited in the assessment and does not relieve the Employer of the consequences of any proven late free-issue supply.

## 4.2 EV02 - Revised IFC Drawings Causing Rework and Delay

| PLANNED BASIS Timely, coordinated and construction-ready IFC / design information. | EVENT Revised or conflicting IFC information requiring review, redesign, resubmission or re-approval. | OPERATIONAL EFFECT Affected shop drawings and dependent construction activities could not proceed as planned or required rework. | SCHEDULE EFFECT Fragnet logic delayed affected submissions / approvals and transferred impact to the critical path. |
| --- | --- | --- | --- |

The EV02 model uses a data date of 17-Mar-2026 and a revised IFC issue milestone of 18-Mar-2026. The fragnet introduces the reworked shop-drawing resubmission and re-approval cycle for the affected structural elements across Buildings B1-B4. The event is assessed under Sub-Clause 1.9 and, where the revision changed scope, sequence or required rework, Sub-Clauses 13.1 and 13.3, subject in all cases to demonstrated critical-path impact under Sub-Clause 8.4.

## 4.3 EV03 - Engineer-Instructed Additional MEP Embedded Works

| INSTRUCTION Additional / instructed embedded pipes, sleeves, puddle flanges and conduits. | ADDED PROCESS Engineering submittal, approval, procurement, fabrication and installation. | CIVIL INTERFACE Embedded items required before associated raft / wall concrete works. | CURRENT TIA RESULT No movement of Project Finish in the before / after comparison presently available. |
| --- | --- | --- | --- |

The current EV03 before / after comparison shows no movement in the Ground Works Finish or Project Finish milestones. Accordingly, the present schedule output does not demonstrate an EOT quantum for EV03. This does not determine or waive the Contractor's separate variation, valuation, disruption or cost entitlement, nor does it prevent a later time assessment if the event's actual impact changes or further evidence demonstrates critical delay.

## 4.4 EV04 - Delayed RFI Response / Technical Clarification

The current TIA summary shows no movement in the relevant milestones before and after the EV04 fragnet. No EOT days are therefore advanced in this response solely on the basis of the current comparison. The Contractor nevertheless reserves its rights in respect of any proven actual delay, disruption, resequencing or cost consequences supported by the final RFI log, response dates, affected activities and contemporaneous programme records.

# 5. TIME IMPACT ANALYSIS METHODOLOGY

The Contractor has applied a contemporaneous fragnet-insertion Time Impact Analysis consistent with the express requirements of Sub-Clause 8.4 and recognised CPM delay-analysis practice. The methodology is event-specific and does not treat the gross duration of an event as the EOT quantum.

| Step | Control | Application |  |
| --- | --- | --- | --- |
| 1 | Select contemporaneous base schedule | Use the accepted / approved update immediately preceding the event, with its actual progress and data date preserved. |  |
| 2 | Validate status and settings | Confirm calendars, constraints, actual dates, remaining durations, out-of-sequence settings and schedule options. |  |
| 3 | Define event fragnet | Model only the event and its immediate consequences using measurable activities supported by records. |  |
| 4 | Connect to affected work | Tie the fragnet to the first activity genuinely prevented or delayed and preserve the original downstream logic. |  |
| 5 | Recalculate CPM | Schedule the unimpacted and impacted models using consistent settings and retain the before / after outputs. |  |
| 6 | Measure incremental movement | Measure the movement of the contractual milestone / Project Finish and the associated float / path change. |  |
| 7 | Review mitigation and concurrency | Credit proven mitigation and assess other causes operating on the same critical path during the same period. |  |
| 8 | Separate time and cost | Determine time entitlement first; assess prolongation, disruption and concurrent-period cost treatment separately. |  |
| CRITICAL-PATH TEST A delay event is EOT-driving only to the extent that the schedule model demonstrates an incremental delay to the contractual completion milestone through the contemporaneous critical / longest path after considering float, progress, mitigation and other concurrent causes. |  |  |

# 6. EVENT-LEVEL TIA RESULTS AND MILESTONE COMPARISON

The following table reproduces the event-level milestone values currently available from the before / after comparison records. These are event-level outputs and shall not be arithmetically added without a chronological consolidation and overlap / concurrency review.

| Event | Data Date | Milestone | Before Fragnet | After Fragnet | Movement | Assessment |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| EV01 - Steel Batch 01 | 31-Oct-2025 | Project Finish | 14-Apr-2027 | 14-Apr-2027 | 0 days | No demonstrated Project Finish impact |  |
| EV01 - Steel Batch 02 | 26-Nov-2025 | Project Finish | 12-May-2027 | 06-Sep-2027 | +117 days | EOT-driving event-level impact |  |
| EV01 - Steel Batch 03 | 13-Jan-2026 | Project Finish | 27-May-2027 | 03-Jul-2027 | +37 days | Event-level impact; consolidation treatment to be reconciled |  |
| EV02 - Revised IFC | 17-Mar-2026 | Project Finish | 06-Jul-2027 | 15-Sep-2027 | +71 days | EOT-driving event-level impact |  |
| EV03 - Additional MEP | See note below | Project Finish | 29-Apr-2027 | 29-Apr-2027 | 0 days | No demonstrated Project Finish impact |  |
| EV04 - Delayed RFI / Clarification | 14-Feb-2026 | Project Finish | 06-Jul-2027 | 06-Jul-2027 | 0 days | No demonstrated Project Finish impact |  |
| EV03 DATA-DATE CONTROL The EV03 comparison sources presently contain conflicting data-date references: 16-Nov-2025 in the detailed JSON comparison and 25-Dec-2025 in the TIA summary workbook. Because the before / after milestone result is identical, this discrepancy does not change the current zero-day Project Finish movement; however, the data-date field must be reconciled in the native P6 issue set before final technical reliance. |  |  |  |  |  |  |

## 6.1 Consolidated EOT Position

Interim Claim No. 1 states a net EOT position of 126 calendar days. The Contractor maintains and preserves the claim position pending issue of a single reconciled cumulative schedule exhibit. The Contractor does not rely on a simple sum of the event-level movements, because such an approach may double-count periods already reflected in later schedule updates or periods of genuine critical concurrency.

For transparency, the detailed EV02 comparison presently available records an after-fragnet Project Finish of 15-Sep-2027 and an incremental movement of 71 calendar days.

# 7. CLARIFICATION OF THE CUT-OFF / MILESTONE DATE

In response to Item 5 of the Engineer's letter, the Contractor clarifies the date references as follows:

| Date | Correct Description | Clarification |
| --- | --- | --- |
| 26-Nov-2025 | EV01 Batch 02 P6 Data Date | This is the schedule status date used for the EV01 Batch 02 before / after TIA comparison. |
| 14-Feb-2026 | Recorded delivery date - Batch 02 Part 01 | Date stated in the steel correspondence / delivery summary. |
| 15-Feb-2026 | EV01 fragnet partial-delivery milestone | The native schedule model places the partial-delivery milestone on the following calendar day. |
| 05-May-2026 | Batch 02 Part 02 complete-delivery milestone | This is the correct date used in the current steel delivery summary and EV01 fragnet. It is an event / delivery milestone, not the P6 Data Date. |

# 8. REQUEST FOR THE ENGINEER'S ASSESSMENT AND DETERMINATION

The Contractor respectfully requests the Engineer to review the submitted particulars and supporting records, assess the demonstrated event-level impacts in accordance with Sub-Clauses 3.5, 8.4, 13.3 and 20.1 as applicable, and proceed with an interim determination of the Contractor's Extension of Time entitlement.

Where the Engineer considers any specific record or particular to remain insufficient, the Contractor requests that the Engineer identify the precise event, activity, period and missing record so that the matter may be addressed efficiently without delaying assessment of the substantiated portions of Interim Claim No. 1.

# 9. RESERVATION OF RIGHTS

This response is submitted for interim assessment only and strictly without prejudice. It is not the Contractor's final claim or an exhaustive statement of all facts, causes, effects, costs or entitlements. The Contractor reserves the right to amend, supplement and further particularise its claim as events develop and further records become available. No omission, cooperation, mitigation, continuation of work or partial submission shall constitute a waiver, release, admission or limitation of any right or entitlement under the Contract or applicable law.

# ANNEX A - CRITICAL NOTICE AND CORRESPONDENCE REGISTER

The following register identifies the principal correspondence records presently relied upon for EV01 and EV02. The signed letter, proof of receipt, occurrence / awareness record and monthly claim account remain the governing documents for notice-compliance assessment.

| Reference | Date | Event | Subject | Notice / Record Purpose |
| --- | --- | --- | --- | --- |
| STR-010 | 25-Sep-2025 | EV01 | Supply of reinforcement steel for the project | Initial steel supply request / programme dependency |
| STR-011 | 29-Sep-2025 | EV01 | Request to Reduce First Reinforcement Steel Delivery | Adjusted first delivery request due to site constraints |
| STR-025 | 26-Nov-2025 | EV01 | Supply of Reinforcement Steel - Second Delivery | Batch 02 request and supply dependency |
| STR-042 | 06-Jan-2026 | EV01 | Supply of Reinforcement Steel - Third Delivery | Batch 03 request |
| STR-044 | 15-Jan-2026 | EV01 | Delay in Supplying Reinforcement Steel | Delay notification and reservation of EOT rights |
| STR-048 | 26-Jan-2026 | EV01 | Follow-up on Delay of Reinforcement Steel Delivery | Warning of stock depletion and continuing impact |
| STR-051 | 07-Feb-2026 | EV01 | Reinforcement Steel Supply Status and EOT Entitlement | Notice of depletion / non-delivery and EOT position |
| STR-053 | 24-Feb-2026 | EV01 | Reinforcement Steel Order No. 2 Delay | Records late / irregular supply and time / cost position |
| STR-062 | 31-Mar-2026 | EV01 | Follow-up on Reinforcement Steel Delivery | Records partial delivery and outstanding supply |
| STR-069 | 19-Apr-2026 | EV01 | Follow-up on Reinforcement Steel Supply and Cumulative Project Impact | Cumulative delay, mitigation and reservation |
| STR-015 | 06-Oct-2025 | EV02 | Reminder to Submit Final Package and Signed Hard Copies | Request for complete IFC package |
| STR-019 | 26-Oct-2025 | EV02 | Request for Complete Set of IFC Drawings | Requests full IFC package following observed changes |
| STR-026 | 30-Nov-2025 | EV02 | Reply of Design Review | Requests resolution of design-review comments |
| STR-029 | 07-Dec-2025 | EV02 | Design Review | Records design-modification position |
| STR-030 | 11-Dec-2025 | EV02 | Re: Design Review | Records incomplete design packages and request for complete IFC |
| STR-032 | 11-Dec-2025 | EV02 | Request for Complete Package for Coordination - TRA-007 | Requests missing coordination package |
| STR-034 | 17-Dec-2025 | EV02 | Re: Design Review | Seeks decision on design criteria / review outcome |
| STR-040 | 05-Jan-2026 | EV02 | Continuation of Works and Final Written Instructions | Records continuation basis and reserves rights |
| STR-057 | 11-Mar-2026 | EV02 / EV04 | Delayed Technical Responses and Outstanding Coordinated Drawings | Notice of missing information / delayed responses |
| STR-063 | 31-Mar-2026 | EV02 | Comparison of Design Issued 18-Mar-2026 vs 27-Oct-2025 | Identifies discrepancies and resulting rework / delay position |
| STR-064 | 02-Apr-2026 | EV04 | Delay in Technical Clarifications | Notice of RFI / clarification delay |
| STR-066 | 11-Apr-2026 | EV02 / EV04 | Modifications Included in Latest Design Package | Records modification and delayed clarification effect |
| STR-067 | 16-Apr-2026 | EV02 | Design Discrepancies and Impact on Time and Cost | Formal reservation in respect of conflicting structural information |
| STR-071 | 27-Apr-2026 | EV01 / EV02 | Early Warning & Notification of Fact pursuant to Sub-Clause 20.1 | Consolidated notice of steel and design constraints and reservation of entitlement |

## ANNEX A1 - NOTICE COMPLIANCE ASSESSMENT BASIS

| Event | Occurrence / Awareness Basis | Principal Notice Trail | Compliance Position |
| --- | --- | --- | --- |
| EV01 - Steel | Approved requirement dates, each partial / non-delivery, depletion of available stock and resulting inability to proceed. | STR-010, STR-025, STR-042, STR-044, STR-048, STR-051, STR-053, STR-062, STR-069 and STR-071 | Continuing and progressively developing event. Timeliness is to be assessed against each evidenced occurrence / awareness date and the signed receipt record. |
| EV02 - Revised IFC | Issue of revised information, discovery of discrepancies, rework / resubmission requirement and subsequent unresolved design matters. | STR-019, STR-026, STR-029, STR-030, STR-034, STR-040, STR-057, STR-063, STR-067 and STR-071 | Progressive notice trail records requests, discrepancies, effect and reservation. The governing compliance evidence is the signed letter, transmittal and associated drawing / submittal record. |
| EV03 - Additional MEP | Engineer instruction / variation, resulting added engineering-procurement-installation cycle and civil interface. | Relevant variation instructions, Contractor reservations and conditional acceptance records | Current TIA shows no Project Finish movement. Notice and commercial entitlement remain subject to the actual instruction and variation records. |
| EV04 - RFI / Clarification | Required-by date, outstanding response, actual response and identified activity prevented or delayed. | STR-057, STR-064, STR-066 and the governing RFI register | Current comparison shows no Project Finish movement. Any further time entitlement requires final RFI response dates and affected-activity proof. |

# ANNEX B - STEEL DELIVERY AND SCHEDULE-LINKAGE PARTICULARS

The following table responds to the Engineer's request for a batch / part delivery table. Quantities and delivery dates are reproduced from the current steel correspondence summary. Activity-level quantity allocation is not asserted beyond the schedule logic shown in the native P6 fragnets and the separate steel allocation / requisition records.

| Batch | Part | Required Qty. (t) | Required Date | Delivered Qty. (t) | Delivery / Status Date | Primary Schedule Linkage |
| --- | --- | --- | --- | --- | --- | --- |
| Batch 01 | Part 01 | 600.000 total batch | 03-Nov-2025 | 146.800 | 27-Oct-2025 | EV01 Batch 01 fragnet; representative footing / below-SOG reinforcement activities |
| Batch 01 | Part 02 | - | - | 440.180 | 09-Dec-2025 | EV01 Batch 01 fragnet; detailed activity allocation per steel allocation register |
| Batch 02 | Part 01 | 726.000 total batch | 27-Nov-2025 | 371.115 | 14-Feb-2026 | EV01 Batch 02 partial-delivery path and first releasable reinforcement activities |
| Batch 02 | Part 02 | - | - | 355.840 | 05-May-2026 | EV01 Batch 02 complete-delivery path; downstream B1-B4 structural reinforcement activities |
| Batch 03 | Outstanding | 512.000 | 13-Jan-2026 | 0.000 | Continuing delay in current summary | EV01 Batch 03 fragnet; detailed activity allocation to be read from native P6 / steel allocation records |

# Enclosures / Submission Index

| Enclosure | Description / Purpose |
| --- | --- |
| 1 | Revised formal response document to ACEPM LET-039. |
| 2 | Notice and correspondence register with event classification. |
| 3 | Steel batch delivery and schedule-linkage table. |
| 4 | Event-specific TIA before/after schedule comparison summary. |
| 5 | Representative affected activities and fragnet core activity tables. |
| 6 | Contractor Claim Workbook Rev03 and native Primavera P6 XER files, to the extent submitted or made available for Engineer review. |