## TIA Summary
TIME IMPACT ANALYSIS – BEFORE / AFTER FRAGNET COMPARISON
Delay Event | Data Date | Activity ID | Milestone / Activity Name | BEFORE FRAGNET |  | AFTER FRAGNET |  | Float Change (Days) | Finish Movement (Calendar Days) | Impact Assessment
|  |  |  | Total Float | Forecast Finish | Total Float | Forecast Finish
Event01
EV01 – Employer’s Late Supply of Free-Issue Reinforcement Steel - Batch01 | 2025-10-31 | KD-MS-1040 | Ground Works Finish Date | 2 | 2026-05-09 | 2 | 2026-05-09 | 0 | 0 | No demonstrated impact
EV01 – Employer’s Late Supply of Free-Issue Reinforcement Steel - Batch01 | 2025-10-31 | KD-MS-1050 | Project Finish Date | -4 | 2027-04-14 | -4 | 2027-04-14 | 0 | 0 | No demonstrated impact
EV01 – Employer’s Late Supply of Free-Issue Reinforcement Steel - Batch02 | 2025-11-26 | KD-MS-1040 | Ground Works Finish Date | -15 | 2026-05-26 | -141 | 2026-09-29 | -126 | 126 | Intermediate milestone impact
EV01 – Employer’s Late Supply of Free-Issue Reinforcement Steel - Batch02 | 2025-11-26 | KD-MS-1050 | Project Finish Date | -32 | 2027-05-12 | -149 | 2027-09-06 | -117 | 117 | EOT-driving project impact
EV01 – Employer’s Late Supply of Free-Issue Reinforcement Steel - Batch03 | 2026-01-13 | KD-MS-1040 | Ground Works Finish Date | -35 | 2026-06-15 | -82 | 2026-08-01 | -47 | 47 | Intermediate milestone impact
EV01 – Employer’s Late Supply of Free-Issue Reinforcement Steel - Batch03 | 2026-01-13 | KD-MS-1050 | Project Finish Date | -47 | 2027-05-27 | -84 | 2027-07-03 | -37 | 37 | EOT-driving project impact
EV02 – Issuance of Revised IFC Drawings Causing Rework and Delay | 2026-03-17 | KD-MS-1040 | Ground Works Finish Date | -78 | 2026-07-28 | -163 | 2026-10-21 | -85 | 85 | Intermediate milestone impact
EV02 – Issuance of Revised IFC Drawings Causing Rework and Delay | 2026-03-17 | KD-MS-1050 | Project Finish Date | -87 | 2027-07-06 | -158 | 2027-09-15 | -71 | 71 | EOT-driving project impact
EV03 – Engineer Instructed Additional MEP Embedded Works | 2025-12-25 | KD-MS-1040 | Ground Works Finish Date | -6 | 2026-05-17 | -6 | 2026-05-17 | 0 | 0 | No demonstrated impact
EV03 – Engineer Instructed Additional MEP Embedded Works | 2025-12-25 | KD-MS-1050 | Project Finish Date | -19 | 2027-04-29 | -19 | 2027-04-29 | 0 | 0 | No demonstrated impact
EV04 – Engineer’s Delayed Response to RFI and Required Technical Clarification | 2026-02-14 | KD-MS-1040 | Ground Works Finish Date | -78 | 2026-07-28 | -78 | 2026-07-28 | 0 | 0 | No demonstrated impact
EV04 – Engineer’s Delayed Response to RFI and Required Technical Clarification | 2026-02-14 | KD-MS-1050 | Project Finish Date | -87 | 2027-07-06 | -87 | 2027-07-06 | 0 | 0 | No demonstrated impact
EOT EVENT SUMMARY
Delay Event |  |  | Project Finish Before |  | Project Finish After |  | Project Finish Movement |  | Event-Level EOT Position
EV01 – Steel Batch 02 |  |  | 2027-05-12 |  | 2027-09-06 |  | 117 |  | 117 calendar days
EV02 – Revised IFC Drawings |  |  | 2027-07-06 |  | 2027-09-15 |  | 71 |  | 76 calendar days
EOT = Event02 Finish Date - Event01 Start Date [ (15-Sep-27) - (12-May-2027) ] = 126