## Slide 1
Master Dashboard
Sophia Mall Mixed-Use Development | Sophia-Mall
PROJECT
Sophia Mall Mixed-Use Development
PROJECT ID
Sophia-Mall
SECTOR
Buildings
STATUS
On Track
CONTRACT VALUE
EGP 2,100,000,000
PAID AMOUNT
EGP 809,004,000
ACTUAL PROGRESS
33.0%
PLANNED PROGRESS
31.0%
BAC / PV / EV / AC
EGP 2,100,000,000 / EGP 1,112,493,976 / EGP 1,166,846,024 / EGP 1,155,177,564
SPI / CPI
1.05 / 1.01
Generated 02 Aug 2026 | Source-controlled selected-project output