## Slide 1
Delay Analysis - Time Impact Analysis
ROYA-BIG PROJECT PHASE01 (B1-4)
Not calculated - individual indicative movements must not be summed without validated overlap, concurrency, and entitlement analysis.
EV01-B01: indicative_ready; movement=8.0;
EV01-B02: indicative_ready; movement=117.0;
EV02-IFC: indicative_ready; movement=76.0;
EV03-MEP: blocked; movement=N/A; Before/after XER internal P6 data dates are not a validated same-date comparison.