## Slide 1
Linked Executive Dashboard
Suez Tunnel Civil & MEP Works | Suez-Tunnel
PROJECT
Suez Tunnel Civil & MEP Works
PROJECT ID
Suez-Tunnel
SECTOR
Tunnels
STATUS
Delayed
CONTRACT VALUE
EGP 1,250,000,000
PAID AMOUNT
EGP 481,550,000
ACTUAL PROGRESS
35.0%
PLANNED PROGRESS
42.0%
BAC / PV / EV / AC
EGP 1,250,000,000 / EGP 563,253,012 / EGP 485,421,687 / EGP 514,546,988
SPI / CPI
0.86 / 0.94
Generated 01 Aug 2026 | Source-controlled selected-project output