## Slide 1
Linked Executive Dashboard
Nasr city-Tunnel | Nasr city-Tunnel
PROJECT
Nasr city-Tunnel
PROJECT ID
Nasr city-Tunnel
SECTOR
Tunnels
STATUS
Delayed
CONTRACT VALUE
EGP 1,845,000,000
PAID AMOUNT
EGP 177,050,000
ACTUAL PROGRESS
26.8%
PLANNED PROGRESS
31.5%
BAC / PV / EV / AC
EGP 199,500,000 / EGP 199,500,000 / EGP 196,112,167 / EGP 206,786,157
SPI / CPI
0.98 / 0.95
Generated 09 Aug 2026 | Source-controlled selected-project output